DEPARTMENT OF THE NAVY

CRITICAL INFRASTRUCTURE PROTECTION

WORKING GROUP

MONTHLY MEETING REPORT

# Date Of Meeting:	20 July 2000

Attendance

Name				Representing	Sector		Phone Nr.	Email(unclassified)

CDR Lynne Gaudreau		DON CIO	Lead		703.607.5581	gaudreau.lynne@hq.navy.mil

Dr. Mahnaz Dean		DON CIO	I & W		703.602.6280	dean.mahnaz@hq.navy.mil

Mel Rushing			DON CIO	Support	703.601.1986	rushing.mel@hq.navy.mil

Jim St. Clair			DON CIO	Support	703.412.4611	stclair.james@hq.navy.mil

Brian Kelly			HQMC/C4I	DII/C3		703.604.7038	kellybj@hqmc.usmc.mil

Steve Anderson		HQMC/I&L	Public Works	703.695.8321	andersonsp@hqmc.usmc.mil

CDR Lynne Title		N643		DII/C3		703.601.1414	title.lynn@hq.navy.mil

CDR Jeff Friar			N462		Public Works	703.601.1629	friar.jeff@hq.navy.mil

LCDR Steve Bell		N461		Public Works	703.601.1635	bell.steve@hq.navy.mil

CAPT Bob Lee		N41B		Log/Trans	703.604.9933	lee.Robert@hq.navy.mil

Carl King			MSC		Transportation	202.685.5506	carl.king@msc.navy.mil

Russ Krause			MSC		Transportation	202.685.5368	russell.Krause@msc.navy.mil

Barin Chakrabarti		NAVFAC	Public Works

CDR Tim Duvall		N20		ISR		703.614.0283	duvall.timothy@hq.navy.mil

Rick Stein			N20		ISR		703.614.7000	stein.Richard@hq.navy.mil

Bill Aldrich			ASN(FM&O)	Financial	202.685.6731	aldrich.William@fmo.navy.mil

James R. Rivera		ASN(FM&O)	Financial	202.685.6713	rivera.james@fmo.navy.mil

CAPT Tonya Concannon	DASN (IF)	Public Works	202.588.6687	concannon.tonya@hq.navy.mil

## Sectors Not Represented:	USN	USMC

Personnel			X	X

Health Affairs			X	N/A

Logistics				X

ISR					X

Report

# Introductions/Roll Call

- An updated Action Officer List will be attached to the forwarding email

- Report from the OSD CIAO Council Meeting of 10 July 2000

- Reporting – CDR Gaudreau

There seemed to be one point of this meeting.  To determine whether the sectors and services had placed the effort as core in their budgets or POM’d for this effort as "above-core.”  ASD(C3I) (Mr. Money) asked each attendee what their overall plans were, and what $$$ they had in their 2002-2007 budgets.  Almost every attendee indicated that they had between $250K and $2.5M budgeted as above core funding.

CIP is part of OPLANS and the DPG, but not budgeted for.

ASD(C3I) stated that he thinks this is much like Y2K, in that all commands need to budget for this effort, it is not just a C3I effort.  There was discussion that parts of this were already funded (like FP) and that we are merely expanding the areas of interest.  Even so, those efforts are not funded to the level that CIP can be dealt with effectively.

- Report from OSD CIPIS Working Group Meeting of 21 June 2000

- FY 00/01 Budget

- Post CIAO Council Activity included an ASD(C3I) plan to approach the Force Protection/Anti-Terrorism Program Review Group and request that CIP be added to this program’s core mission base.  The FY01 objective was reduced again to $23M, which would be dedicated to ASD(C3I) and sector requirements.  FY02 baseline has also been reduced to $31M.  This plan was scuttled when ASD(C3I) learned, from USD(C/CFO)(Dir PA&E), that programming for CIP was purposely ignored due to direction from ex-DEPSECDEF Hamre.  The current plan is for ASD(C3I) to present a decision package to DEPSECDEF Deleon while traveling together to Europe the weekend of 21 July.

- CIP Classification Manual

- Additional work is now underway to:

  - Deconflict several Security Classification Guides where information excluded from automatic downgrading is covered; and

  - Properly format the Security Classification Guide for CIP.

- Target date for completion and release is 31 July 2000

- DOD Directive 5160.54 Critical Infrastructure Protection

- Two major issues need to be resolved prior to publishing:

  - Identifying the USD(A,T&L) role; and

  - Determining DISAs relationship to the DoD Computer Emergency Response Teams (CERT).

- Target date for implementing a new publication strategy is 24 July 2000

- National Plan for Physical Infrastructure Protection

- The target date to publish a new version of the National Plan is Winter

- The new version will primarily be built around obtaining private sector inputs both from the sector coordinators and their government liaisons and from the Partnership’s cross-sector documents

- Assessments

- PACNORWEST Regional outbrief will be conducted in October

- Standard assessment protocol is still in development, Malmstrom assessment will test drive the prototype

- Oahu assessment will slide from FY01 second quarter to FY02

- Installation Outreach

- Mitretek’s Dan Schultz presented the highlights of a one hour briefing developed for educating prospective commanding officers on their responsibilities for implementing and managing a CIP program.  The service representatives reminded ASD(C3I) that the course had to be coordinated through the respective service training hierarchies.

- Defense Infrastructure Sector Assurance Plan Update

- Integrated Plan now available on the webworks site (https://webworks.bah.com)

- Six of 10 sectors are included

- Four remaining are in for final sector CIAO release

- Sector Reports

- Space

- New Director – BG Kevin T. Campbell

- Briefings on webworks:

- USSPACECOM Briefing on CIP

- Denver Research Institute Briefing on the June 00 Air and Space Survivability Workshop

- USSPACE Perspective on the Radiation Hardened Electronics Oversight Council

- Transportation

- Tier 1 list completed – 160 nodes were listed as Tier 1 – blessed by WG and forwarded to CIAO for approval

- New on webworks – Transportation DISAP extract - reformatted

- Logistics

- DISAP not final but submitted without coordination of the services (CAPT Lee has reviewed and considers the document to need major work)

- Extract is the same

- Phase I of characterization is completed for DLA and Army and is being validated internally

- Phase II characterization may start if FY00 sweep up funds are identified.  A Phase II component annex coordinating meeting will be held next week.

- DII/C3

- DISAP and extract released 10 July

- Work on Version II has begun

- New on webworks – 21st Century Assured Computing

- ISR

- No report

- (a copy of the unclassified portions of the DISAP was presented to CDR Gaudreau by CDR Duvall)

- Financial

- DISAP submitted – released for external coordination with comments due 7/31

- Health Affairs

- Doing characterization

- Extract may be submitted within one week

- Personnel

- No report

- Need service POCs identified

- Public Works

- No report

- JPO CIP Data Base – Registered Asset List (RAL)

  - Will be classified

  - Each sector will compile and maintain its own RAL

  - JPO will be a bridge for connecting RALs to OPLANs for use by CINCs and Sectors

  - Just a concept today – unfunded

- DON CIP Planning

- DON CIP Council Meeting scheduled for 26 July 2000

  - DON CIO directed postponing the meeting due to:

    - Uncertainties in the management and resourcing of the DOD plan

    - Lack of a final PACNORWEST assessment report

  - The Council will be called together after the next quarterly OSD CIAO Council Meeting

- GAO Report – Combating Terrorism

- Summary:

“Overall, military forces stationed overseas are better protected today than they were 3 years ago.  We are making recommendations to improve the vulnerability assessment reporting process, increase congressional visibility of unfounded antiterrorism/force protection projects to correct or mitigate vulnerabilities, and improve the training program for antiterrorism/force protection managers.  In written comments to our draft report, the Department of Defense agreed with our recommendations to improve the vulnerability assessment reporting process and the training program for antiterrorism/force protection managers.  The Department disagreed with our recommendation to increase congressional visibility of unfounded projects that would correct or mitigate vulnerabilities because it believes that the current planning, programming, and budgeting system is effective and ensures that high priority items are funded.”

- The URL to the report will be attached to the covering email.

- CIP Action Officer Topics

- None noted

- Next Meeting – 17 August, 1330 - 1530, Presidential Towers - 1100A

Attachments:

Updated Lists:

DON CIP Council

DON CIP Working Group

DISAP Concurrence

URLs:

GAO Report – Combating Terrorism