## COST_PRICE by GFY
COST/PRICE BY GOVERNMENT FISCAL YEAR FOR CPAF CLIN
Cost Plus Award Fee
Total
Cost Element |  | GFY 07 | GFY 08 | GFY 09 | GFY 10 | GFY 11 | GFY 12
Labor Costs
In-Plant Engr Labor Costs
Field Engr Labor Costs
Manufacturing Labor Costs
Interdivisional Transfers
Subcontracts
Subcontractor A
Subcontractor B
Subcontractor C
Subcontractor D
Materials
Purchased Parts
Raw Materials
Services
Overhead
Procurement Overhead
Fringe
In-Plant Engineering Ovhd
Field Engineering Ovhd
Manufacturing Overhead
Travel
Other Direct Costs
ODC A
ODC B
ODC C
ODC D
G&A
Subtotal Cost
FCCOM
Total Estimated Cost
Award Fee
Total Est. Cost + Fee

## Cost by WBS
Cost by WBS
WBS | [11 empty] | Prime Labor | [7 empty] | Inter-Division Transfers |  | Subcontracts | [9 empty] | Total labor |  | Materials |  |  |  | Overhead | [5 empty] | Travel | Other Direct Costs |  |  |  |  | G&A | Total | FCCOM |  |  |  | Total | Fee | Total Sell Price
L |  | L |  | L |  | L | L | L | L | WBS | CLIN No. | Engr Labor - In-Plant |  | Engr Labor - Field Site |  | Manufacturing Labor |  | Total Prime Labor |  |  |  | Subktr A |  | Subktr B |  | Subktr C |  | Subktr D |  | Tot SubKtr | [20 empty] | Est. Cost |  |  |  |  | Estimated
[10 empty] | Description |  | Labor | Labor | Labor | Labor | Labor | Labor | Labor | Labor | Labor |  | Labor |  | Labor |  | Labor |  | Labor |  | Labor |  | Labor |  | Purchased | Raw |  | Total | Procurement/ |  | Engr | Engr |  | Total | [5 empty] | Total |  | (w/o FCCOM) |  |  |  | Total | Cost
1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 |  |  | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Hours | Dollars | Parts | Materials | Services | Materials | Material | Fringe | In-Plant | Field Site | Mfg | Overhead |  | ODC A | ODC B | ODC C | ODC D | ODC |  |  | Labor | G&A | Other | FCCOM
1 | [9 empty] | MMP Upgrade System Development and Demonstration
1 | . | 1 | [7 empty] | Prime Mission Product (PMP)
1 | . | 1 | . | 1 | [5 empty] | Terminal Electronics Unit/Terminal Operator Control (TEU/TOC)
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 2 | [5 empty] | HAC/RMPE
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 3 | [5 empty] | A-kit for TEU/TOC
1 | . | 1 | . | 3 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 3 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 3 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 3 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 4 | [5 empty] | A-kit for HAC/RMPE
1 | . | 1 | . | 4 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 4 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 4 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 4 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 5 | [5 empty] | PMP Applications Software
1 | . | 1 | . | 5 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 5 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 6 | [5 empty] | PMP System Software
1 | . | 1 | . | 6 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 6 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 7 | [5 empty] | Integration, Assembly, Test and Checkout
1 | . | 2 | [7 empty] | Platform Integration
1 | . | 3 | [7 empty] | Systems Engineering/Program Management
1 | . | 3 | . | 1 | [5 empty] | System Engineering
1 | . | 3 | . | 2 | [5 empty] | Program Management
1 | . | 4 | [7 empty] | System Test and Evaluation
1 | . | 4 | . | 1 | [5 empty] | Development Test and Evaluation
1 | . | 4 | . | 2 | [5 empty] | Operational Test and Evaluation
1 | . | 1 | . | 3 | [5 empty] | Mock-ups/System Integration Labs (SILs)
1 | . | 1 | . | 4 | [5 empty] | Test and Evaluation Support
1 | . | 1 | . | 5 | [5 empty] | Test Facilities
1 | . | 5 | [7 empty] | Training
1 | . | 5 | . | 1 | [5 empty] | Equipment
1 | . | 5 | . | 2 | [5 empty] | Services
1 | . | 5 | . | 3 | [5 empty] | Facilities
1 | . | 6 | [7 empty] | Data
1 | . | 6 | . | 1 | [5 empty] | Technical Publications
1 | . | 6 | . | 2 | [5 empty] | Engineering Data
1 | . | 6 | . | 3 | [5 empty] | Management Data
1 | . | 6 | . | 4 | [5 empty] | Support Data
1 | . | 1 | . | 5 | [5 empty] | Data Depository
1 | . | 7 | [7 empty] | Peculiar Support Equipment
1 | . | 7 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 7 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 8 | [7 empty] | Common Support Equipment
1 | . | 8 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 8 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 9 | [7 empty] | Studies

## Cost by WBS by GFY
Cost by WBS by GFY
WBS
L |  | L |  | L |  | L | L | L | L | WBS | CLIN No. | GFY 07 | GFY 08 | GFY 09 | GFY 10 | GFY 11 | GFY 12 | Total
Description
1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7
1 | [9 empty] | MMP Upgrade System Development and Demonstration
1 | . | 1 | [7 empty] | Prime Mission Product (PMP)
1 | . | 1 | . | 1 | [5 empty] | Terminal Electronics Unit/Terminal Operator Control (TEU/TOC)
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 2 | [5 empty] | HAC/RMPE
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 3 | [5 empty] | A-kit for TEU/TOC
1 | . | 1 | . | 3 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 3 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 3 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 3 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 4 | [5 empty] | A-kit for HAC/RMPE
1 | . | 1 | . | 4 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 4 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 4 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 4 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 5 | [5 empty] | PMP Applications Software
1 | . | 1 | . | 5 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 5 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 6 | [5 empty] | PMP System Software
1 | . | 1 | . | 6 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 6 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 7 | [5 empty] | Integration, Assembly, Test and Checkout
1 | . | 2 | [7 empty] | Platform Integration
1 | . | 3 | [7 empty] | Systems Engineering/Program Management
1 | . | 3 | . | 1 | [5 empty] | System Engineering
1 | . | 3 | . | 2 | [5 empty] | Program Management
1 | . | 4 | [7 empty] | System Test and Evaluation
1 | . | 4 | . | 1 | [5 empty] | Development Test and Evaluation
1 | . | 4 | . | 2 | [5 empty] | Operational Test and Evaluation
1 | . | 1 | . | 3 | [5 empty] | Mock-ups/System Integration Labs (SILs)
1 | . | 1 | . | 4 | [5 empty] | Test and Evaluation Support
1 | . | 1 | . | 5 | [5 empty] | Test Facilities
1 | . | 5 | [7 empty] | Training
1 | . | 5 | . | 1 | [5 empty] | Equipment
1 | . | 5 | . | 2 | [5 empty] | Services
1 | . | 5 | . | 3 | [5 empty] | Facilities
1 | . | 6 | [7 empty] | Data
1 | . | 6 | . | 1 | [5 empty] | Technical Publications
1 | . | 6 | . | 2 | [5 empty] | Engineering Data
1 | . | 6 | . | 3 | [5 empty] | Management Data
1 | . | 6 | . | 4 | [5 empty] | Support Data
1 | . | 1 | . | 5 | [5 empty] | Data Depository
1 | . | 7 | [7 empty] | Peculiar Support Equipment
1 | . | 7 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 7 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 8 | [7 empty] | Common Support Equipment
1 | . | 8 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 8 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 9 | [7 empty] | Studies

## Labor Mix
WBS
L |  | L |  | L |  | L | L | L | L | WBS | CLIN No.
Description
1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 |  |  | Total Labor Hours | Total Prime Labor | Labor Category A | Labor Category B | Labor Category C | Labor Category D | Labor Category E | Total Subcontractor Labor | Labor Category A | Labor Category B | Labor Category C | Labor Category D | Labor Category E | Total Interdivisional Transfer | Labor Category A | Labor Category B | Labor Category C | Labor Category D | Labor Category E
1 | [9 empty] | MMP Upgrade System Development and Demonstration
1 | . | 1 | [7 empty] | Prime Mission Product (PMP)
1 | . | 1 | . | 1 | [5 empty] | Terminal Electronics Unit/Terminal Operator Control (TEU/TOC)
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 2 | [5 empty] | HAC/RMPE
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 3 | [5 empty] | A-kit for TEU/TOC
1 | . | 1 | . | 3 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 3 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 3 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 3 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 4 | [5 empty] | A-kit for HAC/RMPE
1 | . | 1 | . | 4 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 4 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 4 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 4 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 5 | [5 empty] | PMP Applications Software
1 | . | 1 | . | 5 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 5 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 6 | [5 empty] | PMP System Software
1 | . | 1 | . | 6 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 6 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 7 | [5 empty] | Integration, Assembly, Test and Checkout
1 | . | 2 | [7 empty] | Platform Integration
1 | . | 3 | [7 empty] | Systems Engineering/Program Management
1 | . | 3 | . | 1 | [5 empty] | System Engineering
1 | . | 3 | . | 2 | [5 empty] | Program Management
1 | . | 4 | [7 empty] | System Test and Evaluation
1 | . | 4 | . | 1 | [5 empty] | Development Test and Evaluation
1 | . | 4 | . | 2 | [5 empty] | Operational Test and Evaluation
1 | . | 1 | . | 3 | [5 empty] | Mock-ups/System Integration Labs (SILs)
1 | . | 1 | . | 4 | [5 empty] | Test and Evaluation Support
1 | . | 1 | . | 5 | [5 empty] | Test Facilities
1 | . | 5 | [7 empty] | Training
1 | . | 5 | . | 1 | [5 empty] | Equipment
1 | . | 5 | . | 2 | [5 empty] | Services
1 | . | 5 | . | 3 | [5 empty] | Facilities
1 | . | 6 | [7 empty] | Data
1 | . | 6 | . | 1 | [5 empty] | Technical Publications
1 | . | 6 | . | 2 | [5 empty] | Engineering Data
1 | . | 6 | . | 3 | [5 empty] | Management Data
1 | . | 6 | . | 4 | [5 empty] | Support Data
1 | . | 1 | . | 5 | [5 empty] | Data Depository
1 | . | 7 | [7 empty] | Peculiar Support Equipment
1 | . | 7 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 7 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 8 | [7 empty] | Common Support Equipment
1 | . | 8 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 8 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 9 | [7 empty] | Studies

## Labor Hours
LABOR HOURS BY WBS
WBS
L |  | L |  | L |  | L | L | L | L | WBS |  |  | Prime | Prime | Prime | Prime
[10 empty] | Description | CLIN No. | Total | Total | Engr | Engr | Mfg | Inter Div | Total
1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 |  |  | Hours | Hours | In-Plant | Field | Hours | Transfer | SubKtrs | SubKtr A | SubKtr B | SubKtr C | SubKtr D | SubKtr E | SubKtr F | SubKtr G | SubKtr H
1 | [9 empty] | MMP Upgrade System Development and Demonstration
1 | . | 1 | [7 empty] | Prime Mission Product (PMP)
1 | . | 1 | . | 1 | [5 empty] | Terminal Electronics Unit/Terminal Operator Control (TEU/TOC)
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 2 | [5 empty] | HAC/RMPE
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 3 | [5 empty] | A-kit for TEU/TOC
1 | . | 1 | . | 3 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 3 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 3 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 3 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 4 | [5 empty] | A-kit for HAC/RMPE
1 | . | 1 | . | 4 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 4 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 4 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 4 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 5 | [5 empty] | PMP Applications Software
1 | . | 1 | . | 5 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 5 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 6 | [5 empty] | PMP System Software
1 | . | 1 | . | 6 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 6 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 7 | [5 empty] | Integration, Assembly, Test and Checkout
1 | . | 2 | [7 empty] | Platform Integration
1 | . | 3 | [7 empty] | Systems Engineering/Program Management
1 | . | 3 | . | 1 | [5 empty] | System Engineering
1 | . | 3 | . | 2 | [5 empty] | Program Management
1 | . | 4 | [7 empty] | System Test and Evaluation
1 | . | 4 | . | 1 | [5 empty] | Development Test and Evaluation
1 | . | 4 | . | 2 | [5 empty] | Operational Test and Evaluation
1 | . | 1 | . | 3 | [5 empty] | Mock-ups/System Integration Labs (SILs)
1 | . | 1 | . | 4 | [5 empty] | Test and Evaluation Support
1 | . | 1 | . | 5 | [5 empty] | Test Facilities
1 | . | 5 | [7 empty] | Training
1 | . | 5 | . | 1 | [5 empty] | Equipment
1 | . | 5 | . | 2 | [5 empty] | Services
1 | . | 5 | . | 3 | [5 empty] | Facilities
1 | . | 6 | [7 empty] | Data
1 | . | 6 | . | 1 | [5 empty] | Technical Publications
1 | . | 6 | . | 2 | [5 empty] | Engineering Data
1 | . | 6 | . | 3 | [5 empty] | Management Data
1 | . | 6 | . | 4 | [5 empty] | Support Data
1 | . | 1 | . | 5 | [5 empty] | Data Depository
1 | . | 7 | [7 empty] | Peculiar Support Equipment
1 | . | 7 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 7 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 8 | [7 empty] | Common Support Equipment
1 | . | 8 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 8 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 9 | [7 empty] | Studies

## Labor Hrs by WBS by GFY
Labor Hours by WBS by GFY
WBS
L |  | L |  | L |  | L | L | L | L | WBS | CLIN No. |  | GFY 07 |  |  | GFY 08 |  |  | GFY 09 |  |  | GFY 10 |  |  | GFY 11 |  |  | GFY 12 |  |  | Total Labor Hours
Description
1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 |  |  | Prime | SubKtr | Total | Prime | SubKtr | Total | Prime | SubKtr | Total | Prime | SubKtr | Total | Prime | SubKtr | Total | Prime | SubKtr | Total | Prime | SubKtr | Total
1 | [9 empty] | MMP Upgrade System Development and Demonstration
1 | . | 1 | [7 empty] | Prime Mission Product (PMP)
1 | . | 1 | . | 1 | [5 empty] | Terminal Electronics Unit/Terminal Operator Control (TEU/TOC)
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 2 | [5 empty] | HAC/RMPE
1 | . | 1 | . | 1 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 1 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 1 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 1 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 3 | [5 empty] | A-kit for TEU/TOC
1 | . | 1 | . | 3 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 3 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 3 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 3 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 4 | [5 empty] | A-kit for HAC/RMPE
1 | . | 1 | . | 4 | . | 1 |  |  |  | Hardware (details 1…n)
1 | . | 1 | . | 4 | . | 2 |  |  |  | Application Software/FW (details CSCI/FW 1…n)
1 | . | 1 | . | 4 | . | 3 |  |  |  | System Software (CSCI 1…n)
1 | . | 1 | . | 4 | . | 4 |  |  |  | Integration, Assembly, Test and Checkout
1 | . | 1 | . | 5 | [5 empty] | PMP Applications Software
1 | . | 1 | . | 5 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 5 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 6 | [5 empty] | PMP System Software
1 | . | 1 | . | 6 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 6 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 7 | [5 empty] | Integration, Assembly, Test and Checkout
1 | . | 2 | [7 empty] | Platform Integration
1 | . | 3 | [7 empty] | Systems Engineering/Program Management
1 | . | 3 | . | 1 | [5 empty] | System Engineering
1 | . | 3 | . | 2 | [5 empty] | Program Management
1 | . | 4 | [7 empty] | System Test and Evaluation
1 | . | 4 | . | 1 | [5 empty] | Development Test and Evaluation
1 | . | 4 | . | 2 | [5 empty] | Operational Test and Evaluation
1 | . | 1 | . | 3 | [5 empty] | Mock-ups/System Integration Labs (SILs)
1 | . | 1 | . | 4 | [5 empty] | Test and Evaluation Support
1 | . | 1 | . | 5 | [5 empty] | Test Facilities
1 | . | 5 | [7 empty] | Training
1 | . | 5 | . | 1 | [5 empty] | Equipment
1 | . | 5 | . | 2 | [5 empty] | Services
1 | . | 5 | . | 3 | [5 empty] | Facilities
1 | . | 6 | [7 empty] | Data
1 | . | 6 | . | 1 | [5 empty] | Technical Publications
1 | . | 6 | . | 2 | [5 empty] | Engineering Data
1 | . | 6 | . | 3 | [5 empty] | Management Data
1 | . | 6 | . | 4 | [5 empty] | Support Data
1 | . | 1 | . | 5 | [5 empty] | Data Depository
1 | . | 7 | [7 empty] | Peculiar Support Equipment
1 | . | 7 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 7 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 8 | [7 empty] | Common Support Equipment
1 | . | 8 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 8 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 9 | [7 empty] | Studies

## Software Info
Software Info: Sizing, Schedule & Historical Information by CSCI
|  | SIZE | [6 empty] | HISTORICAL DATA |  | SCHEDULE (MTHS REQ)
CSCI/FW | SIZING METHOD | NEW | EXISTING | DELETED | UNUSED | % REDES | % REIMP | % RETEST | ANALOGY | PROD RANGE | REQ | DESIGN/ CODE/ TEST | CSCI INTEG | S/W LANGUAGE
CSCI 1
CSCI 2
CSCI 3
CSCI 4
CSCI 5
CSCI 6
CSCI 7
CSCI 8
CSCI 9
CSCI 10
…
FW1
FW2
…

## Software analogy
Software analogy: historical metrics
| PROGRAM NAME | SIZE | [13 empty] | SCHEDULE (MTHS REQ) | [5 empty] | VARIANCE EXPLANATION
|  | AT BID | [6 empty] | CURRENT | [6 empty] | AT BID |  |  | CURRENT
CSCI/FW |  | NEW | EXISTING | DELETED | UNUSED | % REDES | % REIMP | % RETEST | NEW | EXISTING | DELETED | UNUSED | % REDES | % REIMP | % RETEST | REQ | DESIGN/ CODE/ TEST | CSCI INTEG | REQ | DESIGN/ CODE/ TEST | CSCI INTEG
CSCI 1
CSCI 2
CSCI 3
CSCI 4
CSCI 5
CSCI 6
CSCI 7
CSCI 8
CSCI 9
CSCI 10
…
FW1
FW2
…

## Prime Contractor Rates
Prime Contractor Rates by Government Fiscal Year
| 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014
Prime Contractor Labor Rates
Labor Category A
Labor Category B
Labor Category C
Labor Category D
Labor Category E
Labor Category F
Labor Category G
Labor Category H
Labor Category I
Labor Category J
Labor Category K
Labor Category L
Labor Category M
Labor Category N
Labor Category O
Labor Category P
Labor Category Q
Labor Category R
Labor Category S
Prime Contractor Indirect Rates (Percentage)
Fringe
In-Plant Engineering Overhead
Field Engineering Overhead
Manufacturing Overhead
Procurement Overhead
G&A
FCCOM - Labor
FCCOM - G&A
FCCOM - Other
ODC (Factored)
ODC (Factored)
ODC (Factored)

## Time and Material
Time and Material by Government Fiscal Year
| 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014
Prime Contractor Proposed:
Labor Category A
Labor Category B
Labor Category C
Labor Category D
Labor Category E
Subcontractor Proposed:
Labor Category A
Labor Category B
Labor Category C
Labor Category D
Labor Category E
Interdivisional Transfer Proposed:
Labor Category A
Labor Category B
Labor Category C
Labor Category D
Labor Category E

## Bill of Material
Bill of Material
Item (Nomenclature) | Part No. | Supplier | Quantity | Unit Price | Total Price

## B-tables
B-Tables | Proposed unit cost
B-Kit | Lot QTY | FY10 | FY11 | FY12 | FY13 | FY14
TEU/TOC upgrade B-kit (CLIN 0010)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
| 31-40 | $... | $... | $... | $... | $...
| 41-50 | $... | $... | $... | $... | $...
| 51-60 | $... | $... | $... | $... | $...
| 61-70 | $... | $... | $... | $... | $...
| 71+ | $... | $... | $... | $... | $...
HAC/RMPE upgrade B-kit (CLIN 0011)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
| 31-40 | $... | $... | $... | $... | $...
| 41-50 | $... | $... | $... | $... | $...
| 51-60 | $... | $... | $... | $... | $...
| 61-70 | $... | $... | $... | $... | $...
| 71+ | $... | $... | $... | $... | $...
A-kit | Lot QTY | FY10 | FY11 | FY12 | FY13 | FY14
TEU/TOC upgrade A-kit (CLIN 0012)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
| 31-40 | $... | $... | $... | $... | $...
| 41-50 | $... | $... | $... | $... | $...
| 51-60 | $... | $... | $... | $... | $...
| 61-70 | $... | $... | $... | $... | $...
| 71+ | $... | $... | $... | $... | $...
HAC/RMPE upgrade A-kit (CLIN 0013)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
| 31-40 | $... | $... | $... | $... | $...
| 41-50 | $... | $... | $... | $... | $...
| 51-60 | $... | $... | $... | $... | $...
| 61-70 | $... | $... | $... | $... | $...
| 71+ | $... | $... | $... | $... | $...
Spares kit | Lot QTY | FY10 | FY11 | FY12 | FY13 | FY14
TEU/TOC Spares kit (CLIN 0014)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
HAC/RMPE Spares kit (CLIN 0015)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
XDR Mod kit | Lot QTY | FY10 | FY11 | FY12 | FY13 | FY14
XDR Waveform mod kit (CLIN 0016)
| 1-10 | $... | $... | $... | $... | $...
| 11-20 | $... | $... | $... | $... | $...
| 21-30 | $... | $... | $... | $... | $...
| 31-40 | $... | $... | $... | $... | $...
| 41-50 | $... | $... | $... | $... | $...
| 51-60 | $... | $... | $... | $... | $...
| 61-70 | $... | $... | $... | $... | $...
| 71+ | $... | $... | $... | $... | $...

## Procurement Summary at BEQ
Procurement Summary
| FY10 | FY11 | FY12 | FY13 | FY14 | Total
TEU/TOC B-kit (CLIN 0010)
BEQ Qty | 7 | 27 | 16 |  |  | 50
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
TEU/TOC A-kit (CLIN 0012)
BEQ Qty | 7 | 27 | 16 |  |  | 50
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
HAC/RMPE B-kit (CLIN 0011)
BEQ Qty |  | 36 | 10 |  |  | 46
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
HAC/RMPE A-kit (CLIN 0013)
BEQ Qty |  | 36 | 10 |  |  | 46
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
TEU/TOC Spares kit (CLIN 0014)
BEQ Qty | 2 | 8 | 7 |  |  | 17
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
HAC/RMPE Spares kit (CLIN 0015)
BEQ Qty |  | 13 | 6 |  |  | 19
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
XDR Waveform Mod kits (CLIN 0016)
BEQ Qty |  |  | 72 |  |  | 72
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 0 | 0 | 0 | 0 | 0 | 0

## Unconstrained Procurement
Unconstrained Procurement Summary
| FY10 | FY11 | FY12 | FY13 | FY14 | Total
TEU/TOC B-kit (CLIN 0010)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
TEU/TOC A-kit (CLIN 0012)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
HAC/RMPE B-kit (CLIN 0011)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
HAC/RMPE A-kit (CLIN 0013)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
TEU/TOC Spares kit (CLIN 0014)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
HAC/RMPE Spares kit (CLIN 0015)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
XDR Waveform Mod kits (CLIN 0016)
Proposed Qty | [5 empty] | 0
Proposed Unit Cost
Total | 0 | 0 | 0 | 0 | 0 | 0
Grand Total | 0 | 0 | 0 | 0 | 0 | 0

## Price Track
Price Track (Format X)
WBS | [11 empty] | Final Proposal Revision (FPR) Changes
L |  | L |  | L |  | L | L | L | L | WBS
Description
1 |  | 2 |  | 3 |  | 4 | 5 | 6 | 7 |  | Initial Price | Schedule Shift | Spec. Changes | Change in Materials | Changes in Labor Hours (Specify) | Changes in Labor or Burden Rates | Change in Profit Rate | Other Changes | Other Changes | Other Changes | Total Changes | FPR Price
1 | [9 empty] | MMP Upgrade System Development and Demonstration
1 | . | 1 | [7 empty] | Prime Mission Product (PMP)
1 | . | 1 | . | 1 | [5 empty] | Subsystem 1...n (Specify names)
1 | . | 1 | . | 1 | . | 1 |  |  |  | Non-recurring engineering
1 | . | 1 | . | 1 | . | 2 |  |  |  | Prototypes/EDMs
1 | . | 1 | . | 2 | [5 empty] | A-kit 1... n
1 | . | 1 | . | 2 | . | 1 |  |  |  | Non-recurring engineering
1 | . | 1 | . | 2 | . | 2 |  |  |  | Prototypes/EDMs
1 | . | 1 | . | 3 | [5 empty] | PMP Applications Software
1 | . | 1 | . | 3 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 3 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 4 | [5 empty] | PMP System Software
1 | . | 1 | . | 4 | . | 1 |  |  |  | CSCI 1 … n (Specify names)
1 | . | 1 | . | 4 | . | 2 |  |  |  | CSCI to CSCI integration and checkout
1 | . | 1 | . | 5 | [5 empty] | Integration, Assembly, Test and Checkout
1 | . | 2 | [7 empty] | Platform Integration
1 | . | 3 | [7 empty] | Systems Engineering/Program Management
1 | . | 3 | . | 1 | [5 empty] | System Engineering
1 | . | 3 | . | 2 | [5 empty] | Program Management
1 | . | 4 | [7 empty] | System Test and Evaluation
1 | . | 4 | . | 1 | [5 empty] | Development Test and Evaluation
1 | . | 4 | . | 2 | [5 empty] | Operational Test and Evaluation
1 | . | 1 | . | 3 | [5 empty] | Mock-ups/System Integration Labs (SILs)
1 | . | 1 | . | 4 | [5 empty] | Test and Evaluation Support
1 | . | 1 | . | 5 | [5 empty] | Test Facilities
1 | . | 5 | [7 empty] | Training
1 | . | 5 | . | 1 | [5 empty] | Equipment
1 | . | 5 | . | 2 | [5 empty] | Services
1 | . | 5 | . | 3 | [5 empty] | Facilities
1 | . | 6 | [7 empty] | Data
1 | . | 6 | . | 1 | [5 empty] | Technical Publications
1 | . | 6 | . | 2 | [5 empty] | Engineering Data
1 | . | 6 | . | 3 | [5 empty] | Management Data
1 | . | 6 | . | 4 | [5 empty] | Support Data
1 | . | 1 | . | 5 | [5 empty] | Data Depository
1 | . | 7 | [7 empty] | Peculiar Support Equipment
1 | . | 7 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 7 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 8 | [7 empty] | Common Support Equipment
1 | . | 8 | . | 1 | [5 empty] | Test and Measurement Equipment
1 | . | 8 | . | 2 | [5 empty] | Support and Handling Equipment
1 | . | 9 | [7 empty] | Studies

## CLIN Summary
CLIN Summary (in millions)
CLIN No. | Type | Title | GFY 07 | GFY 08 | GFY 09 | GFY 10 | GFY 11 | GFY 12 | GFY 13 | GFY 14 | Total
0001 | CPAF | MMP UPGRADE DESIGN/DEVELOPMENT (3600 FUNDS)
0002 | CPAF | MMPU CPAF DATA
0003 |  | reserved
0004 |  | reserved
0005 | FFP | MMP UPGRADE FFP DATA
0006 | FFP | MMP UPGRADE SDD PHASE ADDITIONAL DATA
0007 | T&M | MMP UPGRADE SDD PHASE ENGINEERING SERVICES
0008 | T&M | MMP UPGRADE SDD PHASE TIME AND MATERIALS DATA
0009 | CPAF | AWARD FEE (3600 FUNDS)
0010 | FFP* | TEU/TOC UPGRADE B-KIT
0011 | FFP* | HAC/RMPE UPGRADE B-KITS
0012 | FFP* | TEU/TOC UPGRADE A-KIT
0013 | FFP* | HAC/RMPE UPGRADE A-KIT
0014 | FFP* | TEU/TOC SPARES KIT
0015 | FFP* | HAC/RMPE SPARES KIT
0016 | FFP* | XDR WAVEFORM MODIFICATION KITS
0017 | CPFF | REFURBISHMENT OF WEAPON SYSTEM OPERATIONAL TEST ARTICLES
0018 | T&M | MMP UPGRADE PRODUCTION PHASE INSTALLATION SUPPORT AND ENGINEERING SVS
0019 | T&M | INTERIM CONTRACTOR SUPPORT
0020 | FFP | SUPPORT EQUIPMENT
0021 | CR | TRAVEL
T & M ceiling amounts are established by the government.
FFP* | FFP at BEQ quantities.