## Recap
ProEnergy EPC
Job Description: |  |  | "Two GE Frame VII FA's"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  |  | 2010-09-20
I. Balance of Plant
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 173.3333 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 173.3333 | calc
|  | 103 | Concrete Foundations |  |  | 13750.7407 | 2750.1481 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 1329.7778 | calc
|  | 106 | Gravel - Sand |  |  |  | 439.5926 | calc
|  | 107 | Structual Steel |  |  |  | 311 | calc
|  | 108 | Fencing |  |  |  | 151.5 | calc
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 5328.6852 |  | 5328.6852
| 200 Buildings | [5 empty] | 976 | calc | 976
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 2292.29 | calc
|  | 320 | Pipe, Valves & Fitting labor |  |  | 29160 | 1691.837 | calc
|  | 330 | Mechanical Subcontractor |  |  | 24885 | 1443.8053 | calc
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 1100 | calc
[7 empty] | 6527.9323 |  | 6527.9323
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 4554.95 | calc
|  | 420 | Substation Equipment |  |  |  | 0 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 43801.56 | 2541.3271 | calc
|  | 440 | Substation Subcontractor |  |  | 0 | 0 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 1300 | calc
|  | 460 | Conduit, Cable & Wire Labor |  |  | 31104 | 1804.6261 | calc
[7 empty] | 10200.9032 |  | 10200.9032
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 360 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 4050 | 234.9774 | calc
[7 empty] | 594.9774 |  | 594.9774
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 720 | calc
|  | 620 | Telephone System |  |  |  | 20 | calc
|  | 630 | Public Address System |  |  |  | 20 | calc
|  | 640 | TV / Security |  |  |  | 20 | calc
[7 empty] | 780 |  | 780
700 Plant Erection
|  | 700 | Plant Erection |  |  | 104846.4 | 6083.0938 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 237846.96 | 6083.0938 |  | 6083.0938
| 800 Equipment Rental | [5 empty] | 2528.24 | calc | 2528.24
| 900 Painting | [5 empty] | 465 | calc | 465
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 429.782 | calc
|  | 1002 | Ocean/Air Freight |  |  |  | 0 | plgd /1000
|  | 1003 | Destination Inland Freight |  |  |  | 0 | plgd /1000
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 429.782 |  | 429.782
| 1100 Site Costs | [5 empty] | 790.6 | calc | 790.6
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 1680 | calc
|  | 1202 | Local Eng |  |  |  | 770 | calc
[7 empty] | 2450 |  | 2450
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 1854 | calc
|  | 1320 | Inspectors |  |  |  | 570 | calc
[7 empty] | 2424 |  | 2424
| 1400 Travel & Perdiem | [5 empty] | 1642.5 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 1642.5 |  | 1642.5
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 1 lot | 0 | 6000 | plgd /1000
|  | 1502 | Fire Water |  | 20 | 2200 | 44 | plgd /1000
|  | 1503 | Gas Compressor |  | 30 | 2200 | 66 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 20 | 2000 | 40 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 120 | 2000 | 240 | plgd /1000
|  | 1507 | Controls Rep |  | 90 | 2000 | 180 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 6570 |  | 6570
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 30 | plgd /1000
|  | 1602 | Concrete |  |  |  | 120 | plgd /1000
|  | 1603 | X Ray |  |  |  | 120 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 200 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 25 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 495 |  | 495
| 1700 Legal | [5 empty] | 0 | plgd /1000 | 0
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 600 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 600 |  | 600
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 2000 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 3% | 10387.24 | 311.6172 | calc
|  | 2150 | Labor Contingency |  | 3% | 13799.6666 | 413.99 | calc
[7 empty] | 2725.6072 |  | 2725.6072
[5 empty] | BOP Cost |  |  |  | 51612.3209
[5 empty] | % Markup |  |  | 25% | 12903.0802
[5 empty] | BOP Sales Price |  |  |  | 64515.4012
II. Gas Turbine Cost
| 5010 Cost of Gas Turbine Generator | [5 empty] | 0 | plgd
| 5030 Cost of modification | [5 empty] | 0 | plgd
| 5040 Gas Turbine Freight | [5 empty] | 0 | plgd
[5 empty] | Cost of GTG |  | 0 |  | 0
[5 empty] | Markup |  |  | 25% | 0
[5 empty] | Gas Turbine Sales Price |  |  |  | 0
[5 empty] | Total Plant Sales Price |  |  |  | 64515.4012

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | ANACO Power Plant | [5 empty] | Date: |  | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [5 empty] | Quote No: |  | T 1025 - 2
Location: |  | Venn | [5 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | "L" | "W" | "D" | Square | Square | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Clearing/Grubbing |  |  | 650 | 800 | 1 | 520000 | 19259.2593 | 9 | 173333.3333
2
3 | Demolition
4
5 | Special Shoring
6
7 | Drainage
8
9 | Dewatering
10
11 | Railroads
12
13 | Docks
14
15 | Tunnels
16
17 | Wells
18
19 | Containment Systems
20
21 | Concrete Work
22
23 | Masonry
24
25
26
27
28
29
30
31
32
33
34
173.3333

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | ANACO Power Plant | [6 empty] | Date: |  | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [6 empty] | Quote No: |  | T 1025 - 2
Location: |  | Venn | [6 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
7 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
8 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
9 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
10
11 | Main Plant Area |  |  |  | 650 | 800 | 1 | 520000 | 19259.2593 | 9 | 173333.3333
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
13 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 173.3333

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | ANACO Power Plant | [7 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [7 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [7 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy
1 | POWER ISLAND | [8 empty] | 1000
2 | GT Generators |  |  | 2 | 90 | 20 | 7 | 25200 | 933.3333 | 1000 | 933333.3333 | 4666.6667
3 | Exhaust Stack |  |  | 2 | 35 | 35 | 4 | 9800 | 362.963 | 1000 | 362962.963 | 1814.8148
4 | Leg A and B |  |  | 2 | 55 | 7 | 4 | 3080 | 114.0741 | 1000 | 114074.0741 | 570.3704
5 | Exhaust Gas Blowers |  |  | 2 | 14 | 14 | 2 | 784 | 29.037 | 1000 | 29037.037 | 145.1852
6 | Air Processing Skid |  |  | 2 | 8 | 6 | 1 | 96 | 3.5556 | 1000 | 3555.5556 | 17.7778
7 | Gas Valve Module |  |  | 2 | 12 | 9 | 1 | 216 | 8 | 1000 | 8000 | 40
8 | Mech Elect Vault |  |  | 2 | 40 | 23 | 1.5 | 2760 | 102.2222 | 1000 | 102222.2222 | 511.1111
9 | Accessory Module |  |  | 2 | 20 | 18 | 2 | 1440 | 53.3333 | 1000 | 53333.3333 | 266.6667
10 | Fuel Gas Heater Module |  |  | 2 | 15 | 15 | 1 | 450 | 16.6667 | 1000 | 16666.6667 | 83.3333
11 | 15KV Breaker Module |  |  | 2 | 20 | 15 | 1 | 600 | 22.2222 | 1000 | 22222.2222 | 111.1111
12 | 15KV Aux Transformers |  |  | 2 | 20 | 15 | 2 | 1200 | 44.4444 | 1000 | 44444.4444 | 222.2222
13 | BALANCE OF PLANT
14 | LO Fin Fan Coolers |  |  | 8 | 15 | 15 | 1 | 1800 | 66.6667 | 1000 | 66666.6667 | 333.3333
15 | LO Cooling Water Pumps |  |  | 4 | 8 | 8 | 2 | 512 | 18.963 | 1000 | 18962.963 | 94.8148
16 | ESD Valve |  |  | 2 | 3 | 3 | 1 | 18 | 0.66667 | 1000 | 666.6667 | 3.3333
17 | Fuel Gas Scrubber |  |  | 2 | 5 | 6 | 1 | 60 | 2.2222 | 1000 | 2222.2222 | 11.1111
18 | Fuel Gas Regulator Skid |  |  | 2 | 18 | 8 | 1 | 288 | 10.6667 | 1000 | 10666.6667 | 53.3333
19 | Fuel Gas GTG Meter Skid |  |  | 1 | 18 | 6 | 1 | 108 | 4 | 1000 | 4000 | 20
20 |  |  |  | 0 | 15 | 15 | 2 | 0 | 0 | 1000 | 0 | 0
21 | Gas Compressors |  |  | 2 | 45 | 15 | 4 | 5400 | 200 | 1000 | 200000 | 1000
22 | Compressor Cooling Tower |  |  | 1 | 20 | 20 | 2 | 800 | 29.6296 | 1000 | 29629.6296 | 148.1481
23 |  |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 1000 | 0 | 0
24 | Waste Oil/Water Storage Tank |  |  | 1 | 15 | 12 | 1 | 180 | 6.6667 | 1000 | 6666.6667 | 33.3333
25 | Oily Water Separator |  |  | 1 | 30 | 20 | 0.5 | 300 | 11.1111 | 1000 | 11111.1111 | 55.5556
26 | Lubricant Storage Area |  |  | 1 | 45 | 30 | 1 | 1350 | 50 | 1000 | 50000 | 250
27 | Instrument Air Comp Skid |  |  | 1 | 10 | 8 | 1 | 80 | 2.963 | 1000 | 2962.963 | 14.8148
28 | Pipe Rack Stanchons |  |  | 40 | 2.5 | 2.5 | 6 | 1500 | 55.5556 | 1000 | 55555.5556 | 277.7778
29 | 18KV ISO Bus Stanchons |  |  | 10 | 5 | 5 | 5 | 1250 | 46.2963 | 1000 | 46296.2963 | 231.4815
30 | Fire Water Pump Skid |  |  | 1 | 15 | 15 | 1 | 225 | 8.3333 | 1000 | 8333.3333 | 41.6667
31 | Area Light Poles |  |  | 8 | 2.5 | 3 | 5 | 300 | 11.1111 | 1000 | 11111.1111 | 55.5556
32 | Aux Trans fndns |  |  | 5 | 10 | 15 | 1.5 | 1125 | 41.6667 | 1000 | 41666.6667 | 208.3333
33 | Cable Trenches see est |  |  | 2 | 180 | 15 | 0.5 | 2700 | 100 | 1000 | 100000 | 500
34 | Water Treatment Plant |  |  | 1 | 20 | 15 | 1 | 300 | 11.1111 | 1000 | 11111.1111 | 55.5556
35 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
36 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
37 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
38 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
39 | Demin Stg Tanks ____ Gal |  |  | 1 | 15 | 15 | 2 | 450 | 16.6667 | 1000 | 16666.6667 | 83.3333
40 | Demin Forwarding Pump Skid |  |  | 1 | 8 | 4 | 1 | 32 | 1.1852 | 1000 | 1185.1852 | 5.9259
41 | Chemical Injection Skid |  |  | 1 | 8 | 5 | 1 | 40 | 1.4815 | 1000 | 1481.4815 | 7.4074
42 | Raw Water Tank Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
43 | Fire Water Tank base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
44 | Emer Generator Base |  |  | 1 | 23 | 10 | 2 | 460 | 17.037 | 1000 | 17037.037 | 85.1852
45
46 | BUILDINGS
47 | Control Bldg/Office |  |  | 1 | 80 | 100 | 1 | 8000 | 296.2963 | 1000 | 296296.2963 | 1481.4815
48 | Warehouse/Maintenance |  |  | 1 | 80 | 100 | 0 | 0 | 0 | 1000 | 0 | 0
49 | Water Treatment Bldg |  |  | 0 | 150 | 75 | 1 | 0 | 0 | 1000 | 0 | 0
50 | Gas Compressor Bldg |  |  | 0 | 120 | 45 | 1 | 0 | 0 | 1000 | 0 | 0
51 | Electrical Bldg |  |  | 0 | 42 | 20 | 1 | 0 | 0 | 1000 | 0 | 0
52 | Pwr Blk Utility Bldg's |  |  | 1 | 30 | 45 | 1 | 1350 | 50 | 1000 | 50000 | 250
53 | Substation Bldg |  |  | 0 | 15 | 12 | 1 | 0 | 0 | 1000 | 0 | 0
54 | Steam Turbine Hall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
55 | Liquid Fuel Unloading |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
56 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
57 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
58
59 | SUBSTATION
60 | GSU Transformer |  |  | 0 | 30 | 30 | 2 | 0 | 0 | 1000 | 0 | 0
61 | (___)KV SF6 Circuit Breaker |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 1000 | 0 | 0
62 | (___)KV Disc Switch w/ Stand |  |  | 0 | 10 | 15 | 1 | 0 | 0 | 1000 | 0 | 0
63 | Dead End Tower |  |  | 0 | 15 | 10 | 3 | 0 | 0 | 1000 | 0 | 0
64 | Transmission Line Poles |  |  | 0 | 5 | 5 | 20 | 0 | 0 | 1000 | 0 | 0
65 | Insulator Support Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
66 | PT Support Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
67 | Static Pole Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0
68
69
70 |  |  | Total Cost of Foundations | [5 empty] | 2750.1481 |  | 2750.1481 | 13750.7407
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | ANACO Power Plant | [7 empty] | Date: |  | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [7 empty] | Quote No: |  | T 1025 - 2
Location: |  | Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description | [7 empty] | Cu | Price | Total
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls | [8 empty] | 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | ANACO Power Plant | [6 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [6 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 850 | 0
2 | Gen Removal Areas |  |  | 50 | 30 | 1 | 1500 | 55.5556 | 850 | 47222.2222
3 | Turbine Removal Areas |  |  | 50 | 30 | 1 | 1500 | 55.5556 | 850 | 47222.2222
4 | Entry Ways |  |  | 40 | 25 | 1 | 1000 | 37.037 | 850 | 31481.4815
5 | Walk ways |  |  | 180 | 6 | 0.5 | 540 | 20 | 850 | 17000
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 850 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 1800 | 20 | 0.7 | 25200 | 933.3333 | 850 | 793333.3333
12 | Parking Lot |  |  | 250 | 100 | 0.5 | 12500 | 462.963 | 850 | 393518.5185
13 | [6 empty] | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 1329.7778
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | ANACO Power Plant | [7 empty] | Date: |  | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [7 empty] | Quote No: |  | T 1025 - 2
Location: |  | Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price
1
2 | Main Plant Area (less substa) |  |  | 1 | 670 | 800 | 0.5 | 268000 | 9925.9259 | 16477.037 | 25 | 411925.9259
3
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 25 | 0
5
6 | Substation |  |  | 0 | 400 | 150 | 1 | 0 | 0 | 0 | 25 | 0
7
8 | Road ways |  |  | 1 | 1800 | 20 | 0.5 | 18000 | 666.6667 | 1106.6667 | 25 | 27666.6667
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | [8 empty] | 439.5926

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | ANACO Power Plant | [5 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [5 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | # of | Qty | Price | Total
No. | [5 empty] | Lbs / Tons |  |  | Price
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 20 | 3500 | 70000
4 | [8 empty] | 0
5 | 18 KV ISO Phase Bus Stanchons | [5 empty] | 20 | 3000 | 60000
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 2 | 18000 | 36000
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 1 | 40000 | 40000
10
11 | Overhead Crane (Maint. Bldg) (_15_) Ton | [5 empty] | 1 | 40000 | 40000
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 1 | 15000 | 15000
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 50000 | 50000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 311

## 108 Fence
FENCING
[5 empty] | (1,000's) |  |  | 108
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 2500 | 15 | 37500
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 3000 | 23 | 69000
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 0 | 0 | 0
6
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 4 | 4000 | 16000
10 | Motor Operated Double Gate(s) |  |  |  |  | 2 | 7000 | 14000
11 | Personnel Gate(s) |  |  |  |  | 6 | 500 | 3000
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 2 | 6000 | 12000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Fencing |  |  |  |  | 151.5

## 109 Architectual
ARCHITECTUAL TREATMENT
[5 empty] | (1,000's) |  |  | 109
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1
2 | Trees and/or Shrubs - Revegetation
3 | Boundry Road |  |  |  |  | 0 | 0 | 0
4 | Within site |  |  |  |  | 0 | 0 | 0
5 | [5 empty] | 0 | 0 | 0
6 | [5 empty] | 0 | 0 | 0
7 | [5 empty] | 0 | 0 | 0
8 | [7 empty] | 0
9 | [7 empty] | 0
10 | [7 empty] | 0
11 | [7 empty] | 0
12 | [7 empty] | 0
13 | [7 empty] | 0
14 | [7 empty] | 0
15 | [7 empty] | 0
16 | [7 empty] | 0
17 | [7 empty] | 0
18 | [7 empty] | 0
19 | [7 empty] | 0
20 | [7 empty] | 0
21 | [7 empty] | 0
22 | [7 empty] | 0
23 | [7 empty] | 0
24 | [7 empty] | 0
25 | [7 empty] | 0
26 | [7 empty] | 0
27 | [7 empty] | 0
28 | [7 empty] | 0
29 | [7 empty] | 0
30 | [7 empty] | 0
31 | [7 empty] | 0
32 | [7 empty] | 0
33 | [7 empty] | 0
34 | [7 empty] | 0
35 | [7 empty] | 0
36 | [7 empty] | 0
37 | [7 empty] | 0
38 | [7 empty] | 0
39
40 |  |  | Total Cost of Arch Treatment |  |  |  |  | 0

## 110 Evap Pond
EVAPORATION POND
|  |  |  | (1,000's) | [5 empty] | 110
Project Name: |  | ANACO Power Plant | [6 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [6 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yard | cy | Price
1 | Storm Water Evap Pond |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0
2 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
7
8
9
10
11 | [8 empty] | Price
12 | [6 empty] | sf |  | sf
13 | Liner |  |  | 0 | 0 |  | 0 |  | 3 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36 | [9 empty] | 0

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | ANACO Power Plant | [5 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [5 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price
1 | Fuel Gas Compressor Shed |  |  |  | 60 | 60 | 3600 | 45 | 162000
2 | Control/Office |  |  |  | 120 | 80 | 9600 | 60 | 576000
3 | Water Treatment |  |  |  | 0 | 0 | 0 | 0 | 0
4 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0
5 | Warehouse/Maintenance |  |  |  | 70 | 80 | 5600 | 40 | 224000
6 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0
7 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0
9 | Pump Room |  |  |  | 0 | 0 | 0 | 0 | 0
10 | Control Room |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 20 | 20 | 400 | 35 | 14000
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 976

## 310, 320, 330 & 340 Mechanical
MECHANICAL
(1,000's)
310 & 330
Project Name: | ANACO Power Plant | ANACO Power Plant | [8 empty] | Date: | 40441 | 40441
Customer: | EFACEC Engenharia, S.A. | EFACEC Engenharia, S.A. | [8 empty] | Quote No: | T 1025 - 2 | T 1025 - 2
Location: | Venn | Venn | [8 empty] | Est By: | WTS | WTS
Bid Due Date: | 2010-09-20 | 2010-09-20
|  |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
|  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
Tag Number | Prime Movers and Associated Equipment | Cost Code |  |  |  | 3% |  | 9
025GTG100 | Gas Turbine Generator 100, 200, 300, … | 310.03 | 2 | 0 | 0 | 0 | 0 | 9 | 12 | 90 | 19440 | 58.0191 | 1127891.304
025DEG100 | Diesel Engine Generator 100, 200,300, … | 310.04 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025EG100 | Emergency Generator 100, 200, … | 310.05 | 1 | 250000 | 250000 | 7500 | 7500 | 9 | 4 | 5 | 180 | 58.0191 | 10443.438
025ES100 | Exhaust Stack Generator 100 | 310.06 | 2 | 0 | 0 | 0 | 0 | 9 | 3 | 4 | 216 | 58.0191 | 12532.1256
025CTLO100 | Lube Oil Cooling Tower for generator | 310.07 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025FFLLO 100 | Lube Oil Fin Fan Coolers for generator | 310.09 | 8 | 0 | 0 | 0 | 0 | 9 | 4 | 4 | 1152 | 58.0191 | 66838.0032
025GRT100 | Grout Gen 100, 200, 300, … | 310.1'0 | 2 | 75000 | 150000 | 4500 | 9000 | 9 | 4 | 5 | 360 | 58.0191 | 20886.876
025LBO100 | Lube Oil Gen 100, 200, 300 …. | 310.11 | 2 | 75000 | 150000 | 4500 | 9000 | 9 | 2 | 4 | 144 | 58.0191 | 8354.7504
025GTT100 | Gas Turbine Tools | 310.12 | 1 | 60000 | 60000 | 1800 | 1800 | 9 | 0 | 0 | 0 | 58.0191 | 0
025AB100 | Anchor Bolts Gen 100, 200, 300 … | 310.13 | 2 | 75000 | 150000 | 4500 | 9000 | 9 | 0 | 0 | 0 | 58.0191 | 0
[12 empty] | 58.0191 | 0
| HRSG and Assoc Equipment | [10 empty] | 58.0191 | 0
025HRSG100 | HRSG 100, 200, 300, … | 310.15 |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025BDV100 | By Pass Diverter Valve HRSG 100, 200, … | 310.16 |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
[8 empty] | 0 | 0 | 0 | 0 | 58.0191 | 0
| SCR |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025SCR100 | SCR100, 200,300 … | 310.2'0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025NHT100 | Amonia Tank 100 | 310.21 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025PNH100 | Amonia Pump 100 | 310.22 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Steam Turbine Generator |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025STG100 | Steam Turbine Generator 100 | 310.25 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025CTSTG | Cooling Tower Steam Turbine | 310.26 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025CND100 | Condenser 100 | 310.27 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025DEA100 | Dearator 100 | 310.28 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025CHISTG100 | Chemical Injection Skid STG Cooling Tower 100 | 310.29 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Inlet Air Conditioning Systems |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025CH100 | Inlet Air Chilling Package 100 | 310.31 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025EVP100 | Gas Turbine Inlet Air Evap Cooling System | 310.32 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025IFG100 | Inlet Air Fogging System 100 | 310.33 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025CTCH100 | Cooling Tower Chiller Package 100 | 310.34 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025GTCC100 | Gas Turbine Inlet Air Cooling Coils 100,200,… | 310.35 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025CHICH100 | Chemical Injection Skid Chiller Cooling Tower | 310.36 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191
| Fuel Gas System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025CGF100,200 | Compressor Fuel Gas 100, 200, … | 310.'40 | 2 | 0 | 0 | 0 | 0 | 9 | 4 | 8 | 576 | 58.0191 | 33419.0016
025CLOFF100 | Compressor Lube Oil Fin Fan 100, 200,… | 310.41 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025CLOCT100 | Compressor Lube Oil Cooling Tower 100 | 310.42 | 1 | 50000 | 50000 | 10000 | 10000 | 9 | 4 | 6 | 216 | 58.0191 | 12532.1256
025MFG100 | Meter Fuel Gas | 310.43 | 1 | 185000 | 185000 | 5550 | 5550 | 9 | 4 | 4 | 144 | 58.0191 | 8354.7504
025ESD100 | Emergency Shut Down Valve | 310.44 | 1 | 25000 | 25000 | 750 | 750 | 9 | 2 | 3 | 54 | 58.0191 | 3133.0314
025SFG100 | Scrubber Fuel Gas | 310.45 | 1 | 80000 | 80000 | 5000 | 5000 | 9 | 4 | 4 | 144 | 58.0191 | 8354.7504
025RGF100A/B | Regulator Fuel Gas Skid (2 Regulators) | 310.46 | 2 | 185000 | 370000 | 5000 | 10000 | 9 | 4 | 4 | 288 | 58.0191
025FGF100A/B | Fuel Gas Filter Skid (2 Filters) | 310.47 | 2 | 100000 | 200000 | 5000 | 10000 | 9 | 4 | 4 | 288 | 58.0191
025HGF100 | Fuel Gas Heater Skid | 310.48 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Liquid Fuel System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025SLF100 | Separator Liquid Fuel | 310.51 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025MLF100 | Meter Liquid Fuel | 310.52 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TLF | Liquid Fuel Treatment Skid | 310.53 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191
025FLF100A/B | Liquid Fuel Filter Skid ( 2 Filters) | 310.54 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191
025HLF100 | Liquid Fuel Heater Skid | 310.55 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Water System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025TRW100 | Water Treatment System (RO and EDI w/Filters) | 310.58 | 1 | 175000 | 175000 | 5250 | 5250 | 9 | 4 | 8 | 288 | 58.0191 | 16709.5008
025RWW100 | Raw Water Well | 310.59 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Pumps |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025PLF100A/B | Pump Liquid Fuel Unloading Skid (2 Pumps) | 310.61 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025PLFF100A/B | Pump Liquid Fuel Forwarding Skid (2 Pumps) | 310.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025PLFI100A/B | Pump Liquid Fuel Injection Skid (2 Pumps) | 310.63 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025PCW100A/B | Pump Cooling Water Skid (2 Pumps) | 310.64 | 2 | 0 | 0 | 0 | 0 | 9 | 3 | 4 | 216 | 58.0191
025PCHW100A/B | Pump Chilled Water Skid (2 Pumps) | 310.65 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191
025PSPT100 | Demin Water Sprint Injection Pump | 310.66 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025PWI100 | Demin Water Injection Pump | 310.67 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025PDW100,200 | Demin Water Forwarding Pump 100, 200, … | 310.68 | 1 | 60000 | 60000 | 2000 | 2000 | 9 | 3 | 4 | 108 | 58.0191 | 6266.0628
025PEV100 | Pump Evap Cooling Water | 310.69 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191
025PIFG100 | Pump Inlet Fogging Water forwarding | 310.'70 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191
025PWO100 | Pump Waste Oil | 310.71 | 1 | 15000 | 15000 | 450 | 450 | 9 | 2 | 3 | 54 | 58.0191 | 3133.0314
025PWW100 | Pump Waste Water | 310.72 | 1 | 15000 | 15000 | 450 | 450 | 9 | 2 | 3 | 54 | 58.0191 | 3133.0314
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Instrument and Service Air Compressor |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025CIA300 | Instrument Air Compressor and Dryer | 310.75 | 1 | 80000 | 80000 | 2400 | 2400 | 9 | 3 | 4 | 108 | 58.0191 | 6266.0628
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
| Oily Water Drain System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025OWS | Oily Water Separator | 310.78 | 1 | 55000 | 55000 | 5000 | 5000 | 9 | 4 | 8 | 288 | 58.0191 | 16709.5008
025TWO300 | Waste Oil Tank | 310.79 | 1 | 15000 | 15000 | 1500 | 1500 | 9 | 4 | 3 | 108 | 58.0191 | 6266.0628
025TWW300 | Waste Water Tank | 310.'80 | 1 | 15000 | 15000 | 1500 | 1500 | 9 | 4 | 3 | 108 | 58.0191 | 6266.0628
|  | 310.81 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
| Tanks | 310.82 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TRW100 | Tank Raw Water | 310.83 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TFW100 | Tank Fire Water | 310.84 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TRFW100 | Tank Raw/Fire Water | 310.85 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TDW100 | Tank Demin Water | 310.86 | 1 | 25000 | 25000 | 1500 | 1500 | 9 | 3 | 5 | 135 | 58.0191 | 7832.5785
025TROW100 | Tank RO Water | 310.87 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TEVW100 | Tank Evap Water | 310.88 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
025TDF1 | DFO Tank | 310.89 | 1 | 15000 | 15000 | 1500 | 1500 | 9 | 3 | 4 | 108
| Fire Water System |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58.0191 | 0
025FWP100 | Fire Water Pump Skid | 310.91 | 1 | 150000 | 150000 | 4500 | 4500 | 9 | 3 | 4 | 108 | 58.0191 | 6266.0628
025FWF100 | Fire Water Foam Skid | 310.92 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
[8 empty] | 9 | 0 | 0 | 24885
[9 empty] | 0 | 0 | 0
|  |  | 0 | 0 | 2290 | 0 | 103.65 | 9 | 0 | 0 | 0
|  | Totals |  |  | 2292.29 |  | 103.7536 | [5 empty] | 1391.5881
[8 empty] | Total Manhours |  |  | 0
[8 empty] | Times Prod Factor |  | 1.8 | 24885 | 58.0191 | 1443.8053
| Pipe Valve and fittings |  | 1 | 1100000 | 1100000 | 33000 | 33000 | 9 | 15 | 120 | 16200 | 58.0191 | 939909.42
[5 empty] | 1100 |  | 33 |  |  |  | 16200 |  | 939909.42
[8 empty] | Total Manhours |  |  | 16200
[8 empty] | Times Prod Factor |  | 1.8 | 29160 | 58.0191 | 1691.837
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 30
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 10.5
44.5
[7 empty] | Contr G&A 8% |  | 3.56
[7 empty] | Contr Mark up 15% |  | 6.675
54.735
[6 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on G134: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on J126: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL
(1,000's)
410 & 460
Project Name: |  | ANACO Power Plant | [8 empty] | Date: | 40441 | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [8 empty] | Quote No: | T 1025 - 2 | T 1025 - 2
Location: |  | Venn | [8 empty] | Est By: | WTS | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  | Generators or Prime Movers |  |  |  |  | 3% |  | 9
2 | Gas Turbine Generator |  |  | 2 | 0 | 0 | 0 | 0 | 9 | 10 | 90 | 16200 | 58.0191 | 939909.42
3 | Emergency Generator |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 4 | 10 | 360 | 58.0191 | 20886.876
4 | Water Treatment System |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 4 | 5 | 180 | 58.0191 | 10443.438
5 | Diesel Fuel Treatment System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
6 | Steam Turbine Generator |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
7 | SCR |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
8 | HRSG |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
9 | Chiller |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
10 | Cooling Tower |  |  | 1 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
11 | Evap Cooling System |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
12 | [8 empty] | 9 | 0 | 0 | 0 | 58.0191 | 0
13 |  | 15 KV Equipment | [10 empty] | 58.0191
14 | 025SWGR100 | GTG Breaker | 410-'10 | 2 | 550000 | 1100000 | 50000 | 100000 | 9 | 4 | 6 | 432 | 58.0191 | 25064.2512
15 | 025SWB15-100 | 15 KV Switchboard | 410-11 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
16 | 025SE15-100 | 15 KV Disconnect | 410-12 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
17 | 025FS-100 | Fused Switch | 410-13 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
18 | 025CB15-100 | Cable Bus | 410-14 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
19 | 025DB15 | Bus Duct | 410-15 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
20 | 025ISOD18-100 | Iso Phase Bus | 410-16 | 2 | 450000 | 900000 | 20000 | 40000 | 9 | 4 | 12 | 864 | 58.0191 | 50128.5024
21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
22 |  | 5 KV Equipment |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
23 | 025B5D-100 | Breaker Distribution 5 KV | 410-'20 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
24 | 025FS5-100 | Fused Switch 5 KV | 410-21 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
25 | 025WSB5-100 | Switchboard 5 KV | 410-22 | 2 | 290000 | 580000 | 10000 | 20000 | 9 | 4 | 4 | 288 | 58.0191 | 16709.5008
26 | 025MCC5-100 | Motor Control Center 5 KV | 410-23 | 1 | 60000 | 60000 | 2000 | 2000 | 9 | 3 | 3 | 81 | 58.0191
27 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
28 |  | 480 Volt Equipment |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
29 | 025DP-1 | Distribution Panel 480 V | 410-27 | 4 | 125000 | 500000 | 1500 | 6000 | 9 | 2 | 3 | 216 | 58.0191 | 12532.1256
30 | 025MCC-1 | Motor Control Center 480 V | 410-28 | 6 | 20000 | 120000 | 1000 | 6000 | 9 | 2 | 5 | 540 | 58.0191 | 31330.314
31 | 025MCC-100,200 | Motor Control Center 480 V GTG | 410-29 | 2 | 0 | 0 | 0 | 0 | 9 | 2 | 10 | 360 | 58.0191 | 20886.876
32 | 025LP-1,2, | 480/277 V Lighting Panel | 410-30 | 1 | 600 | 600 | 150 | 150 | 9 | 2 | 2 | 36 | 58.0191 | 2088.6876
33 | 025ALP - 1,2,3 | Area Lighting Pole | 410-31 | 8 | 1500 | 12000 | 150 | 1200 | 9 | 2 | 2 | 288 | 58.0191 | 16709.5008
34 | 025AFL - 1… | Area Lighting Flood Light | 410-32 | 24 | 500 | 12000 | 50 | 1200 | 9 | 2 | 0.1 | 43.2 | 58.0191 | 2506.4251
35 | [12 empty] | 58.0191
36 |  | Aux Transformers |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
37 | 025AXT15/5-1 | Aux Transformer 15/5 KV | 410-36 | 2 | 375000 | 750000 | 22500 | 45000 | 9 | 4 | 8 | 576 | 58.0191 | 33419.0016
38 | 025AXT15/480-1 | Aux Transformer 15KV/480 Volt | 410-37 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
39 | 025AXT5/480-1 | Aux Transformer 5KV/480 | 410-38 | 4 | 80000 | 320000 | 5000 | 20000 | 9 | 3 | 4 | 432 | 58.0191 | 25064.2512
40 | 025AXT480/120-1 | Aux Transformer 480/120/208 Volt | 410-39 | 4 | 5000 | 20000 | 600 | 2400 | 9 | 2 | 4 | 288 | 58.0191 | 16709.5008
41 | [12 empty] | 58.0191
42 |  | BOP 120/208 Volt Equipment |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
43 | 025P120-1 | Lighting Panel 120/208 | 410-43 | 4 | 400 | 1600 | 48 | 192 | 9 | 2 | 2 | 144 | 58.0191 | 8354.7504
44 | 025LCT - 1 | Lighting Contactor | 410-44 | 2 | 150 | 300 | 40 | 80 | 9 | 2 | 1 | 36 | 58.0191 | 2088.6876
45 | 025CATH - 100 | Cathodic Protection GTG 100 | 410-45 | 2 | 20000 | 40000 | 1200 | 2400 | 9 | 4 | 15 | 1080 | 58.0191 | 62660.628
46 | 025LGT - 100 | Lightning Protection GTG 100 | 410-46 | 2 | 20000 | 40000 | 1200 | 2400 | 9 | 4 | 15 | 1080 | 58.0191 | 62660.628
47 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
48 |  | DC Battery Chargers and Batteries |  | 0 | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
49 | 025CHG125-100 | 125 VDC Battery Charger | 410-50 | 2 | 15000 | 30000 | 500 | 1000 | 9 | 2 | 2 | 72 | 58.0191 | 4177.3752
50 | 025BATT125-100 | 125 VDC Battery | 410-51 | 1 | 22000 | 22000 | 2500 | 2500 | 9 | 2 | 5 | 90 | 58.0191 | 5221.719
51 | 025CHG24-100 | 24 VDC Battery Charger | 410-52 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
52 | 025BATT24-100 | 24 VDC Battery | 410-53 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
53 | 025UPS-100 | UPS System | 410-54 | 2 | 3000 | 6000 | 180 | 360 | 9 | 2 | 2 | 72 | 58.0191 | 4177.3752
54 | 025DP125 | DC Dist Panel | 410-55 | 1 | 450 | 450 | 50 | 50 | 9 | 2 | 2 | 36 | 58.0191 | 2088.6876
55 | Temporary Electrical |  |  | 1 | 40000 | 40000 | 1200 | 1200 | 9 | 2 | 30 | 540 | 58.0191 | 31330.314
56 | Modular Control Building |  |  |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
57 |  |  |  |  | 0 | 0 |  | 0 | 9 | 0 | 0 | 0 | 58.0191 | 0
58 |  |  | Total Cost of Electrical Equipment |  |  | 4554950 |  | 254132 | 4554.95 |  | 254.132 |  |  |  | 24334.2 |  | 1407.1488
[13 empty] | Productivity | 1.8 | 43801.56 | 58.0191 | 2541.3271
59 | Cable Tray, Conduit, & Cable | [5 empty] | 1 | 1300000 | 1300000 | 39000 | 39000 | 9 | 12 | 160 | 17280 | 58.0191 | 1002570.048
60 | [8 empty] | 1300 |  | 39 |  |  |  | 17280 |  | 1002.57
61 | [11 empty] | Total Manhours |  |  | 17280
62 | [11 empty] | Times Prod Factor |  | 1.8 | 31104 | 58.0191 | 1804.6261
Price per hour based with all labor burdens as follows:
[14 empty] | Local Hrly Cost |  | 30
[14 empty] | Fringes |  | 2.5
[14 empty] | Small Tools |  | 1.5
[14 empty] | Labor Burden 35% |  | 10.5
44.5
[14 empty] | Contr G&A 8% |  | 3.56
[14 empty] | Contr Mark up 15% |  | 6.675
54.735
[13 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[13 empty] | 45 | 50 | 60
[13 empty] | 1.06 | 1.1 | 1.17
Note on N90: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q82: Insert Rate Here:

## 420 & 440 Substation
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | ANACO Power Plant | [12 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [12 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [12 empty] | Est By:
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | Cost Code | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | [8 empty] | 3% |  | 9
2 | 025GSU 1,2 GSU Transformer |  |  | 410-01 |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 10 | 0 | 49.2184 | 0
3 | 025152 1,2 SF6 Breaker |  |  | 410-02 |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 49.2184 | 0
4 | 025189 1,2 HV Disconnect |  |  | 410-03 |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 49.2184 | 0
5 | 025DET 1,2 Dead End Tower |  |  | 410-04 |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.05 | 0 | 49.2184 | 0
6 | 025DSP 1,2 Static Pole |  |  | 410-05 |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.5 | 0 | 49.2184 | 0
7 | Insulator Stanchons ______ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.4 | 0 | 49.2184 | 0
8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 5 | 0 | 49.2184 | 0
9 | Alum Bus ______ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.08 | 0 | 49.2184 | 0
10 | Alum Bus Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 49.2184 | 0
11 | Alum Bus End Plugs _____ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.05 | 0 | 49.2184 | 0
12 | Alum Bus Support Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.1 | 0 | 49.2184 | 0
13 | Alum Bus "V" Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.08 | 0 | 49.2184 | 0
14 | Static Wire Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 49.2184 | 0
15 | Area Lighting Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 1 | 0 | 49.2184 | 0
16 | Flood Lights, ______ Watts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 49.2184 | 0
17 | #4/0 Grounding Conductor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.03 | 0 | 49.2184 | 0
18 | 3/4"x10'-0" Ground Rods & Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0.04 | 0 | 49.2184 | 0
19 | #90 Cadweld Shots |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0.3 | 0 | 49.2184 | 0
20 | Metering CT's & CPT's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 49.2184 | 0 | 0
21 | Station Metering w/ In & Out Capabilities |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 49.2184 | 0
22 | Station Protective Relay(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 49.2184 | 0
23 | Station RTU |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 49.2184 | 0
24 | 125V DC System |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 49.2184 | 0
25 | Transmission Line Poles |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 2 | 0 | 49.2184 | 0
26 | Transmission Line Strain Insulators |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 1 | 0 | 0 | 49.2184 | 0 | 0
27 | Cable Bus, Type _____, Size _____ |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 6 | 6 | 0 | 49.2184 | 0
28 | Main Power Transformer Oil, ______ Gal |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 5 | 0 | 49.2184 | 0
29 | Main Power Transformer Dress Out & Test |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 0 | 0 | 49.2184 | 0
30 | Fiber Optic Cable w/ Messenger Cable |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 49.2184 | 0 | 0
31 | Fiber Optic Cable Fittings & Terminations |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 2 | 2 | 0 | 49.2184 | 0
32 | [10 empty] | 9 |  |  |  | 49.2184
33 | [10 empty] | 9 |  |  |  | 49.2184
34 | [10 empty] | 9 |  |  |  | 49.2184
35 | [10 empty] | 9 |  |  |  | 49.2184 | 0
36 |  |  | Total Cost of Substation Equipment |  |  |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
[12 empty] | Total Hours |  | 0
[12 empty] | Prod Factor | 1.12 | 0 | 49.2184 | 0
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 25
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 8.75
37.75
[13 empty] | Contr G&A 8% |  | 3.02
[13 empty] | Contr Mark up 15% |  | 5.6625
46.4325
[12 empty] | 45 | Hour Work Week = |  | 49.2184
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N61: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q53: Insert Rate Here:

## 510 CEMS
CEM's
[5 empty] | (1,000's) |  |  | 510
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Cems | Cost | Cost
1
2 | Rosemont CEM's Unit Most States for 1 ea GTG |  |  |  |  | 0 | 120000 | 0
3
4 | Rosemont CEM's Unit for Califormia for 1 ea GTG |  |  |  |  | 0 | 130000 | 0
5
6 | Installation Support |  |  |  |  | 0 | 18000 | 0
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of CEM's |  |  |  |  | 0

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | ANACO Power Plant | [8 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [8 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [8 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | [6 empty] | 9
2 | Instrumentation for GTG |  |  | 2 | 145000 | 290000 | 9 | 2 | 25 | 900 | 58.0191 | 52217.19
3 | [6 empty] | 9 |  |  |  | 58.0191 | 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 58.0191 | 0
5 | [6 empty] | 9 |  |  |  | 58.0191
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 9 | 4 | 15 | 0 | 58.0191 | 0
7 | [6 empty] | 9 |  |  |  | 58.0191
8 | Instrumentation for Injection Water Treatment |  |  | 1 | 20000 | 20000 | 9 | 2 | 15 | 270 | 58.0191 | 15665.157
9 | [6 empty] | 9 |  |  |  | 58.0191
10 | Instrumentation for Waste Water Treatment |  |  | 0 | 0 | 0 | 9 | 2 | 10 | 0 | 58.0191 | 0
11 | [6 empty] | 9 |  |  |  | 58.0191
12 | Instrumentation for gas compressors |  |  | 2 | 25000 | 50000 | 9 | 4 | 15 | 1080 | 58.0191 | 62660.628
13 | [6 empty] | 9 |  |  |  | 58.0191
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 9 | 4 | 5 | 0 | 58.0191 | 0
15 | [6 empty] | 9 |  |  |  | 58.0191
16 | [6 empty] | 9 |  |  |  | 58.0191
17 | [6 empty] | 9 |  |  |  | 58.0191
18 | [6 empty] | 9 |  |  |  | 58.0191
19 | [6 empty] | 9 |  |  |  | 58.0191
20 | [6 empty] | 9 |  |  |  | 58.0191
21 | [6 empty] | 9 |  |  |  | 58.0191
22 | [6 empty] | 9 |  |  |  | 58.0191
23 |  |  | Total Cost of Plant Instrumentation |  |  | 360 |  |  |  | 2250 |  | 130.543
[8 empty] | Total Hours |  | 2250
[8 empty] | Prod Factor | 1.8 | 4050 | 58.0191 | 234.9774
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 30
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 10.5
44.5
[9 empty] | Contr G&A 8% |  | 3.56
[9 empty] | Contr Mark up 15% |  | 6.675
54.735
[8 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [6 empty] | Cost | Cost
1
2 | DCS Hardware / Software |  |  |  |  | 1 | 575000 | 575000
3
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 2 | 35000 | 70000
5
6 | Documentation |  |  |  |  | 1 | 75000 | 75000
7
8 |  |  |  |  | Total DCS |  |  | 720
9
10 | PBX Communications System |  |  |  |  | 1 | 20000 | 20
11
12 | Loud Speaker System |  |  |  |  | 1 | 20000 | 20
13
14 | TV / Security System |  |  |  |  | 1 | 20000 | 20
15
16
17
[7 empty] | taxable | 645060

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | ANACO Power Plant | [6 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [6 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  |  | 9
2 | GTG Erection |  |  | 2 | 9 | 25 | 120 | 54000 | 58.0191 | 3133031.4
3 |  |  |  |  | 9 |  |  |  | 58.0191
4 | HRSG Erection |  |  | 0 | 9 | 10 | 60 | 0 | 58.0191 | 0
5 |  |  |  |  | 9 |  |  |  | 58.0191
6 | SCR Erection |  |  | 0 | 9 | 10 | 60 | 0 | 58.0191 | 0
7 |  |  |  |  | 9 |  |  |  | 58.0191
8 | Water Treatment and FW Systems |  |  | 1 | 9 | 6 | 10 | 540 | 58.0191 | 31330.314
9 |  |  |  |  | 9 |  |  |  | 58.0191
10 | Waste Water Treatment System |  |  | 0 | 9 | 6 | 20 | 0 | 58.0191 | 0
11 |  |  |  |  | 9 |  |  |  | 58.0191
12 | BOP Equip Erection |  |  | 1 | 9 | 6 | 10 | 540 | 58.0191 | 31330.314
13 |  |  |  |  | 9 |  |  |  | 58.0191
14 | Gas Compressor Erection |  |  | 2 | 9 | 6 | 15 | 1620 | 58.0191 | 93990.942
15 |  |  |  |  | 9 |  |  |  | 58.0191
16 | Evap Cooling Erection |  |  | 0 | 9 | 4 | 4 | 0 | 58.0191 | 0
17 |  |  |  |  | 9 |  |  |  | 58.0191
18 | Fire Water Pump Skid |  |  | 1 | 9 | 4 | 3 | 108 | 58.0191 | 6266.0628
19 |  |  |  |  | 9 |  |  |  | 58.0191
20 | STG Erection |  |  | 0 | 9 | 12 | 36 | 0 | 58.0191 | 0
21 |  |  |  |  | 9 |  |  |  | 58.0191
22 | LO Cooling Tower |  |  | 8 | 9 | 4 | 5 | 1440 | 58.0191 | 83547.504
23 |  |  |  |  | 9 |  |  |  | 58.0191
24 |  |  |  |  | 9 |  |  |  | 58.0191
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 58248 |  | 3379.4965
[6 empty] | Total Hours |  | 58248
[6 empty] | Prod Factor | 1.8 | 104846.4 | 58.0191 | 6083.0938
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 30
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 10.5
44.5
[7 empty] | Contr G&A 8% |  | 3.56
[7 empty] | Contr Mark up 15% |  | 6.675
54.735
[6 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | ANACO Power Plant | [6 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [6 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total
No. | [5 empty] | Units | Unit | Days | Per Day | Cost
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 2 | 60 | 120 | 6000 | 720000
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 2 | 70 | 140 | 3500 | 490000
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 2 | 60 | 120 | 2000 | 240000
6 | 2 ea Sky Tracs |  |  |  |  | 2 | 120 | 240 | 100 | 24000
7 | 2 ea Fork Lifts |  |  |  |  | 2 | 120 | 240 | 100 | 24000
8 | 1 ea Man Lift |  |  |  |  | 0 | 0 | 0 | 100 | 0
9 | 2 ea Welders |  |  |  |  | 6 | 120 | 720 | 100 | 72000
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | LO Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 8 | 3 | 24 | 2500 | 60000
40 | 2ea Fork Lifts |  |  |  |  | 8 | 4 | 32 | 70 | 2240
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 2 | 35 | 70 | 4500 | 315000
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 2 | 15 | 30 | 2000 | 60000
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 160 | 160 | 2500 | 400000
51 | 2 ea Fork Lifts |  |  |  |  | 1 | 160 | 160 | 100 | 16000
52 | 2 ea Sky Tracs |  |  |  |  | 2 | 160 | 320 | 100 | 32000
53 | 2 ea Pick ups |  |  |  |  | 2 | 160 | 320 | 100 | 32000
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 1 | 160 | 160 | 100 | 16000
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
60 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65 | Mobilization | [8 empty] | 25000
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 2856 |  | 2528.24

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Paint for GTG |  |  |  |  | 2 | 130000 | 260000
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 2 | 40000 | 80000
9
10 | Paint for BOP Equipment |  |  |  |  | 1 | 80000 | 80000
11
12 | Paint for Gas Compressor |  |  |  |  | 2 | 15000 | 30000
13
14 | Paint for Water Treatment |  |  |  |  | 1 | 15000 | 15000
15
16 | Paint for Waste Water Treatment |  |  |  |  | 0 | 15000 | 0
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 465

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 103.65 | 103.65
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 254.132 | 254.132
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 0 | 0
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 33 | 33
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 39 | 39
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 429.782

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | ANACO Power Plant | [6 empty] | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. | [6 empty] | Quote No: | T 1025 - 2
Location: |  | Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 8 | 11 | 2500 | 220000
3 | Porta Potties |  |  |  |  | 12 | 11 | 300 | 39600
4 | Water and Ice |  |  |  |  | 4 | 11 | 300 | 13200
5 | Fed X |  |  |  |  | 1 | 11 | 300 | 3300
6 | Telephone |  |  |  |  | 1 | 11 | 2500 | 27500
7 | Office Supplies |  |  |  |  | 1 | 11 | 1500 | 16500
8 | [6 empty] | 11
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 11 | 3500 | 38500
10 | Misc Items |  |  |  |  | 1 | 11 | 7000 | 77000
11 |  |  | Total Monthly Cost | [5 empty] | 435600
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 435600 |  | 435600
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 250000
21 | Cad Station | [8 empty] | 10000
22 | Computers | [8 empty] | 15000
23 | Telephone System and Satalite Dish | [8 empty] | 20000
24 | Plotter | [8 empty] | 5000
25 | Fax Machine and Printers | [8 empty] | 5000
26 | Misc equip | [8 empty] | 50000
27 | Signs | [8 empty] | 0
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 790.6

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Conceptual Engineering |  |  |  |  | 1 | 65000 | 65000
3
4 | Detailed Engineering per GTG |  |  |  |  | 2 | 650000 | 1300000
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering per Gas Compressor |  |  |  |  | 2 | 25000 | 50000
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 1 | 15000 | 15000
13
14 | Detailed Engineering for Civil and Structural Steel |  |  |  |  | 1 | 250000 | 250000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 1680

## 1210 Local Engineering
LOCAL ENGINEERING
[5 empty] | (1,000's) |  |  | 1210
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Soils & Environmental Eng |  |  |  |  | 1 | 45000 | 45000
3
4 | Civil Engineer |  |  |  |  | 9 | 25000 | 225000
5
6 | Mechanical Engineer |  |  |  |  | 10 | 25000 | 250000
7
8 | Electrical Engineer |  |  |  |  | 10 | 25000 | 250000
9
10 | Other |  |  |  |  | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Local Engineering |  |  |  |  | 770

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Mos | Per Mo | Cost
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 11 | 15000 | 165000
2 | Admin Mgr Months on Project |  |  |  |  | 11 | 8000 | 88000
3 | Scheduler |  |  |  |  | 6 | 8000 | 48000
4 | Purchasing Agent |  |  |  |  | 5 | 8000 | 40000
5 | Expediter |  |  |  |  | 5 | 5000 | 25000
6 | Home Office Logistic Coordinator |  |  |  |  | 0 | 9000 | 0
7
8
9 | [6 empty] | 366000
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 9 | 4000 | 36000
18 | Construction Mngr |  |  |  |  | 10 | 18000 | 180000
19 | Contract Cost Admin |  |  |  |  | 0 | 10000 | 0
20 | Scheduler |  |  |  |  | 5 | 8000 | 40000
21 | Mechanical Supervisor |  |  |  |  | 10 | 16000 | 160000
22 | Electrical Supervisor |  |  |  |  | 10 | 16000 | 160000
23 | Civil Supervisor |  |  |  |  | 10 | 16000 | 160000
24 | Clerks |  |  |  |  | 20 | 5000 | 100000
25 | Warehousemen |  |  |  |  | 15 | 3000 | 45000
26 | Draftsman |  |  |  |  | 8 | 9000 | 72000
27 | Security |  |  |  |  | 11 | 15000 | 165000
28 | Safety |  |  |  |  | 11 | 10000 | 110000
29 | QA/QC Mngr |  |  |  |  | 11 | 12000 | 132000
30
31
32 | [6 empty] | 1360000
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 8 | 16000 | 128000
35
36
37
38 | Training |  |  |  |  | 0 | 0 | 0
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 1854
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 8 | 15000 | 120000
47 | Mechanical __ ea ___ mos |  |  |  |  | 10 | 15000 | 150000
48 | Electrical __ ea ___ mos |  |  |  |  | 10 | 15000 | 150000
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 10 | 15000 | 150000
50
51 |  |  |  |  | Total Inspectors |  |  | 570000
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Units | Per Unit | Cost
1
2 | Project & Construciton Management
3 | R T Air Fares |  |  |  |  | 150 | 3500 | 525000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 15 | 4000 | 60000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 30 | 3000 | 90000
6 | Misc expenditures |  |  |  |  | 1 | 250000 | 250000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 3500 | 90 | 315000
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 15 | 3500 | 52500
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 810 | 200 | 162000
16 | Auto Rental for Eng Days at Site |  |  |  |  | 200 | 190 | 38000
17 | Misc Travel Expentitures |  |  |  |  | 1 | 150000 | 150000
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 1642.5
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36

## 1900 Sales Tax
SALES TAXES
[5 empty] | (1,000's) |  |  | 1900
Project Name: |  | ANACO Power Plant |  |  |  |  | Date: | 2010-09-20
Customer: |  | EFACEC Engenharia, S.A. |  |  |  |  | Quote No: | T 1025 - 2
Location: |  | Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-09-20
Item |  | Description |  |  |  | Total | State | Total
No. | [5 empty] | Cost | Tax | Taxes
1
2 | Major Mechanical Equipment |  |  |  |  | 3390 | 0.085 | 288.15
3
4 | Major Electrical Equipment |  |  |  |  | 5854.95 | 0 | 0
5
6 | Substation Equipment |  |  |  |  | 0 | 0 | 0
7
8 | DCS Eqipment |  |  |  |  | 645060 | 0 | 0
9
10 | Instrument |  |  |  |  | 360 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28 |  |  | Total Cost of Plant Sales Taxes |  |  |  |  | 0