- Table of Contents

1	PROENERGY SERVICES SITE MANAGEMENT AND VISITORS	2

2	CONTRACTORS ON SITE TODAY	2

3	DAILY OVERVIEW	2

4	CRITICAL ACTION ITEMS	2

5	MATERIALS & EQUIPMENT ISSUES	2

6	PLANNED ACTIVITIES TOMORROW	2

7	CONSTRUCTION EQUIPMENT	3

8	SAFETY ITEMS	3

9	ENGINEERING / DRAWING ISSUES	3

10	ADDITIONAL COMMENTS	3

# PROENERGY SERVICES SITE MANAGEMENT AND VISITORS

| Carlos Gaset |  |
| --- | --- |

# CONTRACTORS ON SITE TODAY

Company			   Direct Labor 	  Supervision    	  Management

| ProEnergy Services |  |  | 1 |
| --- | --- | --- | --- |
| Eripe Lamilara | 74 | 5 | 2 |
| Doca | 41 | 3 | 1 |
| Paciffic Rim | 4 | 5 | 1 |

# DAILY OVERVIEW

- Working on Rebar tank T2203,T2201

- Cutting and bending re-bar.

- Tank ring T2102 ready for concrete.

- Tying rebar generator foundation.

- Installing rebar warehouse foundation.

- Installing main post on fence.

- Iseven our tank contractor is setting up camp.

# CRITICAL ACTION ITEMS

# MATERIALS & EQUIPMENT ISSUES

- Still waiting for bricks for main containment fence, promise from last week.

# PLANNED ACTIVITIES TOMORROW

- Poured concrete on tank ring T2102

- Set towers and poured bottom beams in perimeter wall.

- Start laying conduit on turbine foundation.

- Continue cutting and bending re-bar

- Work on turbine foundation

- Set rebar on warehouse foundation

# CONSTRUCTION EQUIPMENT

- 1 – 50T crane

- 1 –  forklifts.

- 1 – Backhoe

- 1 – 20’ truck

- 4 air compressors

- Company Truck

- 2 generators

# SAFETY ITEMS

Nothing to notify.

# ENGINEERING / DRAWING STATUS

Drawing status

| Discipline | Required | Released for Construction | % Complete |
| --- | --- | --- | --- |
| Civil – Underground |  | 39 |  |
| Electrical |  | 30 |  |
| Piping |  | 0 |  |
| Mechanical |  | 110 ( all tanks ) |  |
| Instrument / Controls |  | 0 |  |

# ADDITIONAL COMMENTS

- Pacific Rim Engineering has put a hold on the fill of the inside of the tank ring until further notice.