## Sheet1
Month | Payment Milestones | $ US Dollars | BsF | %
0 | Contract Signnining, Star Engineering and procurement | 2103285 | 478800 | 30
1 | Start Fabrication, continue procurement | 1051642.5 | 239400 | 15
2 | Complete engineering, continue fabrication, start receiving components | 1051642.5 | 239400 | 15
3 | Continue fabrication and receiving components, procure consumables, start packing materials for shipment | 701095 | 159600 | 10
4 | Complete fabrication, finish receiving and packing components and miscellaneous materials | 701095 | 159600 | 10
5 | Ship material to Venezuela, receive and deliver to site, start assembly of systems | 701095 | 159600 | 10
6 | Complete assembly of systems | 350547.5 | 79800 | 5
7 | Complete commissioning & start-up and provide documentation | 350547.5 | 79800 | 5
| TOTAL | 7010950 | 1596000 | 100