## Sheet1
Month | Payment Milestones | $ US Dollars | BsF | %
0 | Contract Signnining, Star Engineering and procurement | 2734500 | 622440 | 30
1 | Start Fabrication, continue procurement | 1367250 | 311220 | 15
2 | Complete engineering, continue fabrication, start receiving components | 1367250 | 311220 | 15
3 | Continue fabrication and receiving components, procure consumables, start packing materials for shipment | 911500 | 207480 | 10
4 | Complete fabrication, finish receiving and packing components and miscellaneous materials | 911500 | 207480 | 10
5 | Ship material to Venezuela, receive and deliver to site, start assembly of systems | 911500 | 207480 | 10
6 | Complete assembly of systems | 455750 | 103740 | 5
7 | Complete commissioning & start-up and provide documentation | 455750 | 103740 | 5
| TOTAL | 9115000 | 2074800 | 100