- FIRST CLAUSE: OBJECT

CONTRACTOR agrees to execute for CORPOELEC at all costs, at its exclusive account and with its own elements the work of "ENGINEERING, ASSEMBLING, INSTALLATION, TESTS, CONNECTION AND STARTUP OF TWO (2) GENERATOR EQUIPMENTS MANUFACTURED BY GENERAL ELECTRIC MODEL 7EA IN THE FACILITIES OF ENELVEN AT THE THERMOELECTRIC  COMPLEX  GENERAL RAFAEL URDANETA, IN MARACAIBO, EDO. ZULIA” with power output and heat rate equivalent to ninety percent (90%) of the ISO power corrected for the equipment installation site conditions, which henceforth will be called THE WORK, which shall be executed with the quality, the technical specifications, conditions, prices and deadlines established in this Contract.  (DDW:  It should actually read “110% of ISO Heat Rate”.)

- CLAUSE TWO: SCOPE OF WORK

The scope of work includes the following activities:

- Location of equipment (layout).

- Conformation of the soil.

- Development of engineering, procurement and construction of foundations, pipes, drains and connections to the main and auxiliary equipment of TWO (2) TURBO GENERATOR UNITS MODEL GE 7EA .

- Development of engineering, procurement and construction of piping, equipment, stands, accessories for the proper installation and mechanical assembly of TWO (2) TURBO GENERATOR UNITS MODEL GE 7EA

- Development of engineering, procurement and construction for proper electrical wiring, power, control, instrumentation and lighting of TWO (2) TURBO GENERATOR UNITS MODEL GE 7EA.

- Development of engineering, procurement and construction of piping, equipment, bearings, accessories, for the proper installation of fire fighting system of TWO (2) UNITS TURBO GENERATOR MODEL GE 7EA.

- Installation, Connection, Testing and Start Up.

- Training and personnel training.

In general, within the scope previously established, the CONTRACTOR shall perform the necessary work for the proper execution of the Work in a comprehensive way, in accordance with specifications, standards and ultimately, good engineering practice.

- THIRD CLAUSE: DOCUMENTS THAT ARE PART OF THE CONTRACT

The following documents are part of the Contract:

- This instrument called the "Main Document".

- The Special Contract Conditions for Works of CORPOELEC.

- CORPOELEC’s General Terms and Conditions.

- The final scope of work defined between CORPOELEC, ENELVEN and CONTRACTOR on July 10, 2009

- The Offer of the CONTRACTOR dated 28 July 2009.

All documents that are part of the Contract are mutually complementary. Therefore, it should be interpreted that what has been agreed or stipulated in any of them, is considered, without proof to the contrary, binding for the parties and mandatory as if it were stipulated in all.

In case of contradiction among the provisions of the documents that conform the Contract, the terms of the above-mentioned documents shall apply the with the priorities established in the order they were mentioned in this clause: 1,2,3, 4 and 5.

Any other documents and in general any other Contract Conditions not specifically mentioned in this clause, do not have the character of documents of the Contract, and therefore, its provisions are not applicable.

- CLAUSE FOUR: TIME LIMIT FOR COMPLETION

The deadline for execution of Work under this Contract is set out in the CONTRACTOR's tender dated 28 July 2009, from the date of execution of the Notice to Proceed and CONTRACTOR’s receipt of the Advance Payments as stipulated in Clause Eight, and may be extended for a reasonable period, provided there are circumstances beyond the CONTRACTOR's control that at CORPOELEC’s judgment so advise.

- CLAUSE FIVE: TIME FOR THE COMMENCEMENT OF THE WORK

The CONTRACTOR shall commence the execution of the work after the execution the Notice to Proceed, which will be signed within a maximum of five (5) business days after the execution of the Contract.

- SIXTH CLAUSE: PRICE OF THE WORK

The total price of the Work is the amount of FIFTY ONE MILLION EIGHT HUNDRED THOUSAND UNITED STATES DOLLARS (USD 51.800.000,00), that for the purposes of complying with the provisions of Article. 118 of the Law of the Central Bank of Venezuela, and having used an exchange rate of  TWO BOLIVARS  FIFTEEN CENTS (Bs. F. 2.15) is equivalent to the amount of ONE HUNDRED ELEVEN MILLION THREE HUNDRED SEVENTY THOUSAND BOLIVARS 00/100 (Bs. F. 111.370.000.000,00) for the foreign component, plus the amount of NINETEEN MILLION SEVEN HUNDRED EIGHTY THOUSAND BOLIVARS (Bs. F 19.780.000,00) for the national component, within which are included costs of Nationalization, Engineering and Labor, plus the additional amount of TWO MILLION THREE HUNDRED SEVENTY THREE THOUSAND SIX HUNDRED BOLIVARS,    ( Bs. F. 2.373.600,00), for Value Added Tax (VAT), so that the total estimate of the amount of the Contract adds to ONE HUNDRED THIRTY THREE MILLION FIVE HUNDRED TWENTY-THREE THOUSAND BOLIVARS (Bs F. 133.523.600,00), proposed by the CONTRACTOR and accepted by CORPOELEC.

Price is subject to increase or decrease, if changes in the variation of the quantities of work that ultimately performs the Contractor, with CORPOELEC’s authorization. The necessary adjustments will be made based on the provisions in Clauses INCREASE OF WORK AND SPECIAL WORKS AND INCREASE OR DECREASE OF THE QUANTITIES OF WORK, of CORPOELEC’S General Conditions for Contracting, as applicable.

- SEVENTH CLAUSE: GUARANTEES

To secure the obligations under this Contract, CONTRACTOR shall submit the following Bonds, duly notarized and issued by Insurance or Banking institutions located in Venezuela, and registered with the Superintendence of Banks or with the Superintendence of Insurance, or with the National Society of Reciprocal Guarantees for Small and Medium Industries, as the case may be, to the satisfaction of CORPOELEC.

- Advance Payment Bond:

As a requirement for the Advance Payment, CONTRACTOR shall submit an Advance Payment Bond for an amount equal to fifty percent (50%) of the imported component, that is TWENTY-FIVE MILLION NINE HUNDRED THOUSAND UNITED STATES DOLLARS (USD 25.900.000,00) and fifty percent (50%) of the total national component amount equivalent to NINE MILLION EIGHT HUNDRED AND NINETY THOUSAND BOLIVARS (Bs F. 9.890.000,00).  Such bond shall guarantee CORPOELEC the repayment of the advance payment that is given to CONTRACTOR to comply with the implementation of the object of this Contract, in case CONTRACTOR breaches the terms of this Contract.

Such Bond will take effect from the date the CONTRACTOR receives the aforementioned advance payment and shall remain in force until it has been repaid as follows:

  - TWENTY FIVE MILLION NINE HUNDRED THOUSAND UNITED STATES DOLLARS (USD 25.900.000,00) and NINETY-NINE MILLION EIGHT HUNDRED THOUSAND BOLIVARS (Bs, F. 9.890.000,00) with the presentation of the Memorandum of Completion of Civil Works, Assembly and Electro Mechanical Installation.

- Faithful Compliance Bond:

Upon execution of the Notice to Proceed, CONTRACTOR shall submit a Faithful Compliance Bond for ten percent (10%) of total contract price. This bond shall be released when the Memorandum of Provisional Acceptance of the Work contracted is issued, to the satisfaction of CORPOELEC and against the submittance of the Performance Bond.

- Performance Guarantee:

At Provisional Acceptance of the Work and as a prerequisite for releasing the Faithful Compliance Bond, CONTRACTOR shall submit a Performance Bond in an amount equal to ten percent (10%) of the updated amount of the Contract, and in the terms provided in this literal, to ensure CORPOELEC at the date of executing Memorandum of Provisional Acceptance of the Work, both the high quality of the materials and equipment used, as the proper performance of the object of the Contract, as well as the fulfillment of any other obligation arising from the documents that conform this Contract. If during the term of this Bond, the Work, the equipment or materials supplied have faults that require its replacement or repair, CONTRACTOR will replace or repair, as appropriate, at his expense such equipment or materials and will provide one additional Performance Bond to CORPOELEC for ten percent (10%) of the value of the equipment, works or materials repaired or replaced. The Performance Guarantee shall be released after the Memorandum of Final Acceptance of the Work has been executed, which will occur a year after the signing of the Memorandum of Provisional Acceptance.

- Labor Bond:

Upon signing the Notice to Proceed, Contractor shall submit a Labor Bond for ten percent (10%) of the amount of labor included in the cost structure of its Offer, that is, for the amount of four hundred and ninety-four thousand five hundred Bolivars (Bs. F. 494,500, 00) to ensure payment of the obligations that may be pending from the CONTRACTOR by way of all obligations arising from the implementation of Labor Laws, decrees, regulations and other acts that directly or indirectly establish obligations for CONTRACTOR. This bond shall be released six (6) months counted from the date of execution of the Memorandum of Final Reception of the Work, to the satisfaction of CORPOELEC, upon submittance of the Labor Certificate issued by the Labor Inspectorate of the corresponding jurisdiction, where it declares that there are no claims from any of the workers against the CONTRACTOR, based on contracted labor relations during the execution of the Work contracted.

The amount of bond may be reviewed and must be covered by the CONTRACTOR if the cost of labor is increased beyond what was initially estimated.

The cost of the bond is considered included in the Offer submitted by the CONTRACTOR.

- Civil Liability Insurance Policy:

CONTRACTOR must present prior to the signing of this Contract and maintain in force a civil liability insurance policy and damage to equipment and facilities for third parties, for an amount equal to ten percent (10%) of the amount of the Contract, that is, for the amount of THIRTEEN MILLION THREE HUNDRED FIFTY TWO THOUSAND THREE HUNDRED SIXTY BOLIVARS (Bs. F 13.352.360,00), to ensure any liability and damage to facilities and equipment of third parties that might arise during and after the execution of the Work contracted. This policy will be released within six (6) months following the execution of the Memorandum of Provisional Acceptance of the Work, to the satisfaction of CORPOELEC, provided there are no pending claims.

- CLAUSE EIGHT: TERMS OF PAYMENT

CORPOELEC pay CONTRACTOR as follows:

The total amount of the Contract will be paid by CORPOELEC to the CONTRACTOR, after verifying the fulfillment of the obligations assumed by CONTRACTOR in this Contract, as follows:

- a) FOR THE MATERIAL AND EQUIPMENT FROM ABROAD:

A.1 Fifty percent (50%) of imported component that is TWENTY-FIVE MILLION NINE HUNDRED THOUSAND UNITED STATES DOLLARS (USD 25.900.000,00), payable in foreign currency, via bank transfer, in favor of CONTRACTOR, as Advance Payment, after the execution of the Contract, upon presentation of the Advance Payment Bond for the same amount, to ensure proper return of the amount given as Advance Payment, and the corresponding invoice, duly approved by CORPOELEC’s authorized personnel.

A.2 fifty percent (50%) of imported component that is TWENTY-FIVE MILLION NINE HUNDRED THOUSAND UNITED STATES DOLLARS (USD 25.900.000,00), payable in currency, via bank transfer, in favor of CONTRACTOR, in U.S. Dollars, upon presentation of the following documents.

  - TEN MILLION UNITED STATES DOLLARS (USD 10.000.000,00) with the execution of the  Memorandum of Completion of civil works.

  - TWO MILLION NINE HUNDRED FIFTY THOUSAND UNITED STATES DOLLARS (USD 2.950.000,00) with the execution of the  Memorandum of Completion of assembly and electro mechanical installation.

  - SEVEN MILLION SEVEN HUNDRED SEVENTY THOUSAND UNITED STATES DOLLARS (USD 7.770.000,00) with the execution of the  Memorandum of Provisional Acceptance of Civil Works, Assembly and Electro Mechanical Installation, issued by CORPOELEC.

  - FIVE MILLION ONE HUNDRED EIGHTY THOUSAND UNITED STATES DOLLARS (USD. 5.180.000,00) with the execution of the Memorandum of Nominal Operation of equipment or sixty (60) days from the Inspection (whichever occurs first) of two (2 ) GE 7EA equipment to be installed in the General Rafael Urdaneta Thermoelectric Complex located in La Cañada in Zulia State. (DDW:  They want us to complete this whole project in 8 months and they reserve the right to make this payment 2 months down the road???)  ABSURD!!

Any other document subsequently required, prior agreed by  CORPOELEC and CONTRACTOR.

b) FOR NATIONALIZATION EXPENSES.

CORPOELEC will reimburse to CONTRACTOR the real costs of custom taxes, TSA customs duties, import duties and VAT, of any parts, materials and equipment from foreign origin to be delivered under this Contract, except that CORPOELEC decides to make the process of nationalization, giving prior notice to CONTRACTOR.

It is importantly to indicate that CORPOELEC will only accept:

• For the nationalization of the equipment with Customs Broker hired by  CONTRACTOR, the same % that CORPOELEC pays its customs agents, or CORPOELEC will contract the services.

• If a Warehouse is required, the % that that CORPOELEC pays for storage or  CORPOELEC will contract the services.

To comply with Act 4908 and Section 91 of LOA, it is required that CONTRACTOR presents the documents required by the Customs Management with 30 business days prior to the arrival of the goods to Venezuela, in order to begin the process of application for Certificate of Capital Assets and Tax Exemption. If CONTRACTOR submits these documents at a later date to those thirty days, that is, with less time to complete the formalities for exemption if it applies, it shall bear all expenses incurred by this delay in granting Certification and Release, such as: Storage, Container delay, fines in the cases that apply, default interest and so on, coupled with taxes that could be exonerated.

The approval or rejection by CORPOELEC or its representative, as applicable, of the invoices and supporting documents submitted by the CONTRACTOR as indicated in Sections I and II, this Provision shall be made within fifteen (15) calendar days of their submission. If such approval or rejection is not made within the period aforesaid shall be deemed that the documentation has been filed under, as long as the billing in question complies in all respects with the provisions of this Contract.

c) FOR MATERIAL AND EQUIPMENT FOR NATIONAL ORIGIN, AS WELL AS THE NATIONAL LABOR.

A.1 Fifty percent (50%) of the total amount of the national component equivalent to NINE MILLION EIGHT HUNDRED NINETY THOUSAND BOLIVARS (Bs. F. 9.890.000,00) as an advance payment in Bolivars, via bank transfer or check payable to  CONTRACTOR, after execution of the Contract, upon presentation of the Advance Payment Bond for the same amount, to ensure proper return of the amount given as advance payment and the corresponding invoice, duly approved by the authorized persons of CORPOELEC.

A.2 Twenty-five percent (25%) of the total amount of the national component equivalent to FOUR MILLION NINE HUNDRED AND FORTY FIVE THOUSAND of  (Bs. F. 4.945.000,00) with the execution of the  Memorandum of Completion of civil works.

A.3 Twenty-five percent (25%) of the total amount of the national component equivalent to FOUR MILLION NINE HUNDRED AND FORTY FIVE THOUSAND of  (Bs. F. 4.945.000,00) with the execution of the  Memorandum of Completion of Assembly and Electro Mechanical Installation.

- CLAUSE NINTH: COMMITMENT TO SOCIAL RESPONSIBILITY

From each of the payments to be made to CONTRACTOR, CORPOELEC shall retain an amount equivalent to two percent (2%) of the total contract amount for the purposes of ensuring compliance with the implementation of a project or a social activity established as Social Responsibility Commitment in the execution of the work. This amount will be refunded once the Memorandum of Completion of Social Responsibility Commitment has been signed.

If CONTRACTOR does not comply with the fulfillment of the Social Responsibility Commitment, CORPOELEC will donate this retention to a Social Fund for the execution of projects, programs or social activities in communities under the influence of CORPOELEC.

CLAUSE TENTH: LAPSE OF WARRANTY AND CONSERVATION OF THE WORK.

From the date of execution of the Memorandum of Provisional Acceptance Act, there will be a warranty period of twelve (12) months during which the CONTRACTOR must complete any unfulfilled work, that at CORPOELEC’s judgement can be completed during this period, make the necessary adjustments in the work and the repair of any defect in the work, as required by the Company.

- ELEVENTH CLAUSE: GOOD QUALITY WARRANTY

The CONTRACTOR is obliged for a period of twelve (12) months from Final Acceptance to guarantee the good quality of the works undertaken. In this regard, CONTRACTOR agrees to repair, replace, rebuild, re-do any work again, that during the aforementioned period is necessary to execute at The Company’s request. This warranty also covers equipment, supplies, materials and spare parts that the CONTRACTOR has incorporated or installed in performance of the Contract, which is why undertakes to replace or repair them if these are affected by faults or damage not attributable to CORPOELEC.

The guarantee may be backed with a Good Quality Bond, which shall be equal to that of the secured obligation. This Bond will have the same conditions as the performance bond, in addition to those required by the Company.

CLAUSE TWELFTH: DESIGNATION OF ADMINISTRATORS OF THE CONTRACT BY THE PARTIES

The parties designate the following people as Contract Administrators:

By CONTRACTOR: Mr. JEFFREY CANON

By CORPOELEC:      ECON. CHAYELE NESTOR PEREZ

CLAUSE THIRTEENTH: ASSIGNMENT OF CONTRACT BY CORPOELEC. Pursuant to the provisions of Decree 5330 with Rank, Value and Force of Organic Law on Reorganization of the Electric Sector dated 02 of May 2007, published in the Official Gazette of the Bolivarian Republic of Venezuela No. 38,736 of July 31 2007, which orders the creation of the Corporación Eléctrica Nacional SA, CORPOELEC has the right and so agrees to the transfer all or part of this contract, to a legal person to be named.

For the validity of such transfer will suffice simple notification to CONTRACTOR, conducted privately.

Two (2) counterparts of this Contract shall be made, each to have the same tenor and effect.. In Caracas, at the date of its authentication.