## HOMEOFFICE START-UP
| Project Name | MARGARITA ISLAND | [6 empty] | HOME OFFICE BUDGET | [20 empty] | Per Diem |  | 108 | 3240
| Location | VENEZUELA | [25 empty] | HOME
| Description | 2 7EA | [25 empty] | OFFICE |  | Monthly Family Visit |  |  | 800
| Job No. | xxxxx | [25 empty] | EXPENSES |  | Computer |  |  | 100
| Prepared by | TG | Date | 2010-05-04
| Reviewed by | TE | Date | [26 empty] | TOTAL H/O EXPENSES |  |  | 4140
| Approved by | 0 | Date
| Period of Performance |  | Week No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | Total | Total
|  |  | Date | 2010-05-16 | 2010-05-23 | 2010-05-30 | 2010-06-06 | 2010-06-13 | 2010-06-20 | 2010-06-27 | 2010-07-04 | 2010-07-11 | 2010-07-18 | 2010-07-25 | 2010-08-01 | 2010-08-08 | 2010-08-15 | 2010-08-22 | 2010-08-29 | 2010-09-05 | 2010-09-12 | 2010-09-19 | 2010-09-26 | 2010-10-03 | 2010-10-10 | 2010-10-17 | 2010-10-24 | 2010-10-31 | 2010-11-07 | 2010-11-14 | 2010-11-21 | Manhours | W2
HOME OFFICE TASK
1 | Senior S/U Mgr | W2 Rate | 80 | 40 | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 340 | 27200
2 | SDOI Supervision | W2 Rate | 50 | [28 empty] | 0 | 0
3 | SDOIs | W2 Rate | 40 | [28 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | 40 | [28 empty] | 0 | 0
5 | IOI/AR | W2 Rate | 40 | [28 empty] | 0 | 0
6 | Admin Support | W2 Rate | 20 | [28 empty] | 0 | 0
|  | Total Weekly Manhours |  | 40 | 40 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 340 | 27200
7 | Start-up Manager | W2 Rate | 75 | [5 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [15 empty] | 320 | 24000
8 | Scoping/Turnovers | W2 Rate | 60 | [7 empty] | 40 | 40 | 40 | 40 | 40 | [16 empty] | 200 | 12000
9 | F.A.T. | W2 Rate | 48 | [28 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 40 | 40 | 80 | 80 | 80 | 80 | 80 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 520 | 36000
| Period of Performance |  | Week No. | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | Total | Total
|  |  | DATE | 2010-11-28 | 2010-12-05 | 2010-12-12 | 2010-12-19 | 2010-12-26 | 2011-01-02 | 2011-01-09 | 2011-01-16 | 2011-01-23 | 2011-01-30 | 2011-02-06 | 2011-02-13 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-03-13 | 2011-03-20 | 2011-03-27 | 2011-04-03 | 2011-04-10 | 2011-04-17 | 2011-04-24 | 2011-05-01 | 2011-05-08 | 2011-05-15 | 2011-05-22 | 2011-05-29 | 2011-06-05 | Manhours | W2
1 | Senior S/U Mgr | W2 Rate | 90 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [16 empty] | 120 | 10800
2 | SDOI Supervision | W2 Rate | 50 | [28 empty] | 0 | 0
3 | SDOIs | W2 Rate | 40 | [28 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | 40 | [28 empty] | 0 | 0
5 | IOI/AR | W2 Rate | 40 | [28 empty] | 0 | 0
6 | Admin Support | W2 Rate | 20 | [28 empty] | 0 | 0
|  | Total Weekly Manhours |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 10800
7 | Start-up Manager | W2 Rate | 80 | [28 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | 50 | [28 empty] | 0 | 0
9 | F.A.T. | W2 Rate | 48 | [28 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Period of Performance |  | Week No. | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | Total | Total
|  |  | DATE | 2011-06-12 | 2011-06-19 | 2011-06-26 | 2011-07-03 | 2011-07-10 | 2011-07-17 | 2011-07-24 | 2011-07-31 | 2011-08-07 | 2011-08-14 | 2011-08-21 | 2011-08-28 | 2011-09-04 | 2011-09-11 | 2011-09-18 | 2011-09-25 | 2011-10-02 | 2011-10-09 | 2011-10-16 | 2011-10-23 | 2011-10-30 | 2011-11-06 | 2011-11-13 | 2011-11-20 | 2011-11-27 | 2011-12-04 | 2011-12-11 | 2011-12-18 | Manhours | W2
1 | Senior S/U Mgr | W2 Rate | 60 | [28 empty] | 0 | 0
2 | SDOI Supervision | W2 Rate | 50 | [28 empty] | 0 | 0
3 | SDOIs | W2 Rate | 40 | [28 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | 40 | [28 empty] | 0 | 0
5 | IOI/AR | W2 Rate | 40 | [28 empty] | 0 | 0
6 | Admin Support | W2 Rate | 20 | [28 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Start-up Manager | W2 Rate | 55 | [28 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | 50 | [28 empty] | 0 | 0
9 | F.A.T. | W2 Rate | 48 | [28 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Period of Performance |  | Week No. | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | Total | Total
|  |  | DATE | 2011-12-25 | 2012-01-01 | 2012-01-08 | 2012-01-15 | 2012-01-22 | 2012-01-29 | 2012-02-05 | 2012-02-12 | 2012-02-19 | 2012-02-26 | 2012-03-04 | 2012-03-11 | 2012-03-18 | 2012-03-25 | 2012-04-01 | 2012-04-08 | 2012-04-15 | 2012-04-22 | 2012-04-29 | 2012-05-06 | 2012-05-13 | 2012-05-20 | 2012-05-27 | 2012-06-03 | 2012-06-10 | 2012-06-17 | 2012-06-24 | 2012-07-01 | Manhours | W2
1 | Senior S/U Mgr | W2 Rate | 60 | [28 empty] | 0 | 0
2 | SDOI Supervision | W2 Rate | 50 | [28 empty] | 0 | 0
3 | SDOIs | W2 Rate | 40 | [28 empty] | 0 | 0
4 | Training Doc Prep | W2 Rate | 40 | [28 empty] | 0 | 0
5 | IOI/AR | W2 Rate | 40 | [28 empty] | 0 | 0
6 | Admin Support | W2 Rate | 20 | [28 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Start-up Manager | W2 Rate | 55 | [28 empty] | 0 | 0
8 | Scoping/Turnovers | W2 Rate | 50 | [28 empty] | 0 | 0
9 | F.A.T. | W2 Rate | 48 | [28 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
|  | Total Weekly Manhours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HOME OFFICE PERSONNEL EXPENSES |  | Month | 2010-05-16 | 2010-06-16 | 2010-07-16 | 2010-08-16 | 2010-09-16 | 2010-10-16 | 2010-11-16 | 2010-12-16 | 2011-01-16 | 2011-02-16 | 2011-03-16 | 2011-04-16 | 2011-05-16 | 2011-06-16 | 2011-07-16 | 2011-08-16 | 2011-09-16 | 2011-10-16 | 2011-11-16 | 2011-12-17 | 2012-01-17 | 2012-02-17 | 2012-03-18 | 2012-04-18 | 2012-05-19 | 2012-06-19
|  |  | Manhours | 0 | 240 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Expenses | 0 | 5743.3526 | 6700.578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Expenses
TOTAL HOME OFFICE BUDGET
|  | Home Office Wages Sub-Total |  |  | 38000 | [25 empty] | 12443.9306
|  | Field Office Wages Sub-Total |  |  | 36000
|  | HomeOffice Overhead at0 |  |  | 0
|  | FHomeOffice Overhead at 0 |  |  | 0
|  | Home Office Wages Total |  |  | 74000 |  |  | TOTAL HOME OFFICE MANHOURS |  |  |  | 980
|  | Home Office Personnel Expenses |  |  | 12443.9306
|  |  | TOTAL BUDGET |  | 86443.9306

## START-UP SUMMARY REPORT
ESTIMATE IS BASED ON 2010 DOLLARS
Project Name | MARGARITA ISLAND |  |  | NTP
Location | VENEZUELA
Description | 2 7EA |  |  | BACKFEED | 2010-10-17
Project Number | xxxxx
Prep by: | TG | Date | 2010-05-04 | FF UNIT #1 | 2010-11-20
Reviewed by | TE | Date |  | FF UNIT #2 | 2011-01-02
Approved by |  | Date |  | ACCEPTANCE | 2011-02-03
BUDGET ITEM |  | MANHOURS | SUB-TOTALS | OVERHEAD | TOTALS
HOMEOFFICE START-UP |  | 980 | 74000 | 0 | 74000
HOMEOFFICE EXPENSES |  |  | 12443.9306 |  | 12443.9306
SUBTOTALS ON HOME OFFICE STARTUP |  | 980 | 86443.9306 | 0 | 86443.9306
FIELD START-UP S/T | S/T | 11000 | 1049800 | 0 | 1049800
FIELD START-UP O/T | O/T | 2340 | 228750 | 0 | 228750
FIELD START-UP EXPENSES |  |  | 467142.341 | ` | 467142.341
SUBTOTALS ON FIELD STARTUP |  | 13340 | 1745692.341 | 0 | 1745692.341
CRAFT START-UP SUPPORT | S/T | 20240 | 0 |  | 0
| O/T | 4460 | 0 |  | 0
SUBTOTALS ON CRAFT SUPPORT |  | 24700 | 0 |  | 0
CHEMICAL CLEANING |  |  | 0 |  | 0
OIL/HYD AND WATER FLUSHES |  |  | 200390 |  | 200390
STEAM/AIR BLOWS |  |  | 0 |  | 0
OFFICE EQUIPMENT |  |  | 37800 |  | 37800
START-UP SPARES |  |  | 30200 |  | 30200
ELECTRICAL RELAY TESTING |  |  | 75000 |  | 75000
EMMISSION TESTING |  |  | 0 |  | 0
START-UP TEST EQUIPMENT |  |  | 60000 |  | 60000
FIRST FILLS |  |  | 86459 |  | 86459
PERFORMANCE TESTING |  |  | 0 |  | 0
MOBILIZATION/DEMOBILIZATION |  |  | 77000 |  | 77000
SOFT PRODUCT REPRODUCTION |  |  | 0 |  | 0
SITE VISITATION |  |  | 20000 |  | 20000
SUBTOTALS ON STARTUP INDRECTS |  |  | 586849 |  | 586849
TOTAL PROJECT START-UP COSTS |  |  | 2418985.2717

## START-UP SUPPORT
VENDORS, CONTRACTORS & MISC SUPPORT
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTH(S) |  | COST |  |  |  | QTY | TYPE | RATE |  | MONTH(S) | COST
1 | Specialty Contractor | [11 empty] | 6 | Local Supplier | Test Equipment |  |  |  | 60000 |  | 0 |  | 60000 | 11 | Speciatly Contractor
| Chemical Cleaning | Equip. Rental |  | 0 |  | LUMP SUM |  | 68000 |  |  |  | 0 |  | Test Equipment | [10 empty] | Performance Testing | Subcontractor |  | 2 (2X!) | 128500 |  |  | FALSE
|  | Support Labor |  | 0 |  | 2-6 Man teams |  | 0 |  |  |  | 0 | [15 empty] | 2X1 | 126500 |  |  | FALSE
| CRMS Code No xxxxx.xxx | Subcontractor |  | 0 |  | LUMP SUM |  | 150000 |  |  |  | 0 |  | CRMS Code No xxxxx.xxx | [10 empty] | CRMS Code No xxxxx.xxx |  |  | 3X1 | 129000 |  |  | FALSE
|  | Demin Trailers |  | 0 |  | TRAILER |  | 8200 |  |  |  | 0 | [15 empty] | 3 (1X1) | 127000 |  |  | FALSE
|  | Setup Cost |  | 0 |  | LUMP SUM |  | 450000 |  |  |  | 0 | [15 empty] | 1X1 | 120000 |  |  | FALSE
| Total Cost | Waste Disposal |  | 0 |  | GAL |  | 0.65 |  |  |  | 0 |  | Total Cost | [10 empty] | Total Cost |  |  | S/Cycle | 80000 |  |  | FALSE
| 0 | [12 empty] | 60000 | [10 empty] | 0
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  | QTY | TYPE | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTH(S) | COST
2 | Specialty Contractor | Fills Flushing Oil |  |  |  | GAL |  | 6 |  |  |  | 0 | 7 | Specialty Contractor | Subcontractor | 1 |  | Lump Sum |  | 75000 |  | 75000 |  | 12 | Project Support |  | 4 | VISIT | 5000 |  |  | 20000
| Oil Flushes | Flush Kits |  | 2 |  | Kits |  | 15000 |  |  |  | 30000 |  | Electrical Testing | [10 empty] | Site Vistiation
|  | Support Labor |  | 1 |  | 2-4 Man Teams |  | 20000 |  |  |  | 20000
| CRMS Code No xxxxx.xxx | Setup Cost |  | 1 |  | LUMP SUM |  | 150000 |  |  |  | 150000 |  | CRMS Code No xxxxx.xxx | [10 empty] | CRMS Code No xxxxx.xxx
|  | Wste Dspsl/Splls |  | 600 |  | GAL |  | 0.65 |  |  |  | 390
| Total Cost | [12 empty] | Total Cost | [10 empty] | Total Cost
| 200390 | [12 empty] | 75000 | [10 empty] | 20000
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  | QTY | TYPE | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTH(S) | COST
3 | Specialty Contractor | [11 empty] | 8 | Specialty Contractor | Subcontractor |  | 2X1 | 145000 |  |  |  |  | FALSE | 13 | Project Support |  | 11 | MOBE | 4500 |  |  | 49500
| Steam/Air Blows | Equipment Rental |  | 0 |  | Lump Sum |  | 5000 |  |  |  | 0 |  | Emmissions Testing |  |  | 3X1 | 165000 |  |  |  |  | FALSE |  | Mobilization/demobilization |  | 11 | DEMOBE | 2500 |  |  | 27500
|  | Subcontractor |  | 0 |  | Lump Sum |  | 150000 |  |  |  | 0 |  |  |  |  | 2 (2x1) | 225000 |  |  |  |  | FALSE
| CRMS Code No xxxxx.xxx | Set-up |  | 0 |  | Lump Sum |  | 450000 |  |  |  | 0 |  | CRMS Code No xxxxx.xxx |  |  | 1X1 | 180000 |  |  |  |  | FALSE |  | CRMS Code No xxxxx.xxx
|  | Equipment Rebuild |  | 0 |  | Lump Sum |  | 65000 |  |  |  | 0 |  |  |  |  | Simple | 120000 |  |  |  |  | FALSE
|  | Support Labor |  | 0 |  | 2-8 Man Teams |  | 0 |  |  |  | 0
| Total Cost | [12 empty] | Total Cost | [10 empty] | Total Cost
| 0 | [12 empty] | 0 | [10 empty] | 77000
|  |  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTHS(S) |  | COST |  |  |  | QTY | TYPE | RATE |  | MONTH(S) | COST
4 | Local Supplier | Fax |  | 1 |  | RENTAL |  | 300 |  | 6 |  | 1800 | 9 | Local Supplier | Filters |  | 4 | LS | 600 |  |  |  | 2400 | 14 | Not Used
| Office Equipment | Copier |  | 1 |  | RENTAL |  | 350 |  | 6 |  | 2100 |  | Start-up Spares | Valve Rebuild Kits |  | 2 | LS | 15000 |  |  |  | 2800 |  | Training | 1 |  |  |  | 20000
|  | Radios |  | 13 |  | RENTAL |  | 300 |  | 6 |  | 23400 |  |  | Misc |  | 15 | LS | 25000 |  |  |  | 25000
| CRMS Code No xxxxx.xxx | Computers |  | 5 |  | RENTAL |  | 350 |  | 6 |  | 10500 |  | CRMS Code No xxxxx.xxx | [10 empty] | CRMS Code No xxxxx.xxx
| Total Cost | [12 empty] | Total Cost | [10 empty] | Total Cost
| 37800 | [12 empty] | 30200 | [10 empty] | 0
|  |  | QTY |  | TYPE |  | RATE |  | MONTH(S) |  | COST | [5 empty] | QTY | TYPE | RATE | MONTH(S) |  | COST |  |  |  |  | QTY | TYPE | RATE |  | MONTH(S) | COST
5 | Project Support |  | 0 |  | LS |  | 15000 |  |  |  |  | 0 | 10 | Local Suppliers | Turbine Lube Oil |  | 3600 | GAL | 6 |  |  | 21600 |  | 15 | Not used
| Soft Product Reproduction | [12 empty] | First Fills | Gycol |  | 800 | GAL | 6.36 |  |  | 5088 |  |  | Later
[15 empty] | CO2 |  | 1600 | GAL | 8.51 |  |  | 13616
| CRMS Code No xxxxx.xxx | [12 empty] | CRMS Code No xxxxx.xxx | Hydgron |  | 4000 | GAL | 3.25 |  |  | 13000 |  |  | CRMS Code No xxxxx.xxx
[15 empty] | Wtr/Wstwtr chem |  | 0 | GAL | 3 |  |  | 0
[15 empty] | Blr Chemicals |  | 0 | GAL | 2.5 |  |  | 0
| Total Cost | [12 empty] | Total Cost | Hydraulic Oil |  | 500 | LBS | 4.31 |  |  | 2155 |  |  | Total Cost
| 0 | [12 empty] | 86459 | Oils & Greases |  | 250 | GAL | 4 |  |  | 1000 |  |  | 0
[15 empty] | Transformer Oil |  | 100000 | GAL | 0.3 |  |  | 30000

## FIELD STARTUP
| Project Name |  | MARGARITA ISLAND | [41 empty] | Field Expenses |  | Per Diem Allowance |  | 275 | 8250
| Location |  | VENEZUELA | [8 empty] | FIELD OFFICE BUDGET
| Description |  | 2 7EA | [43 empty] | Monthly Trip Home |  |  | 1400
| Job No. |  | xxxxx
| Prep by: |  | TG |  | Date
| Reviewed by |  | TE |  | Date
| Approved by |  | 0 |  | Date | [41 empty] | Total Expenses per Man Month |  |  | 9650
| Period of Performance |  |  | Week No. | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | Total | Total
|  |  |  | Date | 2010-08-15 | 2010-08-22 | 2010-08-29 | 2010-09-05 | 2010-09-12 | 2010-09-19 | 2010-09-26 | 2010-10-03 | 2010-10-10 | 2010-10-17 | 2010-10-24 | 2010-10-31 | 2010-11-07 | 2010-11-14 | 2010-11-21 | 2010-11-28 | 2010-12-05 | 2010-12-12 | 2010-12-19 | 2010-12-26 | 2011-01-02 | 2011-01-09 | 2011-01-16 | 2011-01-23 | 2011-01-30 | 2011-02-06 | 2011-02-13 | 2011-02-20 | 2011-02-27 | 2011-03-06 | 2011-03-13 | 2011-03-20 | 2011-03-27 | 2011-04-03 | 2011-04-10 | 2011-04-17 | 2011-04-24 | 2011-05-01 | 2011-05-08 | 2011-05-15 | 2011-05-22 | 2011-05-29 | 2011-06-05 | 2011-06-12 | Manhours | Cost
|  |  | Manhours | Rate | [9 empty] | BACK FEED | [5 empty] | FIRST FIRE #1 7EA |  |  |  |  | FIRST FIRE #2 7EA |  |  |  | SUBST. COMLPLETE
1 | Senior Startup Manager |  | Normal | 90 |  | 40 |  |  |  | 40 |  |  |  | 40 | [5 empty] | 40 |  |  |  |  | 40 |  |  |  | 40 | [19 empty] | 240 | 21600
|  |  | Overtime | [10 empty] | 10 | [5 empty] | 10 |  |  |  |  | 10 |  |  |  | 10 | [19 empty] | 40 | 3600
2 | Startup Manager |  | Normal | 80 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [17 empty] | 1080 | 86400
|  |  | Overtime | [10 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 160 | 12800
3 | Fld Startup Dir |  | Normal | 45 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
4 | Mechanical Lead |  | Normal | 70 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [17 empty] | 960 | 67200
|  |  | Overtime | [8 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 180 | 12600
5 | Mechaincal #2 |  | Normal | 65 | [13 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [21 empty] | 400 | 26000
|  |  | Overtime | [14 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [21 empty] | 100 | 6500
| Mechanical #3 |  | Normal | 65 | [44 empty] | 0 | 0
6 |  |  | Overtime | [45 empty] | 0 | 0
7 | GE Mechanical Field Rep |  | Normal | 150 | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [19 empty] | 760 | 114000
|  |  | Overtime | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [21 empty] | 170 | 25500
8 | Electrical Lead |  | Normal | 75 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [17 empty] | 1000 | 75000
|  |  | Overtime | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 210 | 15750
9 | Electrical #2 |  | Normal | 65 | [8 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [23 empty] | 520 | 33800
|  |  | Overtime | [9 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [23 empty] | 130 | 8450
10 | Electrical #3 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
11 | GE Electrical Field Rep |  | Normal | 165 | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [19 empty] | 760 | 125400
|  |  | Overtime | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 190 | 31350
12 | I&C Lead |  | Normal | 75 | [7 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [18 empty] | 760 | 57000
|  |  | Overtime | [10 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 160 | 12000
13 | I&C #2 |  | Normal | 65 | [13 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [22 empty] | 360 | 23400
|  |  | Overtime | [14 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [22 empty] | 90 | 5850
14 | GE I&C Field Rep |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
15 | DCS Lead |  | Normal | 75 |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [17 empty] | 1000 | 75000
|  |  | Overtime | [6 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 200 | 15000
16 | DCS #2 |  | Normal | 65 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
17 | GE Turbine Controls Rep |  | Normal | 165 | [6 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [17 empty] | 840 | 138600
|  |  | Overtime | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 190 | 31350
18 | GE Turbine Controls Rep |  | Normal | 165 | [9 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [19 empty] | 640 | 105600
|  |  | Overtime | [10 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 160 | 26400
19 | Shift Operator #1 |  | Normal | 60 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
20 | Shift Operator #2 |  | Normal | 60 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
21 | Shift Operator #3 |  | Normal | 60 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
22 | LOTO Coordinator |  | Normal | 60 |  |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [18 empty] | 920 | 55200
|  |  | Overtime | [6 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 200 | 12000
23 | T/O Coordinator |  | Normal | 60 | [8 empty] | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | [17 empty] | 760 | 45600
|  |  | Overtime | [10 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | [19 empty] | 160 | 9600
| Support Wage Rate |  | Total Normal Hours |  | 40 | 80 | 120 | 200 | 200 | 240 | 320 | 360 | 440 | 520 | 480 | 480 | 480 | 560 | 560 | 600 | 560 | 560 | 560 | 560 | 600 | 520 | 480 | 440 | 480 | 320 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11000 | 1049800
| EL S/T | 0 | Total Overtime Hours |  | 0 | 0 | 0 | 0 | 10 | 30 | 60 | 70 | 80 | 130 | 120 | 120 | 120 | 140 | 140 | 150 | 140 | 140 | 140 | 140 | 150 | 130 | 120 | 100 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2340 | 228750
| EL O/T | 0 | Total Startup Engineers |  | 1 | 2 | 3 | 5 | 5 | 6 | 8 | 9 | 11 | 13 | 12 | 12 | 12 | 14 | 14 | 15 | 14 | 14 | 14 | 14 | 15 | 13 | 12 | 11 | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13340 | 1278550
| ME S/T | 0 | Electrcial Support S/T |  | 0 | 0 | 80 | 80 | 80 | 80 | 160 | 160 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 240 | 160 | 160 | 160 | 160 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4560 | 0
| ME O/T | 0 | Electrcial Support O/T |  | 0 | 0 | 0 | 0 | 20 | 20 | 40 | 40 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 60 | 40 | 40 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0
| I&C/DCS S/T | 0 | I&C-DCS support S/T |  | 0 | 0 | 80 | 80 | 80 | 80 | 160 | 240 | 240 | 320 | 320 | 320 | 320 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 400 | 320 | 320 | 320 | 240 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7200 | 0
| I&C/DCS O/T | 0 | I&C-DCS support O/T |  | 0 | 0 | 0 | 0 | 0 | 20 | 40 | 40 | 40 | 80 | 80 | 80 | 80 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 80 | 80 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0
| Craft per Startup Engineer |  | Mechanical Support S/T |  | 0 | 0 | 0 | 160 | 160 | 160 | 320 | 320 | 320 | 320 | 320 | 320 | 320 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 480 | 320 | 320 | 160 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8480 | 0
| Electrcial | 2 | Mechanical Support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 80 | 80 | 80 | 80 | 80 | 80 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0
| Mechanical | 4 | TOTAL CRAFT |  | 0 | 0 | 4 | 8 | 8 | 8 | 16 | 18 | 20 | 22 | 22 | 22 | 22 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 28 | 26 | 24 | 20 | 20 | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&c/DCS | 2
| Period of Performance |  |  | WEEK No. | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | Total | Total
|  |  |  | DATE | 2011-06-19 | 2011-06-26 | 2011-07-03 | 2011-07-10 | 2011-07-17 | 2011-07-24 | 2011-07-31 | 2011-08-07 | 2011-08-14 | 2011-08-21 | 2011-08-28 | 2011-09-04 | 2011-09-11 | 2011-09-18 | 2011-09-25 | 2011-10-02 | 2011-10-09 | 2011-10-16 | 2011-10-23 | 2011-10-30 | 2011-11-06 | 2011-11-13 | 2011-11-20 | 2011-11-27 | 2011-12-04 | 2011-12-11 | 2011-12-18 | 2011-12-25 | 2012-01-01 | 2012-01-08 | 2012-01-15 | 2012-01-22 | 2012-01-29 | 2012-02-05 | 2012-02-12 | 2012-02-19 | 2012-02-26 | 2012-03-04 | 2012-03-11 | 2012-03-18 | 2012-03-25 | 2012-04-01 | 2012-04-08 | 2012-04-15 | Manhours | Cost
|  |  | Manhours | Rate
1 | Senior Startup Manager |  | Normal | 60 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
2 | Startup Manager |  | Normal | 55 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
3 | Fld Startup Dir |  | Normal | 50 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
4 | Mechaincal #1 |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
5 | Mechanical #2 |  | Normal | 40 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
6 | Mechainical #3 |  | Normal | 40 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
7 | Mechanical N/S |  | Normal | 40 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
8 | Electrical #1 |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
9 | Electrical #2 |  | Normal | 43 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
10 | Electrical #3 |  | Normal | 43 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
| Electrical N/S |  | Normal | 43 | [44 empty] | 0 | 0
11 |  |  | Overtime | [45 empty] | 0 | 0
12 | I&C #1 |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
13 | I&C #2 |  | Normal | 43 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
14 | I&C N/S |  | Normal | 43 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
15 | DCS #1 |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
16 | DCS #2 |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
17 | DCS #3 |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
18 | [48 empty] | 0 | 0
[49 empty] | 0 | 0
19 | Shift Operator #1 |  | Normal | 30 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
20 | Shift Operator #2 |  | Normal | 30 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
21 | Shift Operator #2 |  | Normal | 30 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
22 | Lead Trainer |  | Normal | 40 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
23 | T/O & Safety |  | Normal | 48 | [44 empty] | 0 | 0
|  |  | Overtime | [45 empty] | 0 | 0
| Support Wage Rate |  | Total Normal Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EL S/T | 46 | Total Overtime Hours |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| EL O/T | 69 | Total Startup Engineers |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ME S/T | 44 | Electrcial Support S/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| ME O/T | 66 | Electrcial Support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&C/DCS S/T | 54 | I&C-DCS support S/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&C/DCS O/T | 81 | I&C-DCS support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Craft per Startup Engineer |  | Mechanical Support S/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Electrcial | 2 | Mechaincal Support O/T |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Mechanical | 4 | TOTAL CRAFT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| I&c/DCS | 2
[46 empty] | Grand Total Normal Hours |  |  | 11000
[46 empty] | Grand Total Overtime Hours |  |  | 2340
[46 empty] | TOTAL HOURS |  |  | 13340
| TOTAL FIELD STAFF BUDGET | [7 empty] | TOTAL FIELD SUPPORT BUDGET
|  | Field Wages Sub-Total |  |  |  | 1278550 |  |  | Field Support Wages |  |  | S/T | 0 | [32 empty] | Total Support S/T Hours |  |  | 20240
|  | Overhead at 0 |  |  |  | 0 |  |  | Field Support Expenses |  |  | O/T | 0 | [32 empty] | Total Support O/T Hours |  |  | 4460
|  | Field Wages Total |  |  |  | 1278550 |  |  | Field Support Expenses | [36 empty] | Total Support Hours |  |  | 24700
|  | Field Personnel Expenses |  |  |  | 467142.341
|  |  |  | TOTAL BUDGET |  | 1745692.341 | [5 empty] | Total | 0