PROPOSAL

Presented To:

GAZPROM

for

Frame 5 Hot Gas Path Inspection

By

Proposal No. 409-2693

September 10, 2009

This document is privileged and contains confidential information intended for use only by

Gazprom.

Table of Contents

1.0	Introduction	3

2.0	Work Scope	3

2.1	Frame 5 Hot Gas Path Inspection	3

2.1.1	Disassembly	3

2.1.2	Inspection, cleaning and repairs	4

2.1.3	Reassembly	4

3.0	Budgetary Pricing	5

3.1	Optional Pricing	5

3.2	Extra Work Rates	5

3.2.1	Administration	5

3.3	Assumptions & Clarifications	6

4.0	Terms & Conditions	6

5.0	Follow Up	6

6.0	Conclusion	6

Attachment A	Supplemental Terms

- Introduction

ProEnergy Services (“ProEnergy”) is pleased to provide this budgetary proposal to Gazprom for a Frame 5 Hot Gas Path Inspection for your facility located in Venezuela.

- Work Scope

The scope of work includes the management, planning, direct supervision and provision of craft labor as required for completing the Hot Gas Path Inspection (HGP).

The inspection team shall prepare an inspection plan which will include but not be limited to the following:

- Inspection Schedule from mobilization through testing and turnover

- Manpower Resource Plan

- Quality Control Plan including, inspection forms and data sheets

- Safety Plan

- Final Report

  - Frame 5 Hot Gas Path Inspection

    - Disassembly

- Remove turbine compartment roof and side panel

- Remove atomizing air lines and manifold

- Remove gas fuel lines and manifold

- Remove fuel nozzles

- Remove flame detectors and spark plugs

- Remove combustion casing covers

- Remove crossfire tube retainers and crossfire tubes, and combustion liners

- Remove wheel space thermocouple wiring and conduit

- Remove upper and lower half cooling and sealing air piping

- Remove all (10) combustion casings

- Install mechanical jacks to support compressor and turbine casings

- Remove upper half turbine casing bolts and upper half second stage nozzle axial pins

- Remove upper half turbine casing

- Remove transition pieces

- Remove upper half first stage nozzle and support ring

- Remove upper half second stage nozzle and inner diaphragm

- Take turbine clearances in hot section

- Remove lower half eccentric pin and first stage nozzle

- Remove lower half eccentric pin and second stage nozzle

- Removed first stage forward thermocouple tubing

- Remove lower half first stage nozzle

- Remove lower half second stage nozzle and diaphragm

    - Inspection, cleaning and repairs

- Ship support ring for repair (Optional)

- Inspect first and second stage turbine shrouds

- Inspect first and second nozzles - Perform first stage nozzle ellepticity checks

- Inspect second stage diaphragm and packing

- Inspect first and second stage turbine wheel and bucket

- Inspect fuel nozzles

- Inspect combustion liners

- Inspect cross fire tubes and retainers

- Inspect transition piece

- Inspect combustion casings

- Inspect and test spark plugs

- Inspect flame detectors

- Clean all mating surfaces and inspect casings for cracks or damages

- Tap all thread holes on casings

- Clean, bag and tag all bolting and hardware

    - Reassembly

- Install lower half second nozzle, diaphragm and wheel space thermocouples

- Install lower half first stage nozzle and support ring

- Align first stage nozzle and install eccentric pin

- Align second stage nozzle and diaphragm and install axial and eccentric pins

- Take turbine clearances

- Install first stage forward wheel space thermocouples

- Install upper half support ring and first stage nozzle

- Install upper half second diaphragm and nozzle

- Install transition pieces

- Install upper half turbine casing

- Install upper half first and second stage eccentric pins

- Remove mechanical jacks from underneath unit casings

- Install outer combustion cans

- Install combustion liners and cross fire tubes

- Install flame detectors and spark plugs

- Install combustion casing covers

- Install fuel nozzles

- Install cooling and sealing air piping

- Install fuel gas manifold and fuel lines

- Install turbine compartment roof and side panels.

- Clean up visual inspection

- Budgetary Pricing

ProEnergy is providing the following budgetary pricing to complete the Frame 5 Hot Gas Path Inspection:

| Description | Budgetary Amount |
| --- | --- |
| Hot Gas Path Inspection | $80,530.00 |

  - Optional Pricing

ProEnergy will provide tooling less any special tooling provided by OEM, estimated additional cost of $43,750.00 and require a minimum of six (6) weeks notice to proceed to allow for shipping.

  - Extra Work Rates

The extra work rates for the assigned employees are quoted below.  Straight time rates will be invoiced for all hours up to eight hours per day, Monday through Friday.  Over time rates will be invoiced for all hours in excess of eight hours a day Monday through Friday and all hours on Saturday and Sunday. The per diem charge will be invoiced for each employee assigned to the project seven days per week for the duration of the extra work.

| Position | ST Hourly Rate | OT Hourly Rate | Per Diem |
| --- | --- | --- | --- |
| Technical Advisors | $165.00 | $165.00 | $150.00 |
| Foreman | $65.60 | $78.50 | $150.00 |

    - Administration

The rates noted above include all US taxes, insurance and benefits associated with the labor. All expense incurred for mobilization, demobilization and local living expenses will be invoiced at cost plus 10%. All time and expense sheets shall be approved and signed by the Gazprom designated representative at the site.

  - Assumptions & Clarifications

The following assumptions have been made in the preparation of this proposal:

- No tooling included in this price, to be provided by site or local contractor.

- No equipment (i.e. forklift, air compressor, light plant) included in this price, to be provided by site or local contractor.

- Estimated time frame for completion only, time in excess will be billed at Extra Work rates.

- No parts or consumables included in this price, to be provided by site or local contractor.

- Site to provide any special tooling provided by the OEM.

- Removal of stuck bolting will be billed at the Extra Work rates listed and extend outage duration on an hour for hour basis.

- Duration is expected to be six (6) days working two (2) twelve-hour shifts per day.

- Terms & Conditions

This proposal shall be valid for thirty (30) days; provided, however, the obligation to treat this proposal as confidential, and that it cannot be shared with any third party without the prior written consent of ProEnergy, shall survive.

This proposal, and any resulting contract or agreement, shall be subject to the terms and conditions set forth in the attached Supplemental Terms.

- Follow Up

Omar Petit, Regional Sales Manager-Latin America

opetit@proenergyservices.com

Office:	660.829.5100

Fax:     660.829.1160

Cell:	660.281.8588

- Conclusion

Why select ProEnergy Services?

ProEnergy Services is the right teaming partner for Gazprom! ProEnergy Services has talent, depth of experience and resources unparalleled in the power generation industry.  When you succeed, we succeed.  ProEnergy Services will win your confidence and your business one job at a time, starting now!

- Attachment A

- Supplemental Terms

These Supplemental Terms complement and are included as part of ProEnergy’s Proposal No. 409-2693 dated September 10, 2009 to Gazcom for the Hot Gas Path Inspection and would be included in any resulting Contract:

1.	Terms obligating ProEnergy to accept pre-existing site conditions and drawing specifications shall only apply in the event ProEnergy has actually been to the sight or inspected the drawings prior to commencement of the work.

2.	For invoice payments not received by ProEnergy within 30 days from the date of receipt, a late fee of the lesser of 1 ½ % per month or the highest rate allow by applicable law may be assessed.  If Client fails to timely make payment ProEnergy may also suspend or terminate performance of any and all of its work.

3.	No retainage will apply in the event ProEnergy is required to post a performance bond.  In no event shall retainage exceed 10% of each invoiced amount.

4. 	Any prohibition on placing a lien on the project by ProEnergy shall be subject to Client fulfilling its payment obligations under the Contract.

5. 	The parties shall indemnify, defend and hold one other harmless from and against any and all liabilities, claims, demands, suits, losses, damages, costs and expenses (including reasonable attorney fees and court costs) for bodily injury to or death of any third person, or damage to or destruction of any property of third party, caused by any negligent act or omission on the part of the indemnifying party its officers, employees, contractors or agents, except to the extent such liabilities, claims, suits, losses, damages, costs and expenses result from any negligent or willful act or omission on the part of the indemnified party, its officers, employees, contractors or agents.

6. 	ProEnergy’s obligation to indemnify and protect Client against infringement of third party intellectual property rights is subject to: (i) ProEnergy’s right to settle or defend such claim or seek the right of continued use or modify or replace the infringing work, (ii) only work which is otherwise not provided according to Client’s design or instructions, (iii) the work being used by Client for its intended use under the Contract, and (iv) any work not manufactured or developed directly by ProEnergy will be limited only to the indemnity, if any, of the manufacturer or vendor of said work.

7.	ProEnergy shall not be responsible or liable for delays in performance of its obligations under the Contract due to any event of force majeure or any other cause beyond its reasonable control.

8.	ProEnergy warrants that its work shall be performed in a competent, diligent and workmanlike manner, of good quality and material, and in compliance with any mutually agreed written instructions or specifications.  ProEnergy’s work shall be warranted for a period of one (1) year from the date of completing the work.  Any repairs or replacements made to ProEnergy’s work during the warranty period shall be warranted for the remainder of the original warranty term or 90 days, whichever is longer.  This provision sets forth the exclusive remedies for all claims based on failure of or defect in the ProEnergy’s work provided under the Contract whether the failure arises before, during or after the warranty period and whether said claim is based on contract, indemnity, warranty, tort (including negligence), strict liability or otherwise.  NO IMPLIED, STATUTORY, OR COMMON LAW WARRANTY OF ANY KIND, INCLUDING MERCHANTABILITY OR FITNESS FOR A PARTICULAR PURPOSE, SHALL APPLY.    The duties, liabilities and obligations of ProEnergy do not extend to any repairs, adjustments, alterations, replacements or maintenance that may be required as a result of normal wear and tear, normal degradation in the performance of equipment, or as a result of (a) improper repair or alteration by Client or other persons, (b) misuse, negligence or damage by Client or other persons, (c) excessive operation at peak capacity, frequent starting, type of fuel, detrimental air inlet conditions, or erosion, corrosion or material deposit of fluids.  The warranty and remedies are further conditioned upon (i) the proper storage, installation, operation and maintenance of the equipment and conformance with the operation and instruction manuals provided by the suppliers and manufacturers and (ii) repair or modification pursuant to the instructions of the suppliers and manufacturers and as otherwise directed by ProEnergy.

9.	Care, custody, control and risk of loss for the work of ProEnergy shall pass to Client upon the earlier of when the work is completed or when it is taken over and used by Client.

10.	The total liability of ProEnergy for all claims of any kind, whether based on contract, warranty, tort (including negligence), indemnity, strict liability or otherwise, for any loss or damage arising out of, connected with, or resulting from the Contract or its work shall in no case exceed the total contract price for the work giving rise to such claim plus any insurance proceeds recovered under the coverages furnished by ProEnergy under the Contract. Notwithstanding anything in the Contract or at law to the contrary, ProEnergy shall in no event be liable for exemplary, special, incidental, indirect or consequential damages of any kind including, but not limited to, loss of use, profits or revenue.  ProEnergy shall have no liability for its competent performance of instructions given by Client or its personnel or representatives in the event such instructions prove to be defective.

11.	ProEnergy will be given at  least 10 days advance written notice and an opportunity to cure before Client may terminate the Contract for a breach of any material term of the Contract by ProEnergy.

12.	In the event ProEnergy agrees to the payment of liquidated damages (LDs) for unexcused shortfalls in any guaranteed performance or delays in any guaranteed completion date(s) then (i) the payment of LDs shall be Client’s exclusive remedy (ii) the total amount of LDs shall not exceed 10% of the total contract price unless otherwise agreed, and (iii) a corresponding bonus shall be paid by Client to ProEnergy in the event of better than guaranteed performance or early completion by ProEnergy.

13. 	Any dispute which cannot be settled amicably between the parties under the Contract will be submitted to binding and final arbitration under the Rules of the American Arbitration Association and such proceeding will be held in a mutually agreeable location.

14.	ProEnergy is not responsible for furnishing any performance bonds and builder’s risk or professional liability insurance unless specifically included in its proposal and proposal price.