## Tacoa Consolidated (hidden)
Planta Picure/Tacoa(2)LM2500s
10-T9003A | Contract Dated June 30, 2009
Customer: | Derwick Associates S.A.
MMG Tower, Piso 16, Calle 53, Urbanizacion Marbella,
Cuidad de Panama, Republica de Panama
Attn: Aljandro Betancourt Lopez
Telefax: 58-212-975-2269
| Payment Schedule |  | Total Bs | 10218950
|  |  |  | A | B
| Description | % | Total Bs | 10218950 | 11268150 | TACOA | Invoice | Invoice |  | Payment | Balance | Observation
Milestone | Milestones are for Unit 1 and 2 |  | Amount | Total Milestone | Total Milestone | CONSOLIDATED | Number | Date | Pay Date | Amount
Down Payment Due Upon Contract Signing |  | 10% | 1021895 | 1021895 | 1126815 | 2148710 | 42 | 2009-07-21 | 7/21/2009 & 9-14 | 2148710 | 0
|  |  | VAT | 122627.4 | 135217.8 | 257845.2 |  |  |  | 257845.2 | 0
|  |  | Witholding | -45985.275 | -50706.675 | -96691.95 |  |  |  | 0 | -96691.95 | Did not withhold
|  |  | Total | 1098537.125 | 1211326.125 | 2309863.25 |  |  |  | 2406555.2 | -96691.95
Milestone 1 | Civil Works & Conceptual Engineering
| Mobilization to Site | 5% | 510947.5 |  |  |  | 46 & 47 | 8/3/09 & 12/7/09 | 2009-10-25
| Site Preparation Complete | 5% | 510947.5 |  |  |  | 50 & 51 | 8/3/09 & 12/7/09 | 2009-10-25
| Site Excavation Complete | 3% | 306568.5 |  |  |  | 54 & 55 | 8/3/09 & 12/7/09 | 2009-10-25
| Foundation Steel on Site | 2% | 204379 |  |  |  | 58 & 59 | 8/3/09 & 12/7/09 | 2009-10-25
| Gas Turbine Foundation Forms Set | 2% | 204379 |  |  |  | 62 & 63 | 8/3/09 & 12/7/09 | 2009-10-25
| Gas Turbine Foundation Ready to Pour Concrete | 3% | 306568.5 |  |  |  | 66 & 67 | 8/3/09 & 12/7/09 | 2009-10-25
| Concrete Poured in Gas Turbine Foundation | 5% | 510947.5 |  |  |  | 70 & 71 | 8/3/09 & 12/7/09 | 2009-10-25
| Total Milestone 1 |  | Sub Total | 2554737.5 | 2817037.5 | 5371775 |  |  |  | 5371775 | 0
|  |  | VAT | 306568.5 | 338044.5 | 644613 |  |  |  | 644613 | 0
|  |  | Witholding | -114963.1875 | -126766.6875 | -241729.875 |  |  |  | -338421.825 | 96691.95 | Witheld including down payment
|  |  | Total | 2746342.8125 | 3028315.3125 | 5774658.125 |  |  |  | 5677966.175 | 96691.95
Milestone 2 | Gas Turbines Set on Foundations
| Gas Turbine Packages Set on Foundations | 6% | 613137 |  |  |  | 74 & 75 | 8/3/09 & 12/7/09 | 2010-02-08
| Mechanical Contractor Mobilized to Site | 2% | 204379 |  |  |  | 78 & 79 | 8/3/09 & 12/7/09 | 2010-02-08
| Electrical Contractor Mobilized to Site | 2% | 204379 |  |  |  | 82 & 83 | 8/3/09 & 12/7/09 | 2010-02-08
| Total Milestone 2 |  |  | 1021895 | 1126815 | 2148710 |  |  |  | 1074355 | 1074355 | Only invoice 50% of the milestone
|  |  | VAT | 122627.4 | 135217.8 | 257845.2 |  |  |  | 128922.6 | 128922.6
|  |  | Witholding | -45985.275 | -50706.675 | -96691.95 |  |  |  | -48345.975 | -48345.975
|  |  | Total | 1098537.125 | 1211326.125 | 2309863.25 |  |  |  | 1154931.625 | 1154931.625
Milestone 3 | Gas Turbine Package Erection
| Gas Turbine Package Erection Complete | 10% | 1021895 |  |  |  | 86 & 87 | 2010-02-10 | 2010-02-11
| Exhaust Stack Erection Complete | 2% | 204379 |  |  |  | 88 & 89 | 2010-02-10 | 2010-02-11
| Complete BOP Foundations | 3% | 306568.5 |  |  |  | 90 & 91 | 2010-02-10 | 2010-02-11
| Total Milestone 3 |  |  | 1532842.5 | 1690222.5 | 3223065 |  |  |  | 3223065 | 0 | Both contracts paid together
|  |  | VAT | 183941.1 | 202826.7 | 386767.8 |  |  |  | 386767.8 | 0 | Requested for Derwick we did not invoice them until they received the Bolivars
|  |  | Witholding | -68977.9125 | -76060.0125 | -145037.925 |  |  |  | -145037.925 | 0
|  |  | Total | 1647805.6875 | 1816989.1875 | 3464794.875 |  |  |  | 3464794.875 | 0
Milestone 4 | Mechanical Completion
| Set Gas Compressors on Foundations | 4% | 408758 |  |  |  | 106 & 107 | 2010-05-04 | outstanding
| Erect Water Treatment Equipment | 3% | 306568.5 |  |  |  | 108 & 109 | 2010-05-04 | outstanding
| Interconnect Piping Installed | 3% | 306568.5 |  |  |  | 110 & 111 | 2010-05-04 | outstanding
| Total Milestone 4 |  |  | 1021895 | 1126815 | 2148710 | 112 | 2010-05-04 | outstanding | 8000000 | -5851290 | From Milestone # 2, 5% invoiced
|  |  | VAT | 122627.4 | 135217.8 | 257845.2 |  |  |  |  | 257845.2
|  |  | Witholding | -45985.275 | -50706.675 | -96691.95 |  |  |  |  | -96691.95
|  |  | Total | 1098537.125 | 1211326.125 | 2309863.25 |  |  |  | 8000000 | -5690136.75
Milestone 5 | Electrical Completion
| Eletrical BOP Equipment Installed | 2% | 204379 |  |  |  | 113 & 114 | 2010-05-04 | outstanding
| Electrical BOP Interconnect Cabling Installed | 4% | 408758 |  |  |  | 115 & 116 | 2010-05-04 | outstanding
| 69KV Transmission Relocation Complete | 4% | 408758 |  |  |  | 117 & 118 | 2010-05-04 | outstanding
| Total Milestone 5 |  |  | 1021895 | 1126815 | 2148710 |  |  | 2010-04-07 |  | 2148710
|  |  | VAT | 122627.4 | 135217.8 | 257845.2 |  |  |  |  | 257845.2
|  |  | Witholding | -45985.275 | -50706.675 | -96691.95 |  |  |  |  | -96691.95
|  |  | Total | 1098537.125 | 1211326.125 | 2309863.25 |  |  |  |  | 2309863.25
Milestone 6 | Precommissioning Complete
| Mechanical Equipment Flushed and Checked | 4% | 408758 |  |  |  | 125 & 126 | 2010-05-04 | outstanding
| Hydrostatic Testing Complete | 2% | 204379 |  |  |  | 127 & 128 | 2010-05-04 | outstanding
| Pumps Rotated and Tested | 2% | 204379 |  |  |  | 129 & 130 | 2010-05-04 | outstanding
| Mechanical Systems Ready for Startup | 3% | 306568.5 |  |  |  | 131 & 132 | 2010-05-04 | outstanding
| Electrical Equipment Statically Tested | 4% | 408758 |  |  |  | 133 & 134 | 2010-05-04 | outstanding
| Total Milestone 6 |  |  | 1532842.5 | 1690222.5 | 3223065 |  |  | 2010-04-07 |  | 3223065
|  |  | VAT | 183941.1 | 202826.7 | 386767.8 |  |  |  |  | 386767.8
|  |  | Witholding | -68977.9125 | -76060.0125 | -145037.925 |  |  |  |  | -145037.925
|  |  | Total | 1647805.6875 | 1816989.1875 | 3464794.875 |  |  |  |  | 3464794.875
Milestone 7 | Plant Commissioning & Testing Complete
| Gas Turbines Tested and Ready for Commercial Operation | 3% | 306568.5 |  |  |  | 145 & 146 | 2010-05-04 | outstanding
| All Mechanical Auxiliary and BOP Equipment Ready for Commercial Operation | 1% | 102189.5 |  |  |  | 147 & 148 | 2010-05-04 | outstanding
| All Electrical Auxiliary and BOP Equipment Tested and Ready for Commercial Operation | 1% | 102189.5 |  |  |  | 149 & 150 | 2010-05-04 | outstanding
| Total Milestone 7 |  |  | 510947.5 | 563407.5 | 1074355 |  |  | 2010-07-07 |  | 1074355
|  |  | VAT | 61313.7 | 67608.9 | 128922.6 |  |  |  |  | 128922.6
|  |  | Witholding | -22992.6375 | -25353.3375 | -48345.975 |  |  |  |  | -48345.975
|  |  | Total | 549268.5625 | 605663.0625 | 1154931.625 |  |  |  |  | 1154931.625
| Sub Total | 100% |  | 10218950 | 11268150 | 21487100 |  |  |  | 19817905 | 1669195
| VAT |  |  | 1226274 | 1352178 | 2578452 |  |  |  | 1418148.6 | 1160303.4
| Witholding |  |  | -459852.75 | -507066.75 | -966919.5 |  |  |  | -531805.725 | -435113.775
| Total |  |  | 10985371.25 | 12113261.25 | 23098632.5 |  |  |  | 20704247.875 | 2394384.625

## VEF Invoicing Summary
VEF Invoice Report July 13
Data
Project | Milestone | Invoice Date | Date Paid | Sum of Cost B/T | Sum of Inoviced B/T | Sum of VAT | Sum of WH | Sum of Total Invoiced | Sum of Paid | Sum of Balance
Guarenas | Down Payment | 2010-05-13 | 2010-04-05 | 10421177.5 | 10421177.5 | 1250541.3 | -468952.9875 | 11202765.8125 | 10421177.5 | 781588.3125
| 1 | 2010-06-07 | - | 4168471 | 4168471 | 500216.52 | -187581.195 | 4481106.325 | 0 | 4481106.325
| 2 | 0 | - | 6252706.5 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | 0 | - | 6252706.5 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | 0 | - | 4168471 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | 0 | - | 4168471 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | 0 | - | 2084235.5 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | 0 | - | 2084235.5 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | 0 | - | 2084235.5 | 0 | 0 | 0 | 0 | 0 | 0
Guarenas Total |  |  |  | 41684710 | 14589648.5 | 1750757.82 | -656534.1825 | 15683872.1375 | 10421177.5 | 5262694.6375
La Raisa | Down Payment | 2010-01-21 | 2010-01-25 | 10483646.75 | 10483646.75 | 1258037.61 | -471764.1038 | 11269920.2562 | 4507968.425 | 6761951.8312
| 1 | 2010-04-06 | 2010-04-15 | 4193458.7 | 4193458.7 | 503215.044 | -188705.6415 | 4507968.1025 | 11269920.2562 | -6761952.1537
| 2 | 2010-04-06 | 15/06/2010 | 2096729.35 | 2096729.35 | 251607.522 | -94352.8207 | 2253984.0513 | 2253984.0513 | 0
| 3 | 2010-04-07 | 2020-05-28 | 6290188.05 | 6290188.05 | 754822.566 | -283058.4623 | 6761952.1538 | 6761952.1538 | 0
| 4 | 2010-05-13 | 2020-05-28 | 6290188.05 | 6290188.05 | 754822.566 | -283058.4622 | 6761952.1537 | 6761952.1537 | 0
| 5 | 2010-05-13 | - | 6290188.05 | 6290188.05 | 754822.566 | -283058.4623 | 6761952.1538 | 0 | 6761952.1538
| 6 | 2010-05-13 | - | 2096729.35 | 2096729.35 | 251607.522 | -94352.8207 | 2253984.0513 | 0 | 2253984.0513
| 7 | 2010-06-08 | - | 2096729.35 | 2096729.35 | 251607.522 | -94352.8208 | 2253984.0513 | 0 | 2253984.0513
| 8 | 2010-06-08 | - | 2096729.35 | 2096729.35 | 251607.522 | -94352.8207 | 2253984.0513 | 0 | 2253984.0513
| T-9018-CO-001 | 2010-06-01 | - | 374843.75 | 374843.75 | 44981.25 | -16867.9687 | 402957.0312 | 0 | 402957.0312
| T-9018-CO-008 | 2010-06-01 | - | 730291.4107 | 730291.4107 | 87634.9693 | -32863.1135 | 785063.2665 | 0 | 785063.2665
La Raisa Total |  |  |  | 43039722.1607 | 43039722.1607 | 5164766.6593 | -1936787.4972 | 46267701.3228 | 31555777.04 | 14711924.2828
Tacoa 2500 | Down Payment | 2009-07-21 | 7/21/2009 & 9-14 | 1021895 | 1021895 | 122627.4 | -45985.275 | 1098537.125 | 1144522.4 | -45985.275
| 1 | 8/3/09 & 12/7/09 | 2009-10-25 | 2554737.5 | 2554737.5 | 306568.5 | -114963.1875 | 2746342.8125 | 2700357.5325 | 45985.28
| 2 | 8/3/09 & 12/7/09 | 2010-02-08 | 1021895 | 510947.5 | 61313.7 | -22992.6375 | 549268.5625 | 549268.5625 | 0
| 3 | 2010-02-10 | 2010-02-11 | 1532842.5 | 1532842.5 | 183941.1 | -68977.9125 | 1647805.6875 | 1647805.6875 | 0
| 4 | 2010-05-04 | - | 1021895 | 1532842.5 | 183941.1 | -68977.9125 | 1647805.6875 | 0 | 1647805.6875
| 5 | 2010-05-04 | - | 1021895 | 1021895 | 122627.4 | -45985.275 | 1098537.125 | 0 | 1098537.125
| 6 | 2010-05-04 | - | 1532842.5 | 1532842.5 | 183941.1 | -68977.9125 | 1647805.6875 | 0 | 1647805.6875
| 7 | 2010-05-04 | - | 510947.5 | 510947.5 | 61313.7 | -22992.6375 | 549268.5625 | 0 | 549268.5625
| T-9003A-CO-016 | 2010-06-02 | - | 3393615.5 | 3393615.5 | 407233.86 | -152712.6975 | 3648136.6625 | 0 | 3648136.6625
| T-9003A-CO-017 | 2010-06-02 | - | 2048962.375 | 2048962.375 | 245875.485 | -92203.3069 | 2202634.5531 | 0 | 2202634.5531
Tacoa 2500 Total |  |  |  | 15661527.875 | 15661527.875 | 1879383.345 | -704768.7544 | 16836142.4656 | 6041954.1825 | 10794188.2831
Tacoa 6000 | Down Payment | 2009-07-21 | 7/21/2009 & 9/14/09 | 1126815 | 1126815 | 135217.8 | -50706.675 | 1211326.125 | 1262032.8 | -50706.675
| 1 | 8/3/09 & 12/7/09 | 2009-10-25 | 2817037.5 | 2817037.5 | 338044.5 | -126766.6875 | 3028315.3125 | 2977608.6325 | 50706.68
| 2 | 8/3/09 & 12/7/09 | 2010-02-08 | 1126815 | 563407.5 | 67608.9 | -25353.3375 | 605663.0625 | 605663.0625 | 0
| 3 | 2010-02-10 | 2010-02-11 | 1690222.5 | 1690222.5 | 202826.7 | -76060.0125 | 1816989.1875 | 1816989.1875 | 0
| 4 | 2010-05-04 | - | 1126815 | 1663222.5 | 199586.7 | -74845.0125 | 1787964.1875 | 0 | 1787964.1875
| 5 | 2010-05-04 | - | 1126815 | 1126815 | 135217.8 | -50706.675 | 1211326.125 | 0 | 1211326.125
| 6 | 2010-05-04 | - | 1690222.5 | 1690222.5 | 202826.7 | -76060.0125 | 1816989.1875 | 0 | 1816989.1875
| 7 | 2010-05-04 | - | 563407.5 | 563407.5 | 67608.9 | -25353.3375 | 605663.0625 | 0 | 605663.0625
Tacoa 6000 Total |  |  |  | 11268150 | 11241150 | 1348938 | -505851.75 | 12084236.25 | 6662293.6825 | 5421942.5675
Termozulia | Down Payment | 2009-10-02 | 2009-10-10 | 9890000 | 9890000 | 0 | 0 | 9890000 | 9890000 | 0
| Civil Work | 2010-03-17 | - | 4945000 | 4945000 | 0 | 0 | 4945000 | 4945000 | 0
| Electrical Work | 2010-03-17 | - | 4945000 | 4945000 | 0 | 0 | 4945000 | 0 | 4945000
Termozulia Total |  |  |  | 19780000 | 19780000 | 0 | 0 | 19780000 | 14835000 | 4945000
All Proejects | Services to different projects | 21/06/2010 | 21-30/06/2010 | 26785714.2857 | 26785714.2857 | 3214285.7143 | 0 | 30000000 | 30000000 | 0
|  | 2010-09-07 | 21-30/06/2010 | 13928571.4286 | 13928571.4286 | 1671428.5714 | 0 | 15600000 | 15600000 | 0
All Proejects Total |  |  |  | 40714285.7143 | 40714285.7143 | 4885714.2857 | 0 | 45600000 | 45600000 | 0
Las Morochas | Down Payment | 23/06/2010 | (blank) | 7241700 | 7241700 | 869004 | -586577.7 | 7524126.3 | 7524126.3 | 0
| 1 | 23/06/2010 | (blank) | 4827800 | 4827800 | 579336 | -217251 | 5189885 | 0 | 5189885
| 2 | (blank) | (blank) | 4827800
| 3 | (blank) | (blank) | 3620850
| 4 | (blank) | (blank) | 2413900
| 5 | (blank) | (blank) | 1206950
Las Morochas Total |  |  |  | 24139000 | 12069500 | 1448340 | -803828.7 | 12714011.3 | 7524126.3 | 5189885
Furrial | Down Payment | 23/06/2010 | (blank) | 29897345.4 | 29897345.4 | 3587681.448 | -1345380.543 | 32139646.305 | 0 | 32139646.305
| 1 | (blank) | (blank) | 19931563.6
| 2 | (blank) | (blank) | 19931563.6
| 3 | (blank) | (blank) | 14948672.7
| 4 | (blank) | (blank) | 9965781.8
| 5 | (blank) | (blank) | 4982890.9
| 10-T1004-Co-001 | 2010-07-09 | (blank) | 1102301.61 | 1102301.61 | 132276.1932 | -49603.5724 | 1184974.2308 |  | 1184974.2308
| 10-T1004-Co-002 | 2010-07-09 | (blank) | 934339.23 | 934339.23 | 112120.7076 | -42045.2653 | 1004414.6722 |  | 1004414.6722
| 10-T1004-Co-003 | 2010-07-09 | (blank) | 2673144.15 | 2673144.15 | 320777.298 | -120291.4867 | 2873629.9612 |  | 2873629.9612
| 10-T1004-Co-004 | (blank) | (blank) |  |  | 0 | 0 | 0 |  | 0
| 10-T1004-Co-005 | 2010-07-09 | (blank) | 183775.9 | 183775.9 | 22053.108 | -8269.9155 | 197559.0925 |  | 197559.0925
Furrial Total |  |  |  | 104551378.89 | 34790906.29 | 4174908.7548 | -1565590.783 | 37400224.2617 | 0 | 37400224.2617
Grand Total |  |  |  | 300838774.64 | 191886740.54 | 20652808.8648 | -6173361.6672 | 206366187.7376 | 122640328.705 | 83725859.0326

## Summary Data
Accounts Receivable Summary
Project | Milestone | Cost B/T | Invoice Date | Date Paid | Inoviced B/T | VAT | WH | Total Invoiced | Paid | Balance
Tacoa 2500 | Down Payment | 1021895 | 2009-07-21 | 7/21/2009 & 9-14 | 1021895 | 122627.4 | -45985.275 | 1098537.125 | 1144522.4 | -45985.275
Tacoa 2500 | 1 | 2554737.5 | 8/3/09 & 12/7/09 | 2009-10-25 | 2554737.5 | 306568.5 | -114963.1875 | 2746342.8125 | 2700357.5325 | 45985.28
Tacoa 2500 | 2 | 1021895 | 8/3/09 & 12/7/09 | 2010-02-08 | 510947.5 | 61313.7 | -22992.6375 | 549268.5625 | 549268.5625 | 0
Tacoa 2500 | 3 | 1532842.5 | 2010-02-10 | 2010-02-11 | 1532842.5 | 183941.1 | -68977.9125 | 1647805.6875 | 1647805.6875 | 0
Tacoa 2500 | 4 | 1021895 | 2010-05-04 | - | 1532842.5 | 183941.1 | -68977.9125 | 1647805.6875 | 0 | 1647805.6875
Tacoa 2500 | 5 | 1021895 | 2010-05-04 | - | 1021895 | 122627.4 | -45985.275 | 1098537.125 | 0 | 1098537.125
Tacoa 2500 | 6 | 1532842.5 | 2010-05-04 | - | 1532842.5 | 183941.1 | -68977.9125 | 1647805.6875 | 0 | 1647805.6875
Tacoa 2500 | 7 | 510947.5 | 2010-05-04 | - | 510947.5 | 61313.7 | -22992.6375 | 549268.5625 | 0 | 549268.5625
Tacoa 6000 | Down Payment | 1126815 | 2009-07-21 | 7/21/2009 & 9/14/09 | 1126815 | 135217.8 | -50706.675 | 1211326.125 | 1262032.8 | -50706.675
Tacoa 6000 | 1 | 2817037.5 | 8/3/09 & 12/7/09 | 2009-10-25 | 2817037.5 | 338044.5 | -126766.6875 | 3028315.3125 | 2977608.6325 | 50706.68
Tacoa 6000 | 2 | 1126815 | 8/3/09 & 12/7/09 | 2010-02-08 | 563407.5 | 67608.9 | -25353.3375 | 605663.0625 | 605663.0625 | 0 | 563407.5
Tacoa 6000 | 3 | 1690222.5 | 2010-02-10 | 2010-02-11 | 1690222.5 | 202826.7 | -76060.0125 | 1816989.1875 | 1816989.1875 | 0
Tacoa 6000 | 4 | 1126815 | 2010-05-04 | - | 1663222.5 | 199586.7 | -74845.0125 | 1787964.1875 | 0 | 1787964.1875 | -536407.5
Tacoa 6000 | 5 | 1126815 | 2010-05-04 | - | 1126815 | 135217.8 | -50706.675 | 1211326.125 | 0 | 1211326.125 | 27000
Tacoa 6000 | 6 | 1690222.5 | 2010-05-04 | - | 1690222.5 | 202826.7 | -76060.0125 | 1816989.1875 | 0 | 1816989.1875
Tacoa 6000 | 7 | 563407.5 | 2010-05-04 | - | 563407.5 | 67608.9 | -25353.3375 | 605663.0625 | 0 | 605663.0625
La Raisa | Down Payment | 10483646.75 | 2010-01-21 | 2010-01-25 | 10483646.75 | 1258037.61 | -471764.1038 | 11269920.2562 | 4507968.425 | 6761951.8312
La Raisa | 1 | 4193458.7 | 2010-04-06 | 2010-04-15 | 4193458.7 | 503215.044 | -188705.6415 | 4507968.1025 | 11269920.2562 | -6761952.1537
La Raisa | 2 | 2096729.35 | 2010-04-06 | 15/06/2010 | 2096729.35 | 251607.522 | -94352.8207 | 2253984.0513 | 2253984.0513 | 0
La Raisa | 3 | 6290188.05 | 2010-04-07 | 2020-05-28 | 6290188.05 | 754822.566 | -283058.4623 | 6761952.1538 | 6761952.1538 | 0
La Raisa | 4 | 6290188.05 | 2010-05-13 | 2020-05-28 | 6290188.05 | 754822.566 | -283058.4622 | 6761952.1537 | 6761952.1537 | 0
La Raisa | 5 | 6290188.05 | 2010-05-13 | - | 6290188.05 | 754822.566 | -283058.4623 | 6761952.1538 | 0 | 6761952.1538
La Raisa | 6 | 2096729.35 | 2010-05-13 | - | 2096729.35 | 251607.522 | -94352.8207 | 2253984.0513 | 0 | 2253984.0513
La Raisa | 7 | 2096729.35 | 40337 | - | 2096729.35 | 251607.522 | -94352.8208 | 2253984.0513 | 0 | 2253984.0513
La Raisa | 8 | 2096729.35 | 40337 | - | 2096729.35 | 251607.522 | -94352.8207 | 2253984.0513 | 0 | 2253984.0513
Termozulia | Down Payment | 9890000 | 2009-10-02 | 2009-10-10 | 9890000 | 0 | 0 | 9890000 | 9890000 | 0
Termozulia | Civil Work | 4945000 | 2010-03-17 | - | 4945000 | 0 | 0 | 4945000 | 4945000 | 0
Termozulia | Electrical Work | 4945000 | 40254 | - | 4945000 | 0 | 0 | 4945000 | 0 | 4945000
Guarenas | Down Payment | 10421177.5 | 2010-05-13 | 2010-04-05 | 10421177.5 | 1250541.3 | -468952.9875 | 11202765.8125 | 10421177.5 | 781588.3125
Guarenas | 1 | 4168471 | 2010-06-07 | - | 4168471 | 500216.52 | -187581.195 | 4481106.325 | 0 | 4481106.325
Guarenas | 2 | 6252706.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Guarenas | 3 | 6252706.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Guarenas | 4 | 4168471 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Guarenas | 5 | 4168471 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Guarenas | 6 | 2084235.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Guarenas | 7 | 2084235.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Guarenas | 8 | 2084235.5 | 0 | - | 0 | 0 | 0 | 0 | 0 | 0
Tacoa 2500 | T-9003A-CO-016 | 3393615.5 | 2010-06-02 | - | 3393615.5 | 407233.86 | -152712.6975 | 3648136.6625 | 0 | 3648136.6625
Tacoa 2500 | T-9003A-CO-017 | 2048962.375 | 2010-06-02 | - | 2048962.375 | 245875.485 | -92203.3069 | 2202634.5531 | 0 | 2202634.5531
La Raisa | T-9018-CO-001 | 374843.75 | 2010-06-01 | - | 374843.75 | 44981.25 | -16867.9687 | 402957.0312 | 0 | 402957.0312
La Raisa | T-9018-CO-008 | 730291.4107 | 2010-06-01 | - | 730291.4107 | 87634.9693 | -32863.1135 | 785063.2665 | 0 | 785063.2665
All Proejects | Services to different projects | 26785714.2857 | 21/06/2010 | 21-30/06/2010 | 26785714.2857 | 3214285.7143 | 0 | 30000000 | 30000000 | 0
Las Morochas | Down Payment | 7241700 | 23/06/2010 |  | 7241700 | 869004 | -586577.7 | 7524126.3 | 7524126.3 | 0
Las Morochas | 1 | 4827800 | 23/06/2010 |  | 4827800 | 579336 | -217251 | 5189885 | 0 | 5189885
Las Morochas | 2 | 4827800
Las Morochas | 3 | 3620850
Las Morochas | 4 | 2413900
Las Morochas | 5 | 1206950
Furrial | Down Payment | 29897345.4 | 23/06/2010 |  | 29897345.4 | 3587681.448 | -1345380.543 | 32139646.305 | 0 | 32139646.305
Furrial | 1 | 19931563.6
Furrial | 2 | 19931563.6
Furrial | 3 | 14948672.7
Furrial | 4 | 9965781.8
Furrial | 5 | 4982890.9
All Proejects | Services to different projects | 13928571.4286 | 2010-09-07 | 21-30/06/2010 | 13928571.4286 | 1671428.5714 | 0 | 15600000 | 15600000 | 0
Furrial | 10-T1004-Co-001 | 1102301.61 | 2010-07-09 |  | 1102301.61 | 132276.1932 | -49603.5724 | 1184974.2308 |  | 1184974.2308
Furrial | 10-T1004-Co-002 | 934339.23 | 2010-07-09 |  | 934339.23 | 112120.7076 | -42045.2653 | 1004414.6722 |  | 1004414.6722
Furrial | 10-T1004-Co-003 | 2673144.15 | 2010-07-09 |  | 2673144.15 | 320777.298 | -120291.4867 | 2873629.9612 |  | 2873629.9612
Furrial | 10-T1004-Co-004 |  |  |  |  | 0 | 0 | 0 |  | 0
Furrial | 10-T1004-Co-005 | 183775.9 | 2010-07-09 |  | 183775.9 | 22053.108 | -8269.9155 | 197559.0925 |  | 197559.0925

## Change Order Summary
Change Order Summary July 1st
Data
Project | CO Number | Currency | IV Number | Date Invoiced | Brief Description | Sum of VEF B/T | Sum of VAT VEF | Sum of Total VEF | Sum of USD
CVGA | 410-3202-co-002 | USD | 2000207 | 2010-06-25 | Supply of fire protection skid package |  |  |  | 262913
CVGA Total | [8 empty] | 262913
EL Furrial | 10-T1004-Co-001 | VEF | 179 | 2010-07-09 | Extra Work to Correct the FootPrint | 1102301.61 | 132276.1932 | 1234577.8032
| 10-T1004-Co-002 | VEF | 180 | 2010-07-09 | Construction of 1.8M Fence with 11 gauge cyclone mesh with 6 lines of barbwire | 934339.23 | 112120.7076 | 1046459.9376
| 10-T1004-Co-003 | VEF | 181 | 2010-07-09 | Over Excavation of foot print area. Back Fill removal engineered fill | 2673144.15 | 320777.298 | 2993921.448
| 10-T1004-Co-004 | VEF | (blank) | (blank) | Waitng for Approval |  | 0 | 0
| 10-T1004-Co-005 | VEF | 182 | 2010-07-09 | Temporary Electricity and Potable water at site | 183775.9 | 22053.108 | 205829.008
EL Furrial Total | [5 empty] | 4893560.89 | 587227.3068 | 5480788.1968
La Raisa | T-9018-CO-001 | USD | 100376 | 2010-05-31 | Change from Single gas Pipe to IndividualRuns For Gas |  |  |  | 116684
|  | VEF | 166 | 2010-06-01 | Change from Single gas Pipe to IndividualRuns For Gas | 374843.75 | 44981.25 | 419825
| T-9018-CO-004 | USD | 100377 | 2010-05-31 | 15KV Auxilary Power. |  |  |  | 896220
| T-9018-CO-005 | USD | 100378 | 2010-05-31 | 5KV Auxilary Power. |  |  |  | 773180
| T-9018-CO-006 | USD | 100379 | 2010-05-31 | Add 3 Nema 3R fused disconnect Switches |  |  |  | 76500
| T-9018-CO-007 | USD | 100380 | 2010-05-31 | Install Fire Water system |  |  |  | 326250
| T-9018-CO-008 | VEF | 164 | 2010-06-01 | Labor and Materials Required | 730291.4107 | 87634.9693 | 817926.38
La Raisa Total | [5 empty] | 1105135.1607 | 132616.2193 | 1237751.38 | 2188834
Tacoa | T-9003A-CO-001 | USD | 100367 | 2010-05-31 | Relocation of liquid fue offloading station as orginally desinged and proposed |  |  |  | 30000
| T-9003A-CO-008 | USD | 100373 | 2010-05-21 | The LM6000 gas compressor Movement south |  |  |  | 8000
| T-9003A-CO-009 | USD | 100368 | 2010-05-31 | Removal of existing fuel oil line on the south hill |  |  |  | 90000
| T-9003A-CO-010 | USD | 100371 | 2010-05-31 | A GSU protection panel added |  |  |  | 45000
| T-9003A-CO-011 | USD | 100369 | 2010-05-31 | Road around unit 100 and 200 was added |  |  |  | 100000
| T-9003A-CO-012 | USD | 100370 | 2010-05-21 | Hot tap line main gas line |  |  |  | 45000
| T-9003ACO-013 | USD | 100372 | 2010-05-21 | LM2500 KV Feeder from GTG Circuit brakers to the EDC GSU Transformers |  |  |  | 1061000
| T-9003ACO-014 | USD | 100374 | 2010-05-21 | LM6000 KV Feeder and Inter Tie with EDC transmission Line |  |  |  | 599000
| T-9003A-CO-015 | USD | 100375 | 2010-05-31 | LM600 Gas Compressor nstreumentation |  |  |  | 86000
| T-9003A-CO-016 | USD | 100388 | 2010-05-31 | Extra Work Support. Inserven |  |  |  | 1139908.5
|  | VEF | 168 | 2010-06-01 | Extra Work Support. Inserven | 3393615.5 | 407233.86 | 3800849.36
| T-9003A-CO-017 | VEF | 165 | 2010-06-01 | Movement of Second 69K | 2048962.375 | 245875.485 | 2294837.86
Tacoa Total | [5 empty] | 5442577.875 | 653109.345 | 6095687.22 | 3203908.5
Grand Total | [5 empty] | 11441273.9257 | 1372952.8711 | 12814226.7968 | 5655655.5

## Datos (hidden)
Change Orders Summary
Project | CO Number | Currency | IV Number | Date Invoiced | Brief Description | VEF B/T | VAT VEF | Total VEF | USD
Tacoa | T-9003A-CO-001 | USD | 100367 | 2010-05-31 | Relocation of liquid fue offloading station as orginally desinged and proposed |  |  |  | 30000 | ok
Tacoa | T-9003A-CO-008 | USD | 100373 | 2010-05-21 | The LM6000 gas compressor Movement south |  |  |  | 8000 | ok
Tacoa | T-9003A-CO-009 | USD | 100368 | 2010-05-31 | Removal of existing fuel oil line on the south hill |  |  |  | 90000 | ok
Tacoa | T-9003A-CO-010 | USD | 100371 | 2010-05-31 | A GSU protection panel added |  |  |  | 45000 | ok
Tacoa | T-9003A-CO-011 | USD | 100369 | 2010-05-31 | Road around unit 100 and 200 was added |  |  |  | 100000 | ok
Tacoa | T-9003A-CO-012 | USD | 100370 | 2010-05-21 | Hot tap line main gas line |  |  |  | 45000 | ok
Tacoa | T-9003ACO-013 | USD | 100372 | 2010-05-21 | LM2500 KV Feeder from GTG Circuit brakers to the EDC GSU Transformers |  |  |  | 1061000 | ok
Tacoa | T-9003ACO-014 | USD | 100374 | 2010-05-21 | LM6000 KV Feeder and Inter Tie with EDC transmission Line |  |  |  | 599000 | ok
Tacoa | T-9003A-CO-015 | USD | 100375 | 2010-05-31 | LM600 Gas Compressor nstreumentation |  |  |  | 86000 | ok
Tacoa | T-9003A-CO-016 | VEF | 168 | 2010-06-01 | Extra Work Support. Inserven | 3393615.5 | 407233.86 | 3800849.36 |  | ok
Tacoa | T-9003A-CO-016 | USD | 100388 | 2010-05-31 | Extra Work Support. Inserven |  |  |  | 1139908.5 | ok
Tacoa | T-9003A-CO-017 | VEF | 165 | 2010-06-01 | Movement of Second 69K | 2048962.375 | 245875.485 | 2294837.86 |  | ok
La Raisa | T-9018-CO-001 | USD | 100376 | 2010-05-31 | Change from Single gas Pipe to IndividualRuns For Gas |  |  |  | 116684 | ok
La Raisa | T-9018-CO-001 | VEF | 166 | 2010-06-01 | Change from Single gas Pipe to IndividualRuns For Gas | 374843.75 | 44981.25 | 419825 |  | ok
La Raisa | T-9018-CO-004 | USD | 100377 | 2010-05-31 | 15KV Auxilary Power. |  |  |  | 896220 | ok
La Raisa | T-9018-CO-005 | USD | 100378 | 2010-05-31 | 5KV Auxilary Power. |  |  |  | 773180 | ok
La Raisa | T-9018-CO-006 | USD | 100379 | 2010-05-31 | Add 3 Nema 3R fused disconnect Switches |  |  |  | 76500 | ok
La Raisa | T-9018-CO-007 | USD | 100380 | 2010-05-31 | Install Fire Water system |  |  |  | 326250 | ok
La Raisa | T-9018-CO-008 | VEF | 164 | 2010-06-01 | Labor and Materials Required | 730291.4107 | 87634.9693 | 817926.38 |  | ok
CVGA | 410-3202-co-002 | USD | 2000207 | 2010-06-25 | Supply of fire protection skid package |  |  |  | 262913 | ok
EL Furrial | 10-T1004-Co-001 | VEF | 179 | 2010-07-09 | Extra Work to Correct the FootPrint | 1102301.61 | 132276.1932 | 1234577.8032 |  | ok
EL Furrial | 10-T1004-Co-002 | VEF | 180 | 2010-07-09 | Construction of 1.8M Fence with 11 gauge cyclone mesh with 6 lines of barbwire | 934339.23 | 112120.7076 | 1046459.9376 |  | ok
EL Furrial | 10-T1004-Co-003 | VEF | 181 | 2010-07-09 | Over Excavation of foot print area. Back Fill removal engineered fill | 2673144.15 | 320777.298 | 2993921.448 |  | ok
EL Furrial | 10-T1004-Co-004 | VEF |  |  | Waitng for Approval |  | 0 | 0
EL Furrial | 10-T1004-Co-005 | VEF | 182 | 2010-07-09 | Temporary Electricity and Potable water at site | 183775.9 | 22053.108 | 205829.008 |  | ok

## Tacoa 2500
Planta Picure/Tacoa(2)LM2500s |  | MMG Tower, Piso 16, Calle 53, Urbanizacion Marbella,
10-T9003A | Contract Dated June 30, 2009 | Cuidad de Panama, Republica de Panama
Attn: Aljandro Betancourt Lopez
Customer: | Derwick Associates S.A. | Telefax: 58-212-975-2269
| Description | % | Total Bs | 10218950 | Invoice | Invoice |  | Amount Invoiced | Payment | Balance | Observation
Milestone | Milestones are for Unit 1 and 2 |  | Amount | Total Milestone | Number | Date | Pay Date |  | Amount
Down Payment Due Upon Contract Signing |  | 10% | 1021895 | 1021895 | 42 | 2009-07-21 | 7/21/2009 & 9-14 | 1021895 | 1021895 | 0
|  |  | VAT | 122627.4 |  |  |  | 122627.4 | 122627.4 | 0
|  |  | Witholding | -45985.275 |  |  |  | -45985.275 |  | -45985.275 | Did not withhold
|  |  | Total | 1098537.125 |  |  |  | 1098537.125 | 1144522.4 | -45985.275
Milestone 1 | Civil Works & Conceptual Engineering
| Mobilization to Site | 5% | 510947.5 |  | 46 & 47 | 8/3/09 & 12/7/09 | 2009-10-25 | 510947.5
| Site Preparation Complete | 5% | 510947.5 |  | 50 & 51 | 8/3/09 & 12/7/09 | 2009-10-25 | 510947.5
| Site Excavation Complete | 3% | 306568.5 |  | 54 & 55 | 8/3/09 & 12/7/09 | 2009-10-25 | 306568.5
| Foundation Steel on Site | 2% | 204379 |  | 58 & 59 | 8/3/09 & 12/7/09 | 2009-10-25 | 204379
| Gas Turbine Foundation Forms Set | 2% | 204379 |  | 62 & 63 | 8/3/09 & 12/7/09 | 2009-10-25 | 204379
| Gas Turbine Foundation Ready to Pour Concrete | 3% | 306568.5 |  | 66 & 67 | 8/3/09 & 12/7/09 | 2009-10-25 | 306568.5
| Concrete Poured in Gas Turbine Foundation | 5% | 510947.5 |  | 70 & 71 | 8/3/09 & 12/7/09 | 2009-10-25 | 510947.5
| Total Milestone 1 |  | Sub Total | 2554737.5 |  | 8/3/09 & 12/7/09 | 2009-10-25 | 2554737.5 | 2554737.5 | 0 | Both contracts paid together
|  |  | VAT | 306568.5 |  |  |  | 306568.5 | 306568.5 | 0
|  |  | Witholding | -114963.1875 |  |  |  | -114963.1875 | -160948.4675 | 45985.28 | Witheld including down payment (not paid on 7/21 inv 42)
|  |  | Total | 2746342.8125 |  |  |  | 2746342.8125 | 2700357.5325 | 45985.28 | totals out at bottom / grand total
Milestone 2 | Gas Turbines Set on Foundations
| Gas Turbine Packages Set on Foundations | 6% | 613137 |  | 74 & 75 | 8/3/09 & 12/7/09 | 2010-02-08 | 306568.5
| Mechanical Contractor Mobilized to Site | 2% | 204379 |  | 78 & 79 | 8/3/09 & 12/7/09 | 2010-02-08 | 102189.5
| Electrical Contractor Mobilized to Site | 2% | 204379 |  | 82 & 83 | 8/3/09 & 12/7/09 | 2010-02-08 | 102189.5
| Total Milestone 2 |  |  | 1021895 |  | 8/3/09 & 12/7/09 | 2010-02-08 | 510947.5 | 510947.5 | 0 | Only invoice 50% of the milestone - Derwick requested to apply to milestone 4 | 510947.5
|  |  | VAT | 122627.4 |  |  |  | 61313.7 | 61313.7 | 0
|  |  | Witholding | -45985.275 |  |  |  | -22992.6375 | -22992.6375 | 0
|  |  | Total | 1098537.125 |  |  |  | 549268.5625 | 549268.5625 | 0
Milestone 3 | Gas Turbine Package Erection
| Gas Turbine Package Erection Complete | 10% | 1021895 |  | 86 & 87 | 2010-02-10 | 2010-02-11 | 1021895
| Exhaust Stack Erection Complete | 2% | 204379 |  | 88 & 89 | 2010-02-10 | 2010-02-11 | 204379
| Complete BOP Foundations | 3% | 306568.5 |  | 90 & 91 | 2010-02-10 | 2010-02-11 | 306568.5
| Total Milestone 3 |  |  | 1532842.5 |  | 2010-02-10 | 2010-02-11 | 1532842.5 | 1532842.5 | 0 | Requested byDerwick to not invoice until they received Bolivars | 0
|  |  | VAT | 183941.1 |  |  |  | 183941.1 | 183941.1 | 0
|  |  | Witholding | -68977.9125 |  |  |  | -68977.9125 | -68977.9125 | 0
|  |  | Total | 1647805.6875 |  |  |  | 1647805.6875 | 1647805.6875 | 0
Milestone 4 | Mechanical Completion
| Set Gas Compressors on Foundations | 4% | 408758 |  | 106 & 107 | 2010-05-04 | outstanding | 408758
| Erect Water Treatment Equipment | 3% | 306568.5 |  | 108 & 109 | 2010-05-04 | outstanding | 306568.5
| Interconnect Piping Installed | 3% | 306568.5 |  | 110 & 111 | 2010-05-04 | outstanding | 306568.5
| 5% contract value from milestone 2 |  |  |  | 112 | 2010-05-04 | outstanding | 510947.5
| Total Milestone 4 |  |  | 1021895 |  | 2010-05-04 | outstanding | 1532842.5 |  | 1532842.5 | It includes remaining 5% from milestone 2 | -510947.5
|  |  | VAT | 122627.4 |  |  |  | 183941.1 |  | 183941.1
|  |  | Witholding | -45985.275 |  |  |  | -68977.9125 |  | -68977.9125
|  |  | Total | 1098537.125 |  |  |  | 1647805.6875 | 0 | 1647805.6875
Milestone 5 | Electrical Completion
| Eletrical BOP Equipment Installed | 2% | 204379 |  | 113 & 114 | 2010-05-04 | outstanding | 204379
| Electrical BOP Interconnect Cabling Installed | 4% | 408758 |  | 115 & 116 | 2010-05-04 | outstanding | 408758
| 69KV Transmission Relocation Complete | 4% | 408758 |  | 117 & 118 | 2010-05-04 | outstanding | 408758
| Total Milestone 5 |  |  | 1021895 |  | 2010-05-04 | 2010-04-07 | 1021895 |  | 1021895
|  |  | VAT | 122627.4 |  |  |  | 122627.4 |  | 122627.4
|  |  | Witholding | -45985.275 |  |  |  | -45985.275 |  | -45985.275
|  |  | Total | 1098537.125 |  |  |  | 1098537.125 |  | 1098537.125
Milestone 6 | Precommissioning Complete
| Mechanical Equipment Flushed and Checked | 4% | 408758 |  | 125 & 126 | 2010-05-04 | outstanding | 408758
| Hydrostatic Testing Complete | 2% | 204379 |  | 127 & 128 | 2010-05-04 | outstanding | 204379
| Pumps Rotated and Tested | 2% | 204379 |  | 129 & 130 | 2010-05-04 | outstanding | 204379
| Mechanical Systems Ready for Startup | 3% | 306568.5 |  | 131 & 132 | 2010-05-04 | outstanding | 306568.5
| Electrical Equipment Statically Tested | 4% | 408758 |  | 133 & 134 | 2010-05-04 | outstanding | 408758
| Total Milestone 6 |  |  | 1532842.5 |  | 2010-05-04 | 2010-04-07 | 1532842.5 |  | 1532842.5
|  |  | VAT | 183941.1 |  |  |  | 183941.1 |  | 183941.1
|  |  | Witholding | -68977.9125 |  |  |  | -68977.9125 |  | -68977.9125
|  |  | Total | 1647805.6875 |  |  |  | 1647805.6875 |  | 1647805.6875
Milestone 7 | Plant Commissioning & Testing Complete
| Gas Turbines Tested and Ready for Commercial Operation | 3% | 306568.5 |  | 145 & 146 | 2010-05-04 | outstanding | 306568.5
| All Mechanical Auxiliary and BOP Equipment Ready for Commercial Operation | 1% | 102189.5 |  | 147 & 148 | 2010-05-04 | outstanding | 102189.5
| All Electrical Auxiliary and BOP Equipment Tested and Ready for Commercial Operation | 1% | 102189.5 |  | 149 & 150 | 2010-05-04 | outstanding | 102189.5
| Total Milestone 7 |  |  | 510947.5 |  | 2010-05-04 | 2010-04-07 | 510947.5 |  | 510947.5
|  |  | VAT | 61313.7 |  |  |  | 61313.7 |  | 61313.7
|  |  | Witholding | -22992.6375 |  |  |  | -22992.6375 |  | -22992.6375
|  |  | Total | 549268.5625 |  |  |  | 549268.5625 |  | 549268.5625
| Sub Total | 100% |  | 10218950 |  |  |  | 10218950 | 5620422.5 | 4598527.5
| VAT |  |  | 1226274 |  |  |  | 1226274 | 674450.7 | 551823.3
| Witholding |  |  | -459852.75 |  |  |  | -459852.75 | -252919.0175 | -206933.7325
| Total |  |  | 10985371.25 |  |  |  | 10985371.25 | 6041954.1825 | 4943417.0675

## Tacoa 6000
Planta Picure/Tacoa(2)LM6000s |  | MMG Tower, Piso 16, Calle 53, Urbanizacion Marbella,
10-T9003B | Contract Dated June 30, 2009 | Cuidad de Panama, Republica de Panama
Attn: Aljandro Betancourt Lopez
Customer: | Derwick Associates S.A. | Telefax: 58-212-975-2269
| Description | % | Total Bs | 11268150 |  | Invoice |  | Amount Invoiced | Payment | Balance | Observation
Milestone | Milestones are for Unit 1 and 2 |  | Amount | Total Milestone | Inv # | Date | Payment Date |  | Amount
Down Payment Due Upon Contract Signing |  | 10% | 1126815 | 1126815 | 42 | 2009-07-21 | 7/21/2009 & 9/14/09 | 1126815 | 1126815 | 0
|  |  | VAT | 135217.8 |  |  |  | 135217.8 | 135217.8 | 0
|  |  | Witholding | -50706.675 |  |  |  | -50706.675 |  | -50706.675 | Did not withhold
|  |  | Total | 1211326.125 |  |  |  | 1211326.125 | 1262032.8 | -50706.675
Milestone 1 | Civil Works & Conceptual Engineering
| Mobilization to Site | 5% | 563407.5 |  | 44& 45 | 8/3/09 & 12/7/09 | 2009-10-25 | 563407.5
| Site Preparation Complete | 5% | 563407.5 |  | 48 & 49 | 8/3/09 & 12/7/09 | 2009-10-25 | 563407.5
| Site Excavation Complete | 3% | 338044.5 |  | 52 & 53 | 8/3/09 & 12/7/09 | 2009-10-25 | 338044.5
| Foundation Steel on Site | 2% | 225363 |  | 56 & 57 | 8/3/09 & 12/7/09 | 2009-10-25 | 225363
| Gas Turbine Foundation Forms Set | 2% | 225363 |  | 60 & 61 | 8/3/09 & 12/7/09 | 2009-10-25 | 225363
| Gas Turbine Foundation Ready to Pour Concrete | 3% | 338044.5 |  | 64 & 65 | 8/3/09 & 12/7/09 | 2009-10-25 | 338044.5
| Concrete Poured in Gas Turbine Foundation | 5% | 563407.5 |  | 68 & 69 | 8/3/09 & 12/7/09 | 2009-10-25 | 563407.5
| Total Milestone 1 |  | VAT | 2817037.5 |  | 8/3/09 & 12/7/09 | 2009-10-25 | 2817037.5 | 2817037.5 | 0
|  |  | Witholding | 338044.5 |  |  |  | 338044.5 | 338044.5 | 0
|  |  | Total | -126766.6875 |  |  |  | -126766.6875 | -177473.3675 | 50706.68 | Witheld including down payment
|  |  |  | 3028315.3125 |  |  |  | 3028315.3125 | 2977608.6325 | 50706.68
Milestone 2 | Gas Turbines Set on Foundations
| Gas Turbine Packages Set on Foundations | 6% | 676089 |  | 72 & 73 | 8/3/09 & 12/7/09 | 2010-02-08 | 338044.5
| Mechanical Contractor Mobilized to Site | 2% | 225363 |  | 76 & 77 | 8/3/09 & 12/7/09 | 2010-02-08 | 112681.5
| Electrical Contractor Mobilized to Site | 2% | 225363 |  | 80 & 81 | 8/3/09 & 12/7/09 | 2010-02-08 | 112681.5
| Total Milestone 2 |  | VAT | 1126815 |  | 8/3/09 & 12/7/09 | 2010-02-08 | 563407.5 | 563407.5 | 0 | Only invoice 50% of the milestone | 563407.5
|  |  | Witholding | 135217.8 |  |  |  | 67608.9 | 67608.9 | 0
|  |  | Total | -50706.675 |  |  |  | -25353.3375 | -25353.3375 | 0
|  |  |  | 1211326.125 |  |  |  | 605663.0625 | 605663.0625 | 0
Milestone 3 | Gas Turbine Package Erection
| Gas Turbine Package Erection Complete | 10% | 1126815 |  | 92 & 93 | 2010-02-10 | 2010-02-11 | 1126815
| Exhaust Stack Erection Complete | 2% | 225363 |  | 94 & 95 | 2010-02-10 | 2010-02-11 | 225363
| Complete BOP Foundations | 3% | 338044.5 |  | 96: 97 & 98 | 2010-02-10 | 2010-02-11 | 338044.5
| Total Milestone 3 |  | VAT | 1690222.5 |  | 2010-02-10 | 2010-02-11 | 1690222.5 | 1690222.5 | 0 | Requested for Derwick we did not invoice them until they received the Bolivars | 0
|  |  | Witholding | 202826.7 |  |  |  | 202826.7 | 202826.7 | 0
|  |  | Total | -76060.0125 |  |  |  | -76060.0125 | -76060.0125 | 0
|  |  |  | 1816989.1875 |  |  |  | 1816989.1875 | 1816989.1875 | 0
Milestone 4 | Mechanical Completion
| Set Gas Compressors on Foundations | 4% | 450726 |  | 99 & 100 | 2010-05-04 | outstanding | 450726
| Erect Water Treatment Equipment | 3% | 338044.5 |  | 101 & 102 | 2010-05-04 | outstanding | 338044.5
| Interconnect Piping Installed | 3% | 338044.5 |  | 103 & 104 | 2010-05-04 | outstanding | 338044.5
| 5% contract value from milestone 2 |  |  |  | 105 | 2010-05-04 | outstanding | 536407.5 |  |  | It was invoiced BSF 536407.50 instead 563407.50
| Total Milestone 4 |  | VAT | 1126815 |  | 2010-05-04 | outstanding | 1663222.5 |  | 1663222.5 | It includes remaining 5% from milestone 2 | -536407.5
|  |  | Witholding | 135217.8 |  |  |  | 199586.7 |  | 199586.7
|  |  | Total | -50706.675 |  |  |  | -74845.0125 |  | -74845.0125
|  |  |  | 1211326.125 |  |  |  | 1787964.1875 | 0 | 1787964.1875
Milestone 5 | Electrical Completion
| Eletrical BOP Equipment Installed | 2% | 225363 |  | 119 & 120 | 2010-05-04 | outstanding | 225363
| Electrical BOP Interconnect Cabling Installed | 4% | 450726 |  | 121 & 122 | 2010-05-04 | outstanding | 450726
| 69KV Transmission Relocation Complete | 4% | 450726 |  | 123 & 124 | 2010-05-04 | outstanding | 450726
| Total Milestone 5 |  | VAT | 1126815 |  | 2010-05-04 |  | 1126815 | 0 | 1126815
|  |  | Witholding | 135217.8 |  |  |  | 135217.8 |  | 135217.8
|  |  | Total | -50706.675 |  |  |  | -50706.675 |  | -50706.675
|  |  |  | 1211326.125 |  |  |  | 1211326.125 |  | 1211326.125
Milestone 6 | Precommissioning Complete
| Mechanical Equipment Flushed and Checked | 4% | 450726 |  | 135 & 136 | 2010-05-04 | outstanding | 450726
| Hydrostatic Testing Complete | 2% | 225363 |  | 137 & 138 | 2010-05-04 | outstanding | 225363
| Pumps Rotated and Tested | 2% | 225363 |  | 139 & 140 | 2010-05-04 | outstanding | 225363
| Mechanical Systems Ready for Startup | 3% | 338044.5 |  | 141 & 142 | 2010-05-04 | outstanding | 338044.5
| Electrical Equipment Statically Tested | 4% | 450726 |  | 143 & 144 | 2010-05-04 | outstanding | 450726
| Total Milestone 6 |  | VAT | 1690222.5 |  | 2010-05-04 | outstanding | 1690222.5 |  | 1690222.5
|  |  | Witholding | 202826.7 |  |  |  | 202826.7 |  | 202826.7
|  |  | Total | -76060.0125 |  |  |  | -76060.0125 |  | -76060.0125
|  |  |  | 1816989.1875 |  |  |  | 1816989.1875 |  | 1816989.1875
Milestone 7 | Plant Commissioning & Testing Complete
| Gas Turbines Tested and Ready for Commercial Operation | 3% | 338044.5 |  | 151 & 152 | 2010-05-04 | outstanding | 338044.5
| All Mechanical Auxiliary and BOP Equipment Ready for Commercial Operation | 1% | 112681.5 |  | 153 & 154 | 2010-05-04 | outstanding | 112681.5
| All Electrical Auxiliary and BOP Equipment Tested and Ready for Commercial Operation | 1% | 112681.5 |  | 155 & 156 | 2010-05-04 | outstanding | 112681.5
| Total Milestone 7 |  | VAT | 563407.5 |  | 2010-05-04 |  | 563407.5 | 0 | 563407.5
|  |  | Witholding | 67608.9 |  |  |  | 67608.9 |  | 67608.9
|  |  | Total | -25353.3375 |  |  |  | -25353.3375 |  | -25353.3375
|  |  |  | 605663.0625 |  |  |  | 605663.0625 |  | 605663.0625
| Sub Total | 100% |  | 11268150 |  |  |  | 11241150 | 6197482.5 | 5043667.5 | 27000
| VAT |  |  | 1352178 |  |  |  | 1348938 | 743697.9 | 605240.1
| Witholding |  |  | -507066.75 |  |  |  | -505851.75 | -278886.7175 | -226965.0325
| Total |  |  | 12113261.25 |  |  |  | 12084236.25 | 6662293.6825 | 5421942.5675

## La Raisa
La Raisa (3) FT8 | Project - Pratt Whitney FT8-3 Swiftpac Units | 13, 8th Avenue Belleville, St. Michael, Barbados
10-T9018 | Contract Dated October 27, 2009 | Attn: Pedro Trebbau Lopez
Customer: | Derwick Associates Corp
|  |  | Total Bs | 41934587 | Invoice | Invoice |  | Amount Invoiced | Payment | Balance | Observation
Milestone | Description | % | Amount | Total Milestone | Number | Date | Payment Date |  | Amount
| Downpayment | 25% | 10483646.75 | 10483646.75 | 85 | 2010-01-21 | 2010-01-25 | 10483646.75 | 4193459 | 6290187.75
|  |  | VAT | 1258037.61 |  |  |  | 1258037.61 | 503215.08 | 754822.53
|  |  | Witholding | -471764.1038 |  |  |  | -471764.1038 | -188705.655 | -283058.4487
|  |  | Total | 11269920.2562 |  |  |  | 11269920.2562 | 4507968.425 | 6761951.8312
Down Payment Due Upon Contract Signing | Civil Works
Milestone 1 | Mobilization to Site | 1% | 419345.87 |  | 157 | 2010-04-06 | 2010-04-15 | 419345.87
| Site Preparation Complete | 2% | 838691.74 |  | 157 | 2010-04-06 | 2010-04-15 | 838691.74
| Site Excavation Complete | 2% | 838691.74 |  | 157 | 2010-04-06 | 2010-04-15 | 838691.74
| Foundation Steel on Site | 1% | 419345.87 |  | 157 | 2010-04-06 | 2010-04-15 | 419345.87
| Gas Turbine Foundation Forms Set | 1% | 419345.87 |  | 157 | 2010-04-06 | 2010-04-15 | 419345.87
| Gas Turbine Foundation Ready to Pour Concrete | 1% | 419345.87 |  | 157 | 2010-04-06 | 2010-04-15 | 419345.87
| Concrete Poured in Gas Turbine Foundations | 2% | 838691.74 |  | 157 | 2010-04-06 | 2010-04-15 | 838691.74
| Total Milestone 1 |  |  | 4193458.7 |  | 2010-04-06 | 2010-04-15 | 4193458.7 | 10483646.75 | -6290188.05
|  |  | VAT | 503215.044 |  |  |  | 503215.044 | 1258037.61 | -754822.566
|  |  | Witholding | -188705.6415 |  |  |  | -188705.6415 | -471764.1038 | 283058.4622
|  |  | Total | 4507968.1025 |  |  |  | 4507968.1025 | 11269920.2562 | -6761952.1537
Gas Turbines Set on Foundations
Milestone 2 | Total Milestone 2 | 5% | 2096729.35 | 2096729.35 | 158 | 2010-04-06 | 15/06/2010 | 2096729.35 | 2096729.35 | 0
|  |  | VAT | 251607.522 |  |  |  | 251607.522 | 251607.522 | 0
|  |  | Witholding | -94352.8207 |  |  |  | -94352.8207 | -94352.8207 | 0
|  |  | Total | 2253984.0513 |  |  |  | 2253984.0513 | 2253984.0513 | 0
Gas Turbine 1 & 2 Erection Complete
Milestone 3 | Assembly of Major Gas Turbine Modules Complete | 10% | 4193458.7 |  | 159 | 2010-04-06 |  | 4193458.7
| Exhaust Stacks Erected | 5% | 2096729.35 |  | 159 | 2010-04-06 |  | 2096729.35
| Total Milestone 3 |  |  | 6290188.05 |  | 2010-04-07 | 2020-05-28 | 6290188.05 | 6290188.05 | 0
|  |  | VAT | 754822.566 |  |  |  | 754822.566 | 754822.566 | 0
|  |  | Witholding | -283058.4623 |  |  |  | -283058.4623 | -283058.4623 | 0
|  |  | Total | 6761952.1538 |  |  |  | 6761952.1538 | 6761952.1538 | 0
Mechanical
Milestone 4 | Gas Turbine #3 Erection Complete | 3% | 1258037.61 |  | 161 | 2010-05-13 |  | 1258037.61
| Gas Turbine Auxiliary Equipment Set | 3% | 1258037.61 |  | 161 | 2010-05-13 |  | 1258037.61
| Interconnect Piping Installed on Units 1 & 2 | 3% | 1258037.61 |  | 161 | 2010-05-13 |  | 1258037.61
| (1) Raw Fuel, (1) Treated Fuel Tank Complete | 3% | 1258037.61 |  | 161 | 2010-05-13 |  | 1258037.61
| Electrical | [6 empty] | 0
| All Major Electrical Equipment Set & Installed | 3% | 1258037.61 |  | 161 | 2010-05-13 |  | 1258037.61
| Total Milestone 4 |  |  | 6290188.05 |  | 2010-05-13 | 2020-05-28 | 6290188.05 | 6290188.05 | 0
|  |  | VAT | 754822.566 |  |  |  | 754822.566 | 754822.566 | 0
|  |  | Witholding | -283058.4622 |  |  |  | -283058.4622 | -283058.4622 | 0
|  |  | Total | 6761952.1537 |  |  |  | 6761952.1537 | 6761952.1537 | 0
Mechanical
Milestone 5 | Liquid Fuel Off Load Station Complete | 2% | 838691.74 |  | 162 | 2010-05-13 |  | 838691.74
| Water Treatment System Installed | 2% | 838691.74 |  | 162 | 2010-05-13 |  | 838691.74
| Interconnect Piping Installed on Unit 3 | 2% | 838691.74 |  | 162 | 2010-05-13 |  | 838691.74
| Gas Compressors Set on Foundation | 2% | 838691.74 |  | 162 | 2010-05-13 |  | 838691.74
Electrical Completion
| All Electrical Interconnect Cabling Installed Units 1&2 | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
Precommissioning Complete on Units 1 &2
| All Mechanical Equipment Flushed and Checked | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
| All Hydrostatic Testing Complete | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
| All Pumps Rotated and Tested | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
| All Mechanical Systems Ready for Startup | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
| All Electrical Equipment Statically Tested | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
| All Electrical Systems Ready for Startup | 1% | 419345.87 |  | 162 | 2010-05-13 |  | 419345.87
| Total Milestone 5 |  |  | 6290188.05 |  | 2010-05-13 |  | 6290188.05 | 0 | 6290188.05
|  |  | VAT | 754822.566 |  |  |  | 754822.566 | 0 | 754822.566
|  |  | Witholding | -283058.4623 |  |  |  | -283058.4623 | 0 | -283058.4623
|  |  | Total | 6761952.1538 |  |  |  | 6761952.1538 | 0 | 6761952.1538 | outstanding
Units 1&2 Commissioning & Testing Complete
Milestone 6 | Gas Turbines Tested and Ready for Commercial Operation | 3% | 1258037.61 |  | 163 | 2010-05-13 |  | 1258037.61
| All Mechanical Auxiliary Ready for Commercial Operation | 1% | 419345.87 |  | 163 | 2010-05-13 |  | 419345.87
| All Electrical Auxiliary Equipment Tested and Ready for Commercial Operation | 1% | 419345.87 |  | 163 | 2010-05-13 |  | 419345.87
| Total Milestone 6 |  |  | 2096729.35 |  | 2010-05-13 |  | 2096729.35 | 0 | 2096729.35
|  |  | VAT | 251607.522 |  |  |  | 251607.522 | 0 | 251607.522
|  |  | Witholding | -94352.8207 |  |  |  | -94352.8207 | 0 | -94352.8207
|  |  | Total | 2253984.0513 |  |  |  | 2253984.0513 | 0 | 2253984.0513 | outstanding
Mechanical
Milestone 7 | All Plant Fuel and Water Tanks Complete | 0.5% | 209672.935 |  |  | 0
| All Plant Fuel and Water Piping Complete | 0.5% | 209672.935
Electrical
| All Electrical Balance of Plant Complete | 0.5% | 209672.935
| All Plant Interconnect Cabling Complete | 0.5% | 209672.935
Precommissioning Complete on Unit 3
| All Mechanical Equipment Flushed and Checked | 0.5% | 209672.935
| All Hydrostatic Testing Complete | 0.5% | 209672.935
| All Pumps Rotated and Tested | 0.5% | 209672.935
| All Mechanical Systems Ready for Startup | 0.5% | 209672.935
| All Electrical Equipment Statically Tested | 0.5% | 209672.935
| All Electrical Systems Ready for Startup | 0.5% | 209672.935
| Total Milestone 7 |  |  | 2096729.35 | 170 | 2010-06-08 |  | 2096729.35 | 0 | 2096729.35 | To be Invoiced June
|  |  | VAT | 251607.522 |  |  |  | 251607.522 | 0 | 251607.522
|  |  | Witholding | -94352.8208 |  |  |  | -94352.8208 | 0 | -94352.8208
|  |  | Total | 2253984.0513 |  |  |  | 2253984.0513 | 0 | 2253984.0513
Plant Commissioning & Testing Complete
Milestone 8 | GT Unit 3 Tested and Ready for Commercial Operation | 1% | 419345.87
| Gas Compression Complete & Ready for PDVSA Gas | 1% | 419345.87
| All Mechanical Auxiliary and Balance of Plant Equipment Ready for Commercial Operation | 1% | 419345.87
| All Electrical Auxiliary and Balance of Plant Equipment Tested and Ready for Commercial Operation | 1% | 419345.87
| All Buildings Finished and Complete | 0.5% | 209672.935
| All Driveways and Finish Grading Complete | 0.5% | 209672.935
| Total Milestone 8 |  |  | 2096729.35 | 170 | 2010-06-08 |  | 2096729.35 | 0 | 2096729.35 | To be Invoiced June
|  |  | VAT | 251607.522 |  |  |  | 251607.522 | 0 | 251607.522
|  |  | Witholding | -94352.8207 |  |  |  | -94352.8207 | 0 | -94352.8207
|  |  | Total | 2253984.0513 |  |  |  | 2253984.0513 | 0 | 2253984.0513
| Sub Total | 100% |  | 41934587 |  |  |  | 41934587 | 29354211.2 | 12580375.8
| VAT |  |  | 5032150.44 |  |  |  | 5032150.44 | 3522505.344 | 1509645.096
| Witholding |  |  | -1887056.415 |  |  |  | -1887056.415 | -1320939.504 | -566116.911
| Total |  |  | 45079681.025 |  |  |  | 45079681.025 | 31555777.04 | 13523903.985

## Termozulia
Termozulia IV
10-T9002
Customer: Corpelec
Payment Schedule
| Total Bs | Invoice | Invoice | Payment | Amount Invoiced | Payment | Balance | Observation
Milestones | Amount | Number | Date | Date |  | Amount
Bs Portion
Down Payment (50%) | 9890000 | 10878 | 2009-10-02 | 2009-10-10 | 9890000 | 9890000 | 0 | 0.1%
| -207690 |  |  |  | -207690 | -9890 | -197800
| 9682310 |  |  |  | 9682310 | 9880110 | -197800
Civil Work Complete (25%) | 4945000 | 200116-VZ | 2010-03-17 | 2010-01-07 | 4945000 | 4945000 | 0 | 4.1%
| -103845 |  |  |  | -103845 | -301645 | 197800
| 4841155 |  |  |  | 4841155 | 4643355 | 197800
Electrical Mechanical Complete (25%) | 4945000 |  | 2010-03-17 |  | 4945000 |  | 4945000
-103845
Total VEF | 19780000 |  |  |  | 33991930 | 29046930 | 4945000 | outstanding

## Guarenas
Guarenas | 2 X GE LM2500 + Duel Fuel and 1 x GE LM6000 Dual Fuel |  | 13, 8th Avenue Belleville, St. Michael, Barbados
10-T1009 | Contract Dated March 26, 2010 |  | Attn: Pedro Trebbau Lopez
Customer: | Derwick Associates Corp |  | Telefax: 58-212-975-2269
|  |  | Total Bs | 41684710 | Invoice | Invoice | Payment | Amount Invoiced | Payment | Balance | Observation
Milestone | Description | % | Amount | Total Milestone | Number | Date | Date |  | Amount
|  | 25% | 10421177.5 | 10421177.5 | 160 | 2010-05-13 | 2010-04-05 | 10421177.5 | 10421177.5 | 0 | Advanced Payment
|  |  | VAT | 1250541.3 |  |  |  | 1250541.3 | 0 | 1250541.3
|  |  | Witholding | -468952.9875 |  |  |  | -468952.9875 | 0 | -468952.9875
|  |  | Total | 11202765.8125 |  |  |  | 11202765.8125 | 10421177.5 | 781588.3125
Down Payment Due Upon Contract Signing | Civil Works
Milestone 1 | Site Preparation Complete | 5% | 2084235.5
| Gas Turbine Foundation Poured for Equipment | 5% | 2084235.5
| Total Milestone 1 |  |  | 4168471 |  | 2010-06-07 |  | 4168471 | 0 | 4168471
|  |  | VAT | 500216.52 |  |  |  | 500216.52 | 0 | 500216.52
|  |  | Witholding | -187581.195 |  |  |  | -187581.195 | 0 | -187581.195
|  |  | Total | 4481106.325 |  |  |  | 4481106.325 | 0 | 4481106.325
Gas Turbines 1 Erection Complete
Milestone 2 | Assembly of Major Gas Turbine Modules Complete | 10% | 4168471
| Exhaust Stacks Erected | 5% | 2084235.5
| Total Milestone 2 |  |  | 6252706.5 |  |  |  |  | 0 | 0
|  |  | VAT | 750324.78 |  |  |  |  | 0 | 0
|  |  | Witholding | -281371.7925 |  |  |  |  | 0 | 0
|  |  | Total | 6721659.4875 |  |  |  |  | 0 | 0
Milestone 3 | Assembly of Major Gas Turbine Modules Complete | 10% | 4168471
| Exhaust Stacks Erected | 5% | 2084235.5
| Total Milestone 3 |  |  | 6252706.5 |  |  |  |  | 0 | 0
|  |  | VAT | 750324.78 |  |  |  |  | 0 | 0
|  |  | Witholding | -281371.7925 |  |  |  |  | 0 | 0
|  |  | Total | 6721659.4875 |  |  |  |  | 0 | 0
Mechanical
Milestone 4 | Gas Turbine #3 Erection Complete | 10% | 4168471
Gas Turbine Auxiliary Equipment Set
Interconnect Piping Installed
Electrical
| All Major Electrical Equipment Set & Installed |  | 0
| Total Milestone 4 |  |  | 4168471 |  |  |  |  | 0 | 0
|  |  | VAT | 500216.52 |  |  |  |  | 0 | 0
|  |  | Witholding | -187581.195 |  |  |  |  | 0 | 0
|  |  | Total | 4481106.325 |  |  |  |  | 0 | 0
Mechanical
Milestone 5 | Water Treatment System Installed | 10% | 4168471
| Interconnect Piping Installed |  | 0
Electrical Completion
| All Electrical Interconnect Cabling Installed Units 1&2 |  | 0
Precommissioning Complete on Units 1 &2
| All Mechanical Equipment Flushed and Checked |  | 0
| All Hydrostatic Testing Complete |  | 0
| All Pumps Rotated and Tested |  | 0
| All Mechanical Systems Ready for Startup |  | 0
| All Electrical Equipment Statically Tested |  | 0
| All Electrical Systems Ready for Startup |  | 0
| Total Milestone 5 |  |  | 4168471 |  |  |  |  | 0 | 0
|  |  | VAT | 500216.52 |  |  |  |  | 0 | 0
|  |  | Witholding | -187581.195 |  |  |  |  | 0 | 0
|  |  | Total | 4481106.325 |  |  |  |  | 0 | 0
Units 1&2 Commissioning & Testing Complete
Milestone 6 | Units 1&2 Tested and Ready for Commercial Operation | 3% | 1250541.3
| All Mechanical Auxiliary Ready for Commercial Operation | 1% | 416847.1
| All Electrical Auxiliary Equipment Tested and Ready for Commercial Operation | 1% | 416847.1
| Total Milestone 6 |  |  | 2084235.5 |  |  |  |  | 0 | 0
|  |  | VAT | 250108.26 |  |  |  |  | 0 | 0
|  |  | Witholding | -93790.5975 |  |  |  |  | 0 | 0
|  |  | Total | 2240553.1625 |  |  |  |  | 0 | 0
Mechanical
Milestone 7 | All Plant Fuel and Water Tanks Complete | 0.5% | 208423.55
| All Plant Fuel and Water Piping Complete | 0.5% | 208423.55
Electrical
| All Electrical Balance of Plant Complete | 0.5% | 208423.55
| All Plant Interconnect Cabling Complete | 0.5% | 208423.55
Precommissioning Complete on Unit 3
| All Mechanical Equipment Flushed and Checked | 0.5% | 208423.55
| All Hydrostatic Testing Complete | 0.5% | 208423.55
| All Pumps Rotated and Tested | 0.5% | 208423.55
| All Mechanical Systems Ready for Startup | 0.5% | 208423.55
| All Electrical Equipment Statically Tested | 0.5% | 208423.55
| All Electrical Systems Ready for Startup | 0.5% | 208423.55
| Total Milestone 7 |  |  | 2084235.5 |  |  |  |  | 0 | 0
|  |  | VAT | 250108.26 |  |  |  |  | 0 | 0
|  |  | Witholding | -93790.5975 |  |  |  |  | 0 | 0
|  |  | Total | 2240553.1625 |  |  |  |  | 0 | 0
Plant Commissioning & Testing Complete
Milestone 8 | GT Unit 3 Tested and Ready for Commercial Operation | 1% | 416847.1
| All Mechanical Auxiliary and Balance of Plant Equipment Ready for Commercial Operation | 1% | 416847.1
| All Electrical Auxiliary and Balance of Plant Equipment Tested and Ready for Commercial Operation | 1% | 416847.1
| All Buildings Finished and Complete | 1% | 416847.1
| All Driveways and Finish Grading Complete | 1% | 416847.1
| Total Milestone 8 |  |  | 2084235.5 |  |  |  |  | 0 | 0
|  |  | VAT | 250108.26 |  |  |  |  | 0 | 0
|  |  | Witholding | -93790.5975 |  |  |  |  | 0 | 0
|  |  | Total | 2240553.1625 |  |  |  |  | 0 | 0
| Sub Total | 100% |  | 41684710 |  |  |  | 14589648.5 | 10421177.5 | 4168471
| VAT |  |  | 5002165.2 |  |  |  | 1750757.82 | 0 | 1750757.82
| Witholding |  |  | -1875811.95 |  |  |  | -656534.1825 | 0 | -656534.1825
| Total |  |  | 44811063.25 |  |  |  | 15683872.1375 | 10421177.5 | 5262694.6375

## Las Morochas
Las Morochas |  |  | 13, 8th Avenue Belleville, St. Michael, Barbados
Attn: Pedro Trebbau Lopez
Customer: | Derwick Associates Corp |  | Telefax: 58-212-975-2269
|  |  | Total Bs | 24139000 | Invoice | Invoice | Payment | Amount Invoiced | Payment | Balance | Observation
Milestone | Description | % | Amount | Total Milestone | Number | Date | Date |  | Amount
Down Payment Due Upon Contract Signing |  | 30% | 7241700 | 7241700 | 175 | 23/06/2010 | 2010-07-08 | 7241700 | 7241700 | 0
|  |  | VAT | 869004 |  |  |  | 869004 | 869004 | 0
|  |  | Witholding 8.1% | -586577.7 |  |  |  | -586577.7 | -586577.7 | 0
|  |  | Total | 7524126.3 |  |  |  | 7524126.3 | 7524126.3 | 0
Civil Works
Milestone 1 | Site Preparation Complete | 10% | 2413900
| Gas Turbine Foundation Poured for Equipment | 10% | 2413900
| Total Milestone 1 |  |  | 4827800 | 176 | 23/06/2010 |  | 4827800 | 0 | 4827800
|  |  | VAT | 579336 |  |  |  | 579336 | 0 | 579336
|  |  | Witholding | -217251 |  |  |  | -217251 | 0 | -217251
|  |  | Total | 5189885 |  |  |  | 5189885 | 0 | 5189885
Gas Turbines 1 Erection Complete
Milestone 2 | Gas Turbine Module Set on Foundation | 20% | 4827800
0
| Total Milestone 2 |  |  | 4827800 |  |  |  |  | 0 | 0
|  |  | VAT | 579336 |  |  |  |  | 0 | 0
|  |  | Witholding | -217251 |  |  |  |  | 0 | 0
|  |  | Total | 5189885 |  |  |  |  | 0 | 0
Milestone 3 | Assembly of Major Gas Turbine Modules Complete | 10% | 2413900
| Exhaust Stacks Erected | 5% | 1206950
| Total Milestone 3 |  |  | 3620850 |  |  |  |  | 0 | 0
|  |  | VAT | 434502 |  |  |  |  | 0 | 0
|  |  | Witholding | -162938.25 |  |  |  |  | 0 | 0
|  |  | Total | 3892413.75 |  |  |  |  | 0 | 0
Precommissioning Complete on Units 1 &2
Milestone 4 | All Mechanical Equipment Flushed and Checked | 10% | 2413900
| All Hydrostatic Testing Complete |  | 0
All Pumps Rotated and Tested
| All Mechanical Systems Ready for Startup |  | 0
All Electrical Equipment Statically Tested
| All Electrical Systems Ready for Startup |  | 0
| Total Milestone 4 |  |  | 2413900 |  |  |  |  | 0 | 0
|  |  | VAT | 289668 |  |  |  |  | 0 | 0
|  |  | Witholding | -108625.5 |  |  |  |  | 0 | 0
|  |  | Total | 2594942.5 |  |  |  |  | 0 | 0
Commissioning & Testing Complete
Milestone 5 | GT Unit 3 Tested and Ready for Commercial Operation | 1% | 241390
| All Mechanical Auxiliary and Balance of Plant Equipment Ready for Commercial Operation | 1% | 241390
| All Electrical Auxiliary and Balance of Plant Equipment Tested and Ready for Commercial Operation | 1% | 241390
| All Buildings Finished and Complete | 1% | 241390
| All Driveways and Finish Grading Complete | 1% | 241390
| Total Milestone 5 |  |  | 1206950 |  |  |  |  | 0 | 0
|  |  | VAT | 144834 |  |  |  |  | 0 | 0
|  |  | Witholding | -54312.75 |  |  |  |  | 0 | 0
|  |  | Total | 1297471.25 |  |  |  |  | 0 | 0
| Sub Total | 100% |  | 24139000 |  |  |  | 12069500 | 7241700 | 4827800
| VAT |  |  | 2896680 |  |  |  | 1448340 | 869004 | 579336
| Witholding |  |  | -1086255 |  |  |  | -543127.5 | -325876.5 | -217251
| Total |  |  | 25949425 |  |  |  | 12974712.5 | 7784827.5 | 5189885

## Furrial
Furrial |  |  | 13, 8th Avenue Belleville, St. Michael, Barbados
Attn: Pedro Trebbau Lopez
Customer: | Derwick Associates Corp |  | Telefax: 58-212-975-2269
|  |  | Total Bs | 99657818 | Invoice | Invoice | Payment | Amount Invoiced | Payment | Balance | Observation
Milestone | Description | % | Amount | Total Milestone | Number | Date | Date |  | Amount
Down Payment Due Upon Contract Signing |  | 30% | 29897345.4 | 29897345.4 | 177 | 23/06/2010 |  | 29897345.4 |  | 29897345.4
|  |  | VAT | 3587681.448 |  |  |  | 3587681.448 | 0 | 3587681.448
|  |  | Witholding | -1345380.543 |  |  |  | -1345380.543 | 0 | -1345380.543
|  |  | Total | 32139646.305 |  |  |  | 32139646.305 | 0 | 32139646.305
Civil Works
Milestone 1 | Site Preparation Complete | 10% | 9965781.8
| Gas Turbine Foundation Poured for Equipment | 10% | 9965781.8
| Total Milestone 1 |  |  | 19931563.6 |  |  |  |  | 0 | 0
|  |  | VAT | 2391787.632 |  |  |  |  | 0 | 0
|  |  | Witholding | -896920.362 |  |  |  |  | 0 | 0
|  |  | Total | 21426430.87 |  |  |  |  | 0 | 0
Gas Turbines 1 Erection Complete
Milestone 2 | Gas Turbine Module Set on Foundation | 20% | 19931563.6
0
| Total Milestone 2 |  |  | 19931563.6 |  |  |  |  | 0 | 0
|  |  | VAT | 2391787.632 |  |  |  |  | 0 | 0
|  |  | Witholding | -896920.362 |  |  |  |  | 0 | 0
|  |  | Total | 21426430.87 |  |  |  |  | 0 | 0
Milestone 3 | Assembly of Major Gas Turbine Modules Complete | 10% | 9965781.8
| Exhaust Stacks Erected | 5% | 4982890.9
| Total Milestone 3 |  |  | 14948672.7 |  |  |  |  | 0 | 0
|  |  | VAT | 1793840.724 |  |  |  |  | 0 | 0
|  |  | Witholding | -672690.2715 |  |  |  |  | 0 | 0
|  |  | Total | 16069823.1525 |  |  |  |  | 0 | 0
Precommissioning Complete on Units 1 &2
Milestone 4 | All Mechanical Equipment Flushed and Checked | 10% | 9965781.8
| All Hydrostatic Testing Complete |  | 0
All Pumps Rotated and Tested
| All Mechanical Systems Ready for Startup |  | 0
All Electrical Equipment Statically Tested
| All Electrical Systems Ready for Startup |  | 0
| Total Milestone 4 |  |  | 9965781.8 |  |  |  |  | 0 | 0
|  |  | VAT | 1195893.816 |  |  |  |  | 0 | 0
|  |  | Witholding | -448460.181 |  |  |  |  | 0 | 0
|  |  | Total | 10713215.435 |  |  |  |  | 0 | 0
Commissioning & Testing Complete
Milestone 5 | GT Tested and Ready for Commercial Operation | 5% | 4982890.9
| All Mechanical Auxiliary and Balance of Plant Equipment Ready for Commercial Operation |  | 0
| All Electrical Auxiliary and Balance of Plant Equipment Tested and Ready for Commercial Operation |  | 0
0
0
| Total Milestone 5 |  |  | 4982890.9 |  |  |  |  | 0 | 0
|  |  | VAT | 597946.908 |  |  |  |  | 0 | 0
|  |  | Witholding | -224230.0905 |  |  |  |  | 0 | 0
|  |  | Total | 5356607.7175 |  |  |  |  | 0 | 0
| Sub Total | 100% |  | 99657818 |  |  |  | 29897345.4 | 0 | 29897345.4
| VAT |  |  | 11958938.16 |  |  |  | 3587681.448 | 0 | 3587681.448
| Witholding |  |  | -4484601.81 |  |  |  | -1345380.543 | 0 | -1345380.543
| Total |  |  | 107132154.35 |  |  |  | 32139646.305 | 0 | 32139646.305