## Tacoa
TACOA
US Labor | People | $/hr | Hr/Days | Job Length | Total
| 9 | 153.4 | 12 | 85 | 1408212
Mob/Demob |  | 2360 |  |  | 21240
Plane tickets |  | 2950 |  |  | 26550
Housing /meals |  | 236 |  |  | 180540
Transportation |  | 177 |  |  | 135405 |  |  | weekly | less 18% per email | weekly cost for 12 weeks
Sub Total |  |  |  |  | 1771947 | USD |  | 145925.0471 | 119658.5386 | 121083.045
[5 empty] | 1452996.54 | total less 18%
Local Labor | [6 empty] | weekly
Civil - Constech | 20 | 3540 | Weeks | 7 | 495600 |  | 70800
Elec Mech - Inserven | 20 | 4720 | Weeks | 12 | 1132800 |  | 94400 |  |  | weekly cost for 12 weeks
Sub Total |  |  |  |  | 1628400 | BsF | 165200 |  |  | 111274
[5 empty] | 1335288 | total less 18%
Union hourly labor includes all taxes and benefits.
All values and work effort above is related directly to the accelleration schedule requireing night shift coverage.
The Expats above include Mech, Elec, Safety, QA,/QC, controls x 2, civil, supervisor, warehouseman, document control / reporting
Materials?
Summary
|  | Tacoa | La Raisa | Totals
|  | 1771947 | 2508444 | 4280391 | USD
|  | 1628400 | 3292200 | 4920600 | BsF

## La Raisa
La Raisa
US Labor | People | $/hr | Hr/Days | Job Length | Total
| 9 | 153.4 | 12 | 120 | 1988064
Mob/Demob |  | 2360 |  |  | 21240
Plane tickets |  | 2950 | 2 | trips | 53100
Housing /meals |  | 236 |  |  | 254880
Transportation |  | 177 |  |  | 191160 |  |  | weekly | less 18% per email | weekly cost for 12 weeks
Sub Total |  |  |  |  | 2508444 | USD |  | 146325.9 | 119987.238 | 171410.34
[5 empty] | 2056924.08 | total less 18%
Local Labor | [6 empty] | weekly
Civil | 30 | 3540 | week | 7 | 743400 |  | 106200
Elec Mech | 45 | 4720 | week | 12 | 2548800 |  | 212400 |  |  | weekly cost for 12 weeks
Sub Total |  |  |  |  | 3292200 | BsF | 318600 |  |  | 224967
[5 empty] | 2699604 | total less 18%
Union hourly labor includes all taxes and benefits.
All values and work effort above is related directly to the accelleration schedule requireing night shift coverage.
The Expats above include Mech, Elec, Safety, QA,/QC, controls x 2, civil, supervisor, warehouseman, document control / reporting
Materials?