## Tacoa
TACOA
US Labor | People | $/hr | Hr/Days | Job Length | Total
| 10 | 125.788 | 12 | 85 | 1283037.6
Mob/Demob |  | 1935.2 |  |  | 19352
Plane tickets |  | 2419 |  |  | 24190
Housing /meals |  | 193.52 |  |  | 164492
Transportation |  | 145.14 |  |  | 123369 |  |  | weekly | weekly cost for 12 weeks
Sub Total |  |  |  |  | 1614440.6 | USD |  | 132953.9318 | 134536.7167
[5 empty] | 1614440.6 | total less 18% calculated at the hourly rate
Local Labor | [6 empty] | weekly
Civil - Constech | 20 | 2902.8 | Weeks | 7 | 406392 |  | 58056
Elec Mech - Inserven | 20 | 3870.4 | Weeks | 12 | 928896 |  | 77408 |  | weekly cost for 12 weeks
Sub Total |  |  |  |  | 1335288 | BsF | 135464 |  | 111274
[5 empty] | 1335288 | total less 18% calculated at the weekly rate
Union hourly labor includes all taxes and benefits.
All values and work effort above is related directly to the accelleration schedule requireing night shift coverage.
The Expats above include Mech, Elec, Safety, QA,/QC, controls x 2, civil, supervisor, warehouseman, document control / reporting
Materials?
Summary
|  | Tacoa | La Raisa | Totals
|  | 1614440.6 | 2056924.08 | 3671364.68 | USD
|  | 1335288 | 2699604 | 4034892 | BsF

## La Raisa
La Raisa
US Labor | People | $/hr | Hr/Days | Job Length | Total
| 9 | 125.788 | 12 | 120 | 1630212.48
Mob/Demob |  | 1935.2 |  |  | 17416.8
Plane tickets |  | 2419 | 2 | trips | 43542
Housing /meals |  | 193.52 |  |  | 209001.6
Transportation |  | 145.14 |  |  | 156751.2 |  |  | weekly |  | weekly cost for 12 weeks
Sub Total |  |  |  |  | 2056924.08 | USD |  | 119987.238 |  | 171410.34
[5 empty] | 2056924.08 | total less 18% calculated at the hourly rate
Local Labor | [6 empty] | weekly
Civil | 30 | 2902.8 | week | 7 | 609588 |  | 87084
Elec Mech | 45 | 3870.4 | week | 12 | 2090016 |  | 174168 |  |  | weekly cost for 12 weeks
Sub Total |  |  |  |  | 2699604 | BsF | 261252 |  |  | 224967
[5 empty] | 2699604 | total less 18% calculated at the weekly rate
Union hourly labor includes all taxes and benefits.
All values and work effort above is related directly to the accelleration schedule requireing night shift coverage.
The Expats above include Mech, Elec, Safety, QA,/QC, controls x 2, civil, supervisor, warehouseman, document control / reporting
Materials? | [8 empty] | 1935.2
4838
6773.2