## Recap
ProEnergy EPC
Job Description: |  |  | " Cost Estimate for Add'l Liquid Fuel Treatment for add'l LM 6000 PC"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | Guarenas Add'l DFO Fuel Treatment |  |  |  |  | Date: | 2010-06-11
Customer: |  |  | Derwick |  |  |  |  | Quote No: | T 1009 - D
Location: |  |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  |  | 2010-06-12
[10 empty] | US Portion | Bs Portion
I. Balance of Plant | [10 empty] | 8
100 Civil Structural
|  | 101 | Site Preparation |  |  |  | 0 | calc
|  | 102 | Excavation - Fill |  |  | Mhrs | 25.4444 | calc
|  | 103 | Concrete Foundations |  |  | 1249.2593 | 212.3741 | calc
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 175 | calc
|  | 106 | Gravel - Sand |  |  |  | 58.5304 | calc
|  | 107 | Structual Steel |  |  |  | 15 | calc
|  | 108 | Fencing |  |  |  | 0 | calc
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 486.3489 |  | 486.3489 | 97.2698 | 3112.6329
| 200 Buildings | [5 empty] | 206.25 | calc | 206.25 | 206.25
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 939 | calc |  | 939
|  | 320 | Pipe, Valves & Fitting labor |  |  | 7200 |  | calc
|  | 330 | Mechanical Subcontractor |  |  | 2820 | 164.1567 | calc |  | 32.8313 | 1050.6029
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 225 | calc |  | 225
[7 empty] | 1328.1567 |  | 1328.1567
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 82 | calc |  | 82
|  | 420 | Substation Equipment |  |  |  | 0 | calc
|  | 430 | Plant Electrical Subcontractor |  |  | 1060 | 61.7043 | calc |  | 12.3409 | 394.9075
|  | 440 | Substation Subcontractor |  |  | 0 | 0 | calc
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 70 | calc |  | 70
|  | 460 | Conduit, Cable & Wire Labor |  |  | 2400 | 139.7078 | calc |  | 27.9416 | 894.1301
[7 empty] | 353.4121 |  | 353.4121
500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 20 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 400 | 23.2846 | calc
[7 empty] | 43.2846 |  | 43.2846 | 43.2846
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 0 | calc
|  | 620 | Telephone System |  |  |  | 0 | calc
|  | 630 | Public Address System |  |  |  | 0 | calc
|  | 640 | TV / Security |  |  |  | 0 | calc
[7 empty] | 0 |  | 0
700 Plant Erection
|  | 700 | Plant Erection |  |  | 800 | 46.5693 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 14680 | 46.5693 |  | 46.5693 | 9.3139 | 298.0434
| 800 Equipment Rental | [5 empty] | 17.5 | calc | 17.5 |  | 17.5
| 900 Painting | [5 empty] | 15 | calc | 15 |  | 15
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 8.85 | calc |  | 8.85
|  | 1002 | Ocean/Air Freight |  |  |  | 100 | plgd /1000 |  | 100
|  | 1003 | Destination Inland Freight |  |  |  | 75 | plgd /1000 |  |  | 600
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site |  |  |  | 0 | plgd /1000
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 30 | plgd /1000 |  |  | 240
|  | 1007 | Storage |  |  |  | 0 | plgd /1000
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 213.85 |  | 213.85
| 1100 Site Costs | [5 empty] | 0 | calc | 0
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 75 | calc
|  | 1202 | Local Eng |  |  |  | 0 | calc
[7 empty] | 75 |  | 75 | 75
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 0 | calc
|  | 1320 | Inspectors |  |  |  | 0 | calc
[7 empty] | 0 |  | 0
| 1400 Travel & Perdiem | [5 empty] | 0 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 0 |  | 0
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 0 | 2500 | 0 | plgd /1000
|  | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000
|  | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | DFO Treatment |  | 15 | 2200 | 33 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 0 | 2000 | 0 | plgd /1000
|  | 1507 | Controls Rep |  | 0 | 3000 | 0 | plgd /1000
|  | 1508 | Evap Cooler |  | 0 | 2000 | 0 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 33 |  | 33 | 33
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 0 | plgd /1000
|  | 1602 | Concrete |  |  |  | 0 | plgd /1000
|  | 1603 | X Ray |  |  |  | 0 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 0 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 0 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 0 |  | 0
| 1700 Legal | [5 empty] | 0 | plgd /1000 | 0
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 0 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 0 |  | 0
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 200 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 5% | 1336 | 66.8 | calc
|  | 2150 | Labor Contingency |  | 5% | 435.4227 | 21.7711 | calc
[7 empty] | 288.5711 |  | 288.5711 | 288.5711
[5 empty] | BOP Cost |  |  |  | 3106.9428 | 2250.6532 | 6622.8167
[5 empty] | % Markup |  |  | 40% | 1242.7771 | 1242.7771
[5 empty] | BOP Sales Price |  |  |  | 4349.7199 | 3493.4303 | 6622.8167
[5 empty] | Local Municipal & Social |  |  | 7.5% |  |  | 496.7113
[5 empty] | IVA |  |  | 16% |  |  | 1059.6507
[5 empty] | Total BOP Sales Price Incl. Taxes |  |  |  |  | 3493.4303 | 8179.1786
Note The price does include the following:
1.0 Add'l Centrifuge 150 M GPD
2.0 Add'l Raw and Treated DFO Storage Tanks
3.0 Three Bay Unloading Truck Station
4.0 Add'l DFO Treatment Shed Extension
The price does not include the following:
1.0 Duties, Permits, etc.

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [6 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: |  | T 1009 - D
Location: |  | Guatire, Venn | [6 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
7 | O/W Sep and Oil tank |  |  |  | 0 | 20 | 15 | 0 | 0 | 30 | 0
8 | GAS Turbine Hall |  |  |  | 0 | 130 | 1 | 0 | 0 | 18 | 0
9 | Liquid Fuel Under ground tank |  |  |  | 20 | 20 | 1 | 400 | 14.8148 | 30 | 444.4444
10
11 | Main Plant Area |  |  |  | 150 | 150 | 1 | 22500 | 833.3333 | 30 | 25000
12 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
13 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 25.4444

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [7 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [7 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [7 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5 | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy | E=Est
1 | POWER ISLAND | [8 empty] | 850
2 | GT Generators LM 2500+ | [6 empty] | 0 | 0 | 850 | 0 | 0
| GT Generator LM 6000 | [6 empty] | 0 | 0 | 850 | 0 | 0
3 | Exhaust Stack | [6 empty] | 0 | 0 | 850 | 0 | 0
4 | HRSG | [6 empty] | 0 | 0 | 850 | 0 | 0
5 | SCR | [6 empty] | 0 | 0 | 850 | 0 | 0
6 | STG | [6 empty] | 0 | 0 | 850 | 0 | 0
7 | STG Cooling Tower | [6 empty] | 0 | 0 | 850 | 0 | 0
8 | STG Inlet Chillers | [6 empty] | 0 | 0 | 850 | 0 | 0
9 | Gen LO Pump Skid | [6 empty] | 0 | 0 | 850 | 0 | 0
10 | Aux Skid(s) for GTG | [6 empty] | 0 | 0 | 850 | 0 | 0
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  | 0 | 12 | 6 | 1 | 0 | 0 | 850 | 0 | 0
16 | Fuel Gas GTG Meter Skid |  |  | 0 | 18 | 6 | 1 | 0 | 0 | 850 | 0 | 0
17 | Fin Fan L O Coolers |  |  |  | 15 | 15 | 2 | 0 | 0 | 850 | 0 | 0
18 | Gas Compressors |  |  |  | 30 | 15 | 3 | 0 | 0 | 850 | 0 | 0
19 | Fuel Gas Plant Metering Skid |  |  |  | 15 | 8 | 1 | 0 | 0 | 850 | 0 | 0
20 | Comp Fin Fans |  |  |  | 15 | 15 | 1 | 0 | 0 | 850 | 0 | 0
21 | Waste Oil/Water Storage Tank |  |  |  | 30 | 22 | 1 | 0 | 0 | 850 | 0 | 0
22 | Oily Water Separator |  |  |  | 30 | 22 | 0.5 | 0 | 0 | 850 | 0 | 0
23 | Lubricant Storage Area |  |  |  | 45 | 30 | 1 | 0 | 0 | 850 | 0 | 0
24 | Instrument Air Comp Skid |  |  |  | 10 | 8 | 1 | 0 | 0 | 850 | 0 | 0
25 | Pipe Rack Stanchons |  |  |  | 2.5 | 2.5 | 6 | 0 | 0 | 850 | 0 | 0
26 | 15KV Cable Tray Stanchons |  |  |  | 2.5 | 2.5 | 6 | 0 | 0 | 850 | 0 | 0
27 | Fire Water Pump Skid |  |  |  | 15 | 30 | 1 | 0 | 0 | 850 | 0 | 0
28 | Area Light Poles |  |  |  | 2.5 | 3 | 5 | 0 | 0 | 850 | 0 | 0
29 | Aux Trans fndns |  |  |  | 10 | 15 | 1.5 | 0 | 0 | 850 | 0 | 0
30 | Cable Trenches see est |  |  |  | 300 | 15 | 1 | 0 | 0 | 850 | 0 | 0
31 | Water Treatment Plant |  |  |  | 30 | 40 | 0.7 | 0 | 0 | 850 | 0 | 0
32 | Condenser Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
33 | Deaerator Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
34 | BFW Pump Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
35 | DFO Treatment Skid |  |  | 1 | 12 | 8 | 1 | 96 | 3.5556 | 850 | 3022.2222 | 17.7778
36 | Add'l DFO Raw Tank |  |  | 1 | 35 | 35 | 1 | 1225 | 45.3704 | 850 | 38564.8148 | 226.8519
37 | Add'l Treated DFO Tank |  |  | 1 | 25 | 25 | 1 | 625 | 23.1481 | 850 | 19675.9259 | 115.7407
38 | Chemical Injection Skid |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
39 | Raw Water Tank Base |  |  | 0 | 45 | 45 | 1 | 0 | 0 | 850 | 0 | 0
40 | Fire Water Tank base |  |  | 0 | 35 | 20 | 1 | 0 | 0 | 850 | 0 | 0
41 | Emer Generator Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
42
43 | BUILDINGS
44 | Control Bldg/Office |  |  | 0 | 90 | 60 | 0.5 | 0 | 0 | 850 | 0 | 0
45 | Warehouse/Maintenance |  |  | 0 | 90 | 30 | 0.7 | 0 | 0 | 850 | 0 | 0
46 | Water Treatment Bldg |  |  | 0 | 40 | 50 | 0.7 | 0 | 0 | 850 | 0 | 0
47 | Gas Compressor Bldg |  |  | 0 | 60 | 40 | 1 | 0 | 0 | 850 | 0 | 0
48 | DFO Treatment Shed |  |  | 1 | 30 | 20 | 1 | 600 | 22.2222 | 850 | 18888.8889 | 111.1111
49 | Pwr Blk Utility Bldg's |  |  | 0 | 30 | 20 | 1 | 0 | 0 | 850 | 0 | 0
50 | Substation Bldg |  |  | 0 | 15 | 12 | 1 | 0 | 0 | 850 | 0 | 0
51 | Gas Turbine Hall |  |  | 0 | 120 | 50 | 0.7 | 0 | 0 | 850 | 0 | 0
52 | Liquid Fuel Unloading |  |  | 1 | 60 | 70 | 1 | 4200 | 155.5556 | 850 | 132222.2222 | 777.7778
53 | Pump Room(s) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
54 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
55
56 | SUBSTATION
57 | GSU Transformer |  |  |  | 30 | 30 | 3 | 0 | 0 | 850 | 0 | 0
58 | (___)KV SF6 Circuit Breaker |  |  |  | 15 | 15 | 1 | 0 | 0 | 850 | 0 | 0
59 | (___)KV Disc Switch w/ Stand |  |  |  | 10 | 15 | 1 | 0 | 0 | 850 | 0 | 0
60 | Dead End Tower |  |  |  | 15 | 10 | 3 | 0 | 0 | 850 | 0 | 0
61 | Transmission Line Poles |  |  |  | 5 | 5 | 20 | 0 | 0 | 850 | 0 | 0
62 | Insulator Support Base |  |  |  | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
63 | PT Support Base |  |  |  | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
64 | Static Pole Base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 850 | 0 | 0
65
66
67 |  |  | Total Cost of Foundations | [5 empty] | 249.8519 |  | 212.3741 | 1249.2593
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [7 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [7 empty] | Quote No: |  | T 1009 - D
Location: |  | Guatire, Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description | [7 empty] | Cu | Price | Total | Q=Quote
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price | E=Est
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls | [8 empty] | 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [6 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total | Q=Quote
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | E=Est
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0
2 | Gen Removal Areas |  |  | 0 | 20 | 1 | 0 | 0 | 750 | 0
3 | Turbine Removal Areas |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0
4 | Entry Ways |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0
5 | Walk ways |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 750 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 450 | 20 | 0.7 | 6300 | 233.3333 | 750 | 175000
12 | Parking Lot |  |  | 0 | 50 | 0.7 | 0 | 0 | 750 | 0
13 | [6 empty] | 0 | 0 |  | 0
14 | [6 empty] | 0 | 0 |  | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 175
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [7 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [7 empty] | Quote No: |  | T 1009 - D
Location: |  | Guatire, Venn | [7 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price | E=Est
1
2 | Main Plant Area (less substa) |  |  | 1 | 200 | 200 | 0.5 | 20000 | 740.7407 | 1229.6296 | 35 | 43037.037
3
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 35 | 0
5
6 | Substation |  |  | 0 | 400 | 150 | 1 | 0 | 0 | 0 | 35 | 0
7
8 | Road ways |  |  | 1 | 450 | 20 | 0.8 | 7200 | 266.6667 | 442.6667 | 35 | 15493.3333
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | [8 empty] | 58.5304

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [5 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | # of | Qty | Price | Total | Q=Quote
No. | [5 empty] | Lbs / Tons |  |  | Price | E=Est
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 4 | 2500 | 10000
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [5 empty] | 0 | 3500 | 0
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 0 | 15000 | 0
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 0 | 0 | 0
10
11 | Overhead Crane (Bldg) (______) Ton | [5 empty] | 0 | 15000 | 0
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 5000 | 5000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 15

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [5 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [5 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [5 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total | Q=Quote
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price | E=Est
1 | Office/Control/Warehouse |  |  |  | 0 | 60 | 0 | 60 | 0
2 | Water Treatment |  |  |  | 0 | 50 | 0 | 55 | 0
3 | Gas Compr Shed |  |  |  | 0 | 35 | 0 | 55 | 0
4 | DFO Treatment Shed |  |  |  | 20 | 30 | 600 | 55 | 33000
5 | DFO Unloading Shed |  |  |  | 55 | 70 | 3850 | 45 | 173250
6 |  |  |  |  | 0 |  | 0 |  | 0
7 |  |  |  |  | 0 |  | 0 |  | 0
8 |  |  |  |  | 0 | 0 | 0 | 0 | 0
9 |  |  |  |  | 0 | 0 | 0 | 0 | 0
10 |  |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 0 | 15 | 0 | 55 | 0
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 206.25

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [9 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [9 empty] | Quote No: |  | T 1009 - D
Location: |  | Guatire, Venn | [9 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
[15 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
| GTG | [5 empty] | 3% |  | 10
1 | GTG Type 2ea GE LM 2500 + 1ea LM 6000 |  |  |  |  | 0 | 0 | 0 | 10 | 6 | 35 | 0 | 58.2116 | 0 |  | E
2 | Lube oils and Chemicals |  |  |  |  | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
3 | Exhaust Stack |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | Project Grouting |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | GTG Tools |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | Anchor Bolts |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
18 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
30 | Inlet Fogging System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
31 | Inlet Evap Cooling System |  |  | 0 |  | 0 | 0 | 0 | 10 | 4 | 18 | 0 | 58.2116 | 0 |  | E
32 | Inlet Cooling System Cooling Tower |  |  | 0 |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
33 | Cooling Water Circulation Pumps |  |  | 0 |  | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
34 | Chilled Water Pumps |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  | 0 |  | 0 | 0 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
39 | Fuel Gas Check Metering/Regulator Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
40 | Fuel Gas Turbine Metering Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
41 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  | 0 |  | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
42 | ESD Valve, ___" ___# |  |  | 0 |  | 0 | 0 | 0 | 10 | 2 | 1 | 0 | 58.2116 | 0 |  | E
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  | 1 | 30000 | 30000 | 900 | 900 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
46 | Metering Skid |  |  | 1 | 145000 | 145000 | 4350 | 4350 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
47 | Forwarding Pump Skid |  |  | 1 | 25000 | 25000 | 2000 | 2000 | 10 | 3 | 3 | 90 | 58.2116 | 5239.0436 |  | E
48 | Transfer Pump Skid |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
49 | Basket Strainer |  |  | 2 | 15000 | 30000 | 500 | 1000 | 10 | 2 | 3 | 120 | 58.2116 | 6985.3914 |  | E
50 | Filter Skids |  |  | 1 | 59000 | 59000 | 1500 | 1500 | 10 | 3 | 4 | 120 | 58.2116 | 6985.3914 |  | E
51 | Centrifuge |  |  | 1 | 300000 | 300000 | 9000 | 9000 | 10 | 4 | 8 | 320 | 58.2116 | 18627.7104 |  | E
52 | Bag Filter Skid |  |  | 1 | 25000 | 25000 | 2000 | 2000 | 10 | 4 | 4 | 160 | 58.2116 | 9313.8552 |  | E
53 | Raw DFO Add'l Storage Tank |  |  | 1 | 150000 | 150000 | 15000 | 15000 | 10 | 3 | 6 | 180 | 58.2116 | 10478.0871 |  | E
54 | Treated DFO Add'l Storage Tank |  |  | 1 | 150000 | 150000 | 15000 | 15000 | 10 | 4 | 6 | 240 | 58.2116 | 13970.7828 |  | E
55
56 | Water Supply System
57 | Raw/Fire Water Storage Tank 450 M gal |  |  |  |  | 0 | 0 | 0 | 10 | 4 | 6 | 0 | 58.2116 | 0 |  | E
58 | Raw Water Supply Pumps |  |  |  |  | 0 | 0 | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
59 | Raw Water Forwarding Pumps |  |  |  |  | 0 | 0 | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
60
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
64 | Demin Treatment System 115 M gal/day |  |  | 0 | 0 | 0 |  | 0 | 10 | 4 | 8 | 0 | 58.2116 | 0 |  | E
65 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
66 | Demin water fiberglass tank |  |  | 0 | 0 | 0 |  | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
67 | Demin forwarding pumps |  |  | 0 | 0 | 0 |  | 0 | 10 | 3 | 2 | 0 | 58.2116 | 0 |  | E
68 | Demin Filter Skid |  |  | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
69 | Demin Water Tank, SS 200M gal |  |  | 0 | 0 | 0 |  | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  |  |  | 0 |  | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
73 | Oily Waste Tank 10000 gal |  |  |  |  | 0 |  | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
74 | Waste Water Tank 10000 gal |  |  |  |  | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
75 | Waste Oil and Water forwarding pumps w/ skid |  |  |  |  | 0 |  | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
76
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  |  |  | 0 |  | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
79 | Fire Water Foam System |  |  |  |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
80 | [15 empty] | E
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  |  | 0 | 0 | 3000 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
88 | Potable Water System |  |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
89 | Anti-Icing Ducting |  |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
90 | Sanitary Sewer |  |  |  | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
91 | [8 empty] | 10
92
93 |  |  | Total Cost |  |  | 939 |  | 51.5 |  |  |  | 1410
94 | [13 empty] | 82.0783
[9 empty] | Total Manhours |  |  | 1410
[9 empty] | Times Prod Factor |  | 2 | 2820 | 58.2116 | 164.1567
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 225000 | 225000 | 6750 | 6750 | 10 | 6 | 60 | 3600 | 58.2116 | 209561.742 |  | E
96 |  |  | Total Cost |  |  | 225 |  | 6.75 |  |  |  | 3600 |  | 209561.742
97
98 | [8 empty] | Total Manhours |  |  | 3600
99 | [8 empty] | Times Prod Factor |  | 2 | 7200 | 58.2116
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 27
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 9.45
40.45
[8 empty] | Contr G&A 8% |  | 3.236
[8 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[7 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K127: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N119: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [11 empty] | Date: |  | 2010-06-11
Customer: |  | Derwick | [11 empty] | Quote No: |  | T 1009 - D
Location: |  | Guatire, Venn | [11 empty] | Est By: |  | WTS
Bid Due Date: |  | 2010-06-12
[17 empty] | Mat'l | Labor
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | Power Island Equipment | [7 empty] | 3% |  | 10
2 | Gas Turbine Generator LM 2500 & LM 6000 |  |  |  |  | 0 |  |  | 0 |  | 10 | 6 | 35 | 0 | 58.2116 | 0 |  | E
3 | HRSG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
4 | SCR |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
5 | STG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
6 | STG Cooling Tower |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.2116 | 0 |  | E
7 | DFO Treatment Package |  |  |  |  | 1 |  |  | 0 |  | 10 | 4 | 6 | 240 | 58.2116 | 13970.7828 |  | E
8 | Water Treatment Package |  |  |  |  | 0 |  |  | 0 |  | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
9 | [13 empty] | 0 | 58.2116 | 0
10 | 15KV | [13 empty] | 58.2116
11 | Generator Breaker(s) | [7 empty] | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
12 | Distribution Breaker(s) | [7 empty] | 0 | 0 | 10 | 4 | 4 | 0 | 58.2116 | 0 |  | E
13 | Fused Disconnect(s) | [7 empty] | 0 | 0 | 10 | 3 | 3 | 0 | 58.2116 | 0 |  | E
14 | Bus Duct |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.2116 | 0 |  | E
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
17 | 5KV | [13 empty] | 58.2116
18 | Distribution Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
19 | Fused Disconnect(s) |  |  |  |  | 0 |  | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0 |  | E
20 | MCC's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 1 | 0 | 58.2116 | 0 |  | E
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.2116 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0
23 | 600V | [13 empty] | 58.2116
24 | Distribution Panel(s) |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 2 | 5 | 100 | 58.2116 | 5821.1595 |  | E
25 | GTG MCC(s) LM 6000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
| LM 2500 Plus MCCs |  |  |  |  | 0 | 0 | 0 | 0 |  | 10 | 2 | 5 | 0 | 58.2116 | 0
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
27 | STG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0 |  | E
28 | BOP MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
29 | DFO Treatment MCC(s) |  |  |  |  | 1 | 12000 | 12000 | 360 | 360 | 10 | 2 | 2 | 40 | 58.2116 | 2328.4638 |  | E
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 58.2116 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.2116 | 0
32 | Aux Transformer(s) | [13 empty] | 58.2116
33 | 15/5KV ___________ MVA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
34 | 15/600V _500 KVA |  |  |  |  | 1 | 45000 | 45000 | 2500 | 2500 | 10 | 3 | 5 | 150 | 58.2116 | 8731.7393 |  | E
35 | 600/120/208V ________ KVA |  |  |  |  | 0 | 5000 | 0 | 0 | 0 | 10 | 3 | 6 | 0 | 58.2116 | 0 |  | E
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
38 | Area Lighting | [13 empty] | 58.2116
39 | Poles _______ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 1 | 0 | 58.2116 | 0 |  | E
40 | Floodlights _______ Watts |  |  |  |  | 0 | 0 | 0 | 50 | 0 | 10 | 1 | 0.5 | 0 | 58.2116 | 0 |  | E
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 60 | 0 | 58.2116 | 0
43 | Other Systems | [13 empty] | 58.2116
44 | UPS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 3 | 0 | 58.2116 | 0 |  | E
45 | DC |  |  |  |  | 0 | 0 | 0 | 1500 | 0 | 10 | 2 | 4 | 0 | 58.2116 | 0 |  | E
46 | Cathodic Protection |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
47 | Lightning Protection |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.2116 | 0 |  | E
48 | [11 empty] | 0 | 0 | 0 | 58.2116 | 0
49 | [14 empty] | 58.2116
50 | Temporary Electric | [6 empty] | 0 | 0 | 0 | 10 | 2 | 35 | 0 | 58.2116 | 0 |  | E
51 | Electrical Control Module LM 2500+ | [6 empty] | 0 |  | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
52 | Electrical Control Module LM 6000 | [6 empty] | 0 |  | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0
53 | [6 empty] | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.2116 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 82 |  | 3.61 |  |  |  | 530 |  | 30.8521
[12 empty] | Productivity | 2 | 1060 | 58.2116 | 61.7043
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 70000 | 70000 | 2100 | 2100 | 10 | 4 | 30 | 1200 | 58.2116 | 69853.914 |  | E
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 70 |  | 2.1 |  |  |  | 1200 |  | 69.8539
58 | [10 empty] | Total Manhours |  |  | 1200
59 | [10 empty] | Times Prod Factor |  | 2 | 2400 | 58.2116 | 139.7078
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 27
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 9.45
40.45
[13 empty] | Contr G&A 8% |  | 3.236
[13 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[12 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N88: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q80: Insert Rate Here:

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [8 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [8 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [8 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
[13 empty] | Mat'l | Labor
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote | Q=Quote
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est | E=Est
1 | [6 empty] | 10
2 | Instrumentation for GTG |  |  |  |  | 0 | 10 | 2 | 10 | 0 | 58.2116 | 0 |  | E
3 | [6 empty] | 10 |  |  |  | 58.2116 | 0
4 | Instrumentation for SCR |  |  |  |  | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
5 | [6 empty] | 10 |  |  |  | 58.2116
6 | Instrumentation for HRSG |  |  |  |  | 0 | 10 | 4 | 15 | 0 | 58.2116 | 0 |  | E
7 | [6 empty] | 10 |  |  |  | 58.2116
8 | Instrumentation for Injection Water Treatment |  |  |  |  | 0 | 10 | 2 | 8 | 0 | 58.2116 | 0 |  | E
9 | [6 empty] | 10 |  |  |  | 58.2116
10 | Instrumentation for DFO Centrifuges |  |  | 1 | 20000 | 20000 | 10 | 2 | 10 | 200 | 58.2116 | 11642.319 |  | E
11 | [6 empty] | 10 |  |  |  | 58.2116
12 | Instrumentation for gas compressors |  |  | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.2116 | 0 |  | E
13 | [6 empty] | 10 |  |  |  | 58.2116
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 10 | 3 | 5 | 0 | 58.2116 | 0 |  | E
15 | [6 empty] | 10 |  |  |  | 58.2116
16 | [6 empty] | 10 |  |  |  | 58.2116
17 | [6 empty] | 10 |  |  |  | 58.2116
18 | [6 empty] | 10 |  |  |  | 58.2116
19 | [6 empty] | 10 |  |  |  | 58.2116
20 | [6 empty] | 10 |  |  |  | 58.2116
21 | [6 empty] | 10 |  |  |  | 58.2116
22 | [6 empty] | 10 |  |  |  | 58.2116
23 |  |  | Total Cost of Plant Instrumentation |  |  | 20 |  |  |  | 200 |  | 11.6423
[8 empty] | Total Hours |  | 200
[8 empty] | Prod Factor | 2 | 400 | 58.2116 | 23.2846
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 27
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 9.45
40.45
[9 empty] | Contr G&A 8% |  | 3.236
[9 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[8 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [6 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total | Q=Quote
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor | E=Est
1 |  |  |  |  | 10
2 | GTG Erection |  |  |  | 10 | 12 | 30 | 0 | 58.2116 | 0 | E
3 |  |  |  |  | 10 |  |  |  | 58.2116
4 | HRSG Erection |  |  |  | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
5 |  |  |  |  | 10 |  |  |  | 58.2116
6 | SCR Erection |  |  |  | 10 | 10 | 60 | 0 | 58.2116 | 0 | E
7 |  |  |  |  | 10 |  |  |  | 58.2116
8 | Water Treatment and FW Systems |  |  |  | 10 | 4 | 8 | 0 | 58.2116 | 0 | E
9 |  |  |  |  | 10 |  |  |  | 58.2116
10 | DFO Treatment System |  |  | 1 | 10 | 4 | 10 | 400 | 58.2116 | 23284.638 | E
11 |  |  |  |  | 10 |  |  |  | 58.2116
12 | BOP Equip Erection |  |  |  | 10 | 6 | 10 | 0 | 58.2116 | 0 | E
13 |  |  |  |  | 10 |  |  |  | 58.2116
14 | Gas Compressor Erection |  |  |  | 10 | 6 | 5 | 0 | 58.2116 | 0 | E
15 |  |  |  |  | 10 |  |  |  | 58.2116
16 | Evap Cooling Erection |  |  |  | 10 | 4 | 4 | 0 | 58.2116 | 0 | E
17 |  |  |  |  | 10 |  |  |  | 58.2116
18 | Fire Water Pump Skid |  |  |  | 10 | 4 | 3 | 0 | 58.2116 | 0 | E
19 |  |  |  |  | 10 |  |  |  | 58.2116
20 | STG Erection |  |  |  | 10 | 12 | 36 | 0 | 58.2116 | 0 | E
21 |  |  |  |  | 10 |  |  |  | 58.2116
22 | STG Cooling Tower |  |  | 0 | 10 | 8 | 8 | 0 | 58.2116 | 0 | E
23 |  |  |  |  | 10 |  |  |  | 58.2116
24 |  |  |  |  | 10 |  |  |  | 58.2116
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 400 |  | 23.2846
[6 empty] | Total Hours |  | 400
[6 empty] | Prod Factor | 2 | 800 | 58.2116 | 46.5693
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 27
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 9.45
40.45
[7 empty] | Contr G&A 8% |  | 3.236
[7 empty] | Contr Mark up 15% |  | 6.0675
49.7535
[6 empty] | 60 | Hour Work Week = |  | 58.2116
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | Guarenas Add'l DFO Fuel Treatment | [6 empty] | Date: | 2010-06-11
Customer: |  | Derwick | [6 empty] | Quote No: | T 1009 - D
Location: |  | Guatire, Venn | [6 empty] | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total | Q=Quote
No. | [5 empty] | Units | Unit | Days | Per Day | Cost | E=Est
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator | [6 empty] | 0 | 10000 | 0
3 | 1 ea 150 Ton Crane w/ operator | [6 empty] | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator | [6 empty] | 0 | 2000 | 0
5 | 1 ea 20 Ton Crane w/ operator | [6 empty] | 0 | 3800 | 0
6 | 2 ea Sky Tracs | [6 empty] | 0 | 70 | 0
7 | 2 ea Fork Lifts | [6 empty] | 0 | 100 | 0
8 | 1 ea Man Lift | [6 empty] | 0 | 80 | 0
9 | 2 ea Welders | [6 empty] | 0 | 60 | 0
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | STG Cooling Tower
38 | 150 Ton Crane |  |  |  |  | 0 | 0 | 0 | 3000 | 0
39 | 40 Ton Crane |  |  |  |  | 0 | 0 | 0 | 1500 | 0
40 | 2ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 5 | 5 | 3500 | 17500
51 | 2 ea Fork Lifts |  |  |  |  | 0 |  | 0 | 70 | 0
52 | Welders |  |  |  |  | 0 |  | 0 | 70 | 0
53 | 2 ea Pick ups |  |  |  |  | 0 |  | 0 | 30 | 0
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 0 | 0 | 0 | 70 | 0
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator | [6 empty] | 0 | 4000 | 0
58 | 1 ea 100 Ton Crane w/ operator | [6 empty] | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator | [6 empty] | 0 | 1500 | 0
60 | 2 ea Man Lifts | [6 empty] | 0 | 80 | 0
61 | 2 ea Sky Tracs | [6 empty] | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 5 |  | 17.5

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | Guarenas Add'l DFO Fuel Treatment |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - D
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Paint for GTG | [5 empty] | 45000 | 0 | E
3
4 | Paint for STG and Auxiliaries | [5 empty] | 60000 | 0 | E
5
6 | Paint for SCR w/ Pipe Racks | [5 empty] | 135000 | 0 | E
7
8 | Paint for Pipe Rack etc. | [5 empty] | 40000 | 0 | E
9
10 | Paint for BOP Equipment | [5 empty] | 50000 | 0 | E
11
12 | Paint for Gas Compressor | [5 empty] | 15000 | 0 | E
13
14 | Paint for Water Treatment | [5 empty] | 15000 | 0 | E
15
16 | Paint for DFO Treatment |  |  |  |  | 1 | 15000 | 15000 | E
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0 | E
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 15

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | Guarenas Add'l DFO Fuel Treatment |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - D
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Transportation of Plant Major Mechanical Equip | [5 empty] | 51.5 | 0 | E
3
4 | Transportation of Plant Major Electrical Equip | [5 empty] | 3.61 | 0 | E
5
6 | Transportation Substation Equip |  |  |  |  | 0 | 0 | 0 | E
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 6.75 | 6.75 | E
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 2.1 | 2.1 | E
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 8.85

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | Guarenas Add'l DFO Fuel Treatment |  |  |  |  | Date: | 2010-06-11
Customer: |  | Derwick |  |  |  |  | Quote No: | T 1009 - D
Location: |  | Guatire, Venn |  |  |  |  | Est By: | WTS
Bid Due Date: |  | 2010-06-12
Item |  | Description |  |  |  | Qty | Unit | Total | Q=Quote
No. | [5 empty] | Units | Cost | Cost | E=Est
1
2 | Conceptual Engineering WGPS | [6 empty] | 0 | E
3
4 | Detailed Engineering per GTG | [6 empty] | 0
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering for DFO Treatment |  |  |  |  | 1 | 25000 | 25000
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 0 | 0 | 0
13
14 | Detailed Engineering for civil/structural/bldg |  |  |  |  | 0 | 0 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 25