Draft 2/9/09

DISMANTLING SERVICES AGREEMENT

This Dismantling Services Agreement ("Agreement") is made this __ day of __________, 2009, by and between AP HOLDINGS SOUTHAVEN, LLC ("Owner"), and PROENERGY EPC SERVICES, LLC ("Contractor").

1. WORK.  Contractor shall provide all labor, equipment, vehicles, tools and materials to dismantle two (2) GE Frame 7EA gas turbines and related balance of plant equipment as more fully described in Exhibit A (the "Equipment"), package the Equipment for shipment and load the Equipment onto the equipment of the carrier as directed by Owner or its customer at the site of Owner's facility in Southaven, Mississippi (the "Site"), such services by Contractor, the "Work". Contractor shall perform the Work in accordance with the schedule ("Project Schedule") to be prepared by Contractor and approved by Owner, and as it may change from time to time as agreed by Owner, and shall complete the Work within sixty (60) days of the date of this Agreement (the "Deadline"). The Work shall not be complete until the Equipment has been fully loaded onto the carrier's equipment. Contractor shall give timely notices to governmental authorities pertaining to Work and shall be responsible for all permits, fees, licenses, assessments, inspections, testing and taxes necessary to complete the Work.

2. CONDITION OF THE SITE.  As part of the Work, Contractor shall remove all above ground objects that remain on the portions of the Site from which the Equipment is removed, cover all holes and otherwise leave such portions of the Site in a clean and safe condition, at a minimum, in the same condition in which other portions of the Site from which other turbines and related equipment have been removed have been left. The Work shall be performed in accordance with all applicable laws. During the performance of the Work, Contractor shall keep the Site clean and free from accumulations of waste materials, rubbish and other debris resulting from the Work.  Contractor shall not bring any hazardous substances on to the Site unless such substances are necessary for the performance of the Work and without having obtained Owner's prior written consent, and Contractor shall transport, handle, store and dispose of any hazardous substances that Owner consents to be brought on to the Site in accordance with all applicable laws. Prior to completion of the Work, Contractor will remove the waste materials, rubbish, Contractor’s tools and equipment and other items used for the Work from the Site. If Contractor has failed to complete its obligations under this Section 2 within five (5) days following completion of the Work, then Owner may carry out the activities needed to comply with this Section 2 itself or through other contractors, and Contractor shall be liable for the cost of such work.

3. CONTRACT AMOUNT.  Owner agrees to pay Contractor, for satisfactory and timely performance and completion of the Work, the amount set forth in Exhibit B (the "Contract Amount").

4. INSURANCE; HOLD HARMLESS AGREEMENT.  Contractor shall purchase and maintain insurance that will protect Owner from claims arising out of Contractor's performance of the Work, whether the operations are by Contractor, or any of Contractor's consultants or subcontractors or anyone directly or indirectly employed by any of them, or by anyone for whose acts any of them may be liable. Contractor shall maintain coverage and limits of liability as set forth in Exhibit C. In the event Contractor uses any consultants or subcontractors for the performance of the Work on or at the Facility, such consultant or subcontractor shall be required to maintain insurance as set forth in Exhibit C and shall be required to execute the Hold Harmless Agreement appended as Exhibit D.

5. EXHIBITS.  In the event of a conflict between the terms of this Agreement and any of the Exhibits or any other document, the terms of this Agreement shall prevail.

6. SAFETY.  To protect persons and property, Contractor shall establish a safety program implementing safety measures, policies and standards conforming to (a) those required or recommended by governmental authorities having jurisdiction over the Work, (b) good industry practices and (c) the requirements of this Agreement.

7. ASSIGNMENT.  Contractor shall not assign or subcontract the whole or any part of Work or this Agreement without prior written approval of Owner, which consent shall not be unreasonably withheld.

8. TIME.

8.1 TIME IS OF THE ESSENCE.  Time is of the essence of this Agreement. Contractor shall perform the Work so that it may be completed in accordance with this Agreement. In the event that Contractor does not complete the Work by the Deadline, except due to an event of force majeure, Owner shall have the right to assess liquidated damages, as its sole remedy, in the amount of $10,000 per day for each day thereafter that Contractor has not completed the Work, for the first thirty (30) days, and $25,000 per day thereafter.  Contractor shall not be responsible for the payment of liquidated damages in cases where (i) Contractor is delayed in completing the Work due to a Force Majeure Event (as defined below), (ii) Contractor has dismantled the Equipment and is ready to commence transporting it as soon as Owner has received full payment of the purchase price for the Equipment from its customer, and (iii) Contractor has dismantled and transported the Equipment and completed the Work other than minor cleanup or punchlist items to be completed at the Site which shall in any event be completed within thirty (30) days following the Deadline.

8.2 PROJECT SCHEDULE.  In consultation with Owner, and subject to Owner's approval, Contractor shall prepare the Project Schedule for performance of the Work and shall revise and update the Project Schedule, as necessary, and as agreed by Owner, as Contractor's work progresses. Owner shall have the right to determine and, if necessary, change the time, order and priority in which various portions of Work shall be performed and all other matters relative to Work, including performing portions of the Work itself provided such changes requested by Owner do not impact the cost or schedule for Contractor's performance of the Work unless otherwise agreed by Contractor.

8.3  FORCE MAJEURE.	Contractor shall not be responsible or liable for delays in performance of its obligations under this Agreement due to any cause beyond its reasonable control including, but not limited to, explosions, fires, nuclear radiation, contamination, hurricanes, earthquakes, floods, natural disasters, epidemics, other acts of God, and any other similar circumstances; war and other hostilities (whether declared or not), revolution, public disorders, insurrection, rebellion, sabotage, acts of public officials or terrorist action; failure of any third party supplier of goods or services, any action taken by any government authority; labor disputes; and equipment failure, provided, however, that none of the circumstances above shall be considered to be a Force Majeure Event to the extent such circumstance is due to the act, neglect, omission, breach of contract or of statutory duty, negligence or misconduct of Contractor or it personnel or subcontractors (a “Force Majeure Event”).  Contractor shall notify Owner as soon as reasonably practicable of the delay.  The date for completing any delayed performance shall be extended for a period of time equal to the period of time lost by the delay plus such additional time necessary to overcome the effect of such delay.

9. CHANGE ORDERS.  When Owner orders in writing, Contractor, without nullifying this Agreement, shall make any and all changes in Work, which are within the general scope of this Agreement provided such changes requested by Owner do not impact the cost or schedule for Contractor's performance of the Work unless otherwise agreed by Contractor. Any adjustment in the Contract Amount or time of performance shall be authorized by a Change Order. No adjustments shall be made for any changes performed by Contractor that have not been ordered by Owner. A Change Order is a written instrument prepared by Owner and signed by Contractor stating their agreement upon the change in Work. If commencement and/or progress of Work is delayed without the fault or responsibility of Contractor, the time for Work shall be extended by Change Order to the extent obtained by Contractor, and the Project Schedule shall be revised accordingly.

10. PAYMENT.  Payment of the Contract Amount shall be made by Owner to Contractor's account by wire transfer as instructed by Contractor. Payment shall be made to Contractor within two business days after Owner's receipt of full payment from its customer for the Equipment. Payment shall not be due to Contractor unless and until such payment is received from Owner's customer. Payment is subject to receipt of such unconditional Lien releases, waivers, affidavits, or other documentation executed by Contractor and its subcontractors and vendors reasonably requested by Owner to evidence full payment by Contractor to its subcontractors and vendors.

11. LIENS.

11.1	NO LIENS OF CONTRACTOR. Contractor shall promptly pay its subcontractors and vendors used for the performance of the Work.  Contractor shall keep the Site and the Equipment free and clear from all liens, encumbrances, security interests, or claims of any type (whether for breach of contract, pursuant to law or otherwise), including without limitation, all mechanic's or materialmen's liens, for labor, material, equipment or services furnished under this Agreement ("Liens") created by or through Contractor or its   personnel, subcontractors or vendors. Contractor shall promptly notify Owner of any Lien filed against the Site or the Equipment by any of its personnel, subcontractors or vendors as soon as such Liens become known to Contractor.  Contractor shall indemnify, defend and hold harmless Owner from any Lien placed against Owner's property by any of its personnel, subcontractors or vendors; provided that such Lien is not the result of Owner's breach of its payment obligations under this Agreement.

11.2	DISCHARGE OR BOND.  No later than 10 days after Contractor is notified by Owner or becomes aware of a Lien filed against the Site or the Equipment by any of Contractor's personnel, subcontractors or vendors, and provided that such Lien is not the result of Owner's breach of its payment obligations under this Agreement, Contractor shall cause such Lien to be discharged or shall provide such bond or other security as is required to cause the Lien to be released.  If Contractor fails to discharge or promptly bond any such Lien, in addition to any other rights of Owner under this agreement, Owner shall have the right to take reasonable actions and steps to satisfy, defend, settle or otherwise remove the Lien at Contractor's expense, including reasonable attorneys' fees, costs and expenses.  Owner shall have the right to deduct any such fees, costs and expenses from the Contract Amount.

12. INDEMNITY.   Contractor covenants and agrees to fully defend, protect, indemnify and hold harmless Owner and its affiliates, employees, officers, directors, agents and representatives (“Owner Group”) from and against each and every claim, demand, suit, or cause of action, and any judgment, settlement, liability, cost, expense (including, but not limited to reasonable attorney’s fees and expenses incurred in defense of a member of Owner Group), damage or loss in connection therewith, whether arising in equity, at common law, or by statute, or under the law of contracts, torts (including, without limitation, negligence and strict liability without regard to fault) or property, of every kind and character, (including, without limitation, for personal injury (including death and emotional distress), real or personal property damage, and economic loss), which may be (i) made or asserted at any time by any person or entity (including Contractor’s employees, agents, subcontractors or its carrier), based upon, in connection with, relating to or arising out of the Work or (ii) arising out of or relating to damage caused to the Facility during the Work, except to the extent due to the negligence or other fault, breach of contract or warranty, or strict liability without regard to fault of Owner Group.

13. CONFIDENTIALITY. Owner and Contractor each agree that it will not, at any time prior to or after the termination or expiration of, or closing under, this Agreement, make any disclosure of any of the terms of this Agreement to any person or party that is not a signatory of this Agreement except (i) in performing its obligations hereunder or (ii) to any of its parent entities or to its or its parent entities' directors, officers,  employees or representatives strictly on a “need to know” basis.

14. DISPUTES.  If a dispute arises out of or relates to this Agreement, the parties shall endeavor to settle the dispute through direct discussion, and if the parties are unable to resolve such dispute within thirty (30) days of commencing such discussions, either party may enforce its rights in an appropriate state or federal court.

15. NOTICES. All notices, requests, demands, claims, and other communications hereunder shall be in writing and delivered by hand, messenger, reputable overnight private courier service, or facsimile, and shall be deemed delivered upon actual receipt by the addressee to the following addresses, or such other address as the receiving party may have specified by notice to the notifying party:

If to Contractor, to:

ProEnergy EPC Services, LLC

2031 Adams Road

Sedalia, Missouri 65301

Attn: Jeff Canon

Telephone: (660) 829-5100

Facsimile: (660) 829-1160

If to Owner, to:

AP Holdings Southaven, LLC

c/o BTEC Turbines LP

16730 Jacintoport Blvd.

Houston, Texas  77015

Attention: Phiroz M. Boyce

Telephone: (281) 864-9122

Facsimile: (281) 864-9562

With a copy to:

Nancy A. Wodka

Bracewell & Giuliani LLP

2000 K Street, N.W. Suite 500

Washington, D.C. 20006

Telephone: (202) 828-5862

Facsimile: (202) 857-2132

Any party may change the address to which notices, requests, demands, claims, and other communications hereunder are to be delivered by giving the other party notice in the manner herein set forth

16.  MISCELLANEOUS.

16.1 ENTIRE AGREEMENT. This Agreement contains the complete agreement between the parties and may be modified only by a separate written agreement mutually agreed and signed by both parties.

16.2 GOVERNING LAW. This Agreement shall be governed by, construed and enforced in accordance with the laws of the State of Texas, but without regard to any conflict of laws provisions of that State which would 	have the effect of applying the law of another state or jurisdiction.

16.3 NO CONSEQUENTIAL OR PUNITIVE DAMAGES. Neither Contractor nor Owner nor any of their respective affiliates, employees, officers, directors, agents or representatives shall be liable to the other for consequential, incidental, punitive, exemplary or indirect damages, lost profits or other business interruption damages, whether by statute, in tort or contract or otherwise in respect of this Agreement or otherwise in connection with this transaction.

16.4 SEVERABILITY. The invalidity, illegality or unenforceability of any provision of this Agreement, or the occurrence of any event rendering any portion or provision of this Agreement void, shall in no way affect the 	validity or enforceability of any other portion or provision of this Agreement.  If any provision of this Agreement is invalid, illegal or unenforceable in any jurisdiction, the provision will be fully severable from this Agreement and the other provisions of this Agreement will remain in full force and effect in the jurisdiction and the remaining provisions of this Agreement will be liberally construed to carry out the provisions and intent of this Agreement.  The parties further agree to reform this Agreement to replace any stricken provision with a valid provision that comes as close as possible to the intent of the stricken provision.

16.5  HEADINGS.   The section headings contained in this Agreement are inserted for convenience only and 	shall not affect in any way the meaning or interpretation of this Agreement.

16.5	Successors and Assigns. This Agreement may not be assigned by either party without the written consent of the other party, which consent shall not be unreasonably withheld. This Agreement shall be binding upon the parties and their respective successors and permitted assigns.

16.6 AMENDMENTS AND WAIVERS.  This Agreement may not be modified or amended except by an instrument in writing signed by authorized representatives of the parties. No delay or failure to exercise a right resulting from a breach of this Agreement shall impair such right or shall be construed to be a waiver thereof, but such right may be exercised from time to time and as often as may be deemed expedient.

16.7  LIMITED RECOURSE. No judgment, order or execution entered in any lawsuit, action or proceeding in favor of a party, whether legal or equitable, under this Agreement shall be obtained or enforced against any party's affiliates, officers or directors for the purpose of obtaining satisfaction of any obligation arising under this Agreement, and any right to so proceed is hereby expressly waived, renounced and remitted by each respective party for itself and for its successors and assigns.

16.8  COUNTERPARTS.  This Agreement may be signed in any number of counterparts, each of which will be deemed an original, but all of which together will constitute one and the same document.  A facsimile 	transmission of a party’s signature on such signature page will be deemed an original and will bind that party.

The parties, by executing below, hereby enter into this Agreement as of the date first set forth above.

Owner:  AP HOLDINGS SOUTHAVEN LLC

BY: _________________________________

NAME: ________________________________

TITLE _________________________________

Contractor:  PROENERGY EPC SERVICES, LLC

BY: _________________________________

NAME: ________________________________

TITLE _________________________________

EXHIBIT A

EQUIPMENT

Gas Turbine Package #1 Serial No. 297631 				Quantity

Accessory/Starter Skid 						1

Turbine Skid 								1

Generator								1

Gas Turbine Package #2 Serial No. 297632

Accessory/Starter Skid 						1

Turbine Skid 								1

Generator 								1

BOP Equipment

Generator Air Filter 							2

Generator Auxiliary Compartment (GAC) 				2

Turbine Inlet Air Filter 						2

Inlet Fogging System 							2

Air Processing Unit 							2

Lube Oil Demister 							2

Fuel Gas Module 							2

Packaged Electrical & Electronic Control Center (PEECC) 		2

- Generator Control System

- 480V Motor Controls

- 125V DC Battery System

- Mark VI Turbine Control System

Exhaust Stack 								2

Exhaust Frame Blowers 						4

Fuel Gas Electric Heater 						2

Fuel Gas Scrubber 							2

Cooling Water Module 						2

CO2 Fire Protection Unit 						1 		1 per 2 CTGs

Constant Emissions Monitoring System 				2

Power Distribution Center (PDC) 					1 		1 per 2 CTGs

Auxiliary Transformers 						2

- 13.8kV to 4160V 						1 		1 per 2 CTGs

- 13.8kV to 480V 						1 		1 per 2 CTGs

Generator Step Up Transformer 					1

Switchyard Equipment 						1 		1 per 2 CTGs

Above ground piping (>3") and pipe racks 				1

Above ground cable trays and racks (not embedded in concrete) 	1

EXHIBIT B

CONTRACT AMOUNT

Nine hundred thousand dollars ($900,000).

EXHIBIT C

INSURANCE REQUIREMENTS

Contractor shall procure and at all times during the Work maintain with insurers reasonably acceptable to Owner the following insurance protecting Owner against liability from damages because of injuries, including death suffered by persons, including employees of Contractor, and from damages to the Equipment, the Facility or Owner’s other property arising from or resulting out of Contractor’s presence at the Facility, including actions of its agents or subcontractors. Contractor shall (1) include Owner and its affiliate, BTEC Turbines LP as an additional insured on all insurance policies, except Workers’ Compensation Insurance and (2), obtain waiver of subrogation endorsements on all liability insurance policies for the benefit of Owner and BTEC Turbines LP.

- General Liability – Occurrence Form, with limits of $2,000,000 per occurrence, $2,000,000 Products-completed Operations Aggregate, $2,000,000 General Aggregate, $2,000,000 Personal & Advertising Injury limit, $50,000 Fire Damage Limit (any one fire) and $10,000 Premises Medical Payment.

- Worker’s Compensation with statutory limits.

- Employer’s Liability with limits of $1,000,000 Each Accident., $1,000,000 Each Employee – Disease, and $1,000,000 Each Disease – Policy Limit.

(d) 	Automobile Liability with limits of $1,000,000 combined single limit.

(e)	Excess (or Umbrella) Liability coverage with limits of no less than $20,000,000 in excess of the underlying limits stated above.

All insurance required to be maintained by Contractor shall be primary to any insurance carried by Owner that might apply on the same basis. Contractor shall be required to furnish Owner with a certificate of insurance evidencing the coverages set forth in this Exhibit C prior to being allowed to bring its personnel, agents or subcontractors to the Facility. Nothing contained in this Exhibit C shall be construed as a limitation of the liability of Contractor for damage or injury, including death, which arises out of Contractor's performance of the Work or other activities at the Facility.

EXHIBIT D

FORM OF

HOLD HARMLESS AND INDEMNIFICATION AGREEMENT

This Hold Harmless and Indemnification Agreement, referred to as the Agreement, is executed by ______________ ("Company"), as the indemnitor, in favor of AP Holdings Southaven, LLC ("Owner"), as the indemnitee, on this ___ day of _________, 200_.

Company has been employed by or on behalf of ____________________________ ("Contractor") to perform work that will take place on the premises of Owner's facility located in Southaven, Mississippi ("Owner Premises"). As a condition to the performance of such work on the Owner Premises, Owner requires that Company execute this Agreement. Therefore, it is agreed between Owner and Company as follows:

Company covenants and agrees to fully defend, protect, indemnify and hold harmless Owner and its affiliates, employees, officers, directors, agents and representatives (“Owner Group”) from and against each and every claim, demand, suit, or cause of action, and any judgment, settlement, liability, cost, expense (including, but not limited to reasonable attorney’s fees and expenses incurred in defense of a member of Owner Group), damage or loss in connection therewith, whether arising in equity, at common law, or by statute, or under the law of contracts, torts (including, without limitation, negligence and strict liability without regard to fault) or property, of every kind and character, (including, without limitation, for personal injury (including death and emotional distress), real or personal property damage, and economic loss), which may be (i) made or asserted at any time by any person or entity (including Company’s employees, agents, subcontractors or its carrier), based upon, in connection with, relating to or arising out of the Company's work or (ii) arising out of or relating to damage caused to the Owner Premises during the performance of the Company's work, except to the extent due to the negligence or other fault, breach of contract or warranty, or strict liability without regard to fault of Owner Group.

Company represents to Owner that it has the following minimum insurance coverages:

(a)	General Liability – Occurrence Form, with limits of $2,000,000 per occurrence, $2,000,000 Products-completed Operations Aggregate, $2,000,000 General Aggregate, $2,000,000 Personal & Advertising Injury limit, $50,000 Fire Damage Limit (any one fire) and $10,000 Premises Medical Payment

(b)	Worker’s Compensation with statutory limits.

(c)      Employer’s Liability with limits of $1,000,000 Each Accident., $1,000,000 Each Employee – Disease, and $1,000,000 Each Disease – Policy Limit.

- Automobile Liability with limits of $1,000,000 combined single limit.

- Excess (or Umbrella) Liability coverage with limits of no less than $20,000,000 in excess of the underlying limits stated above

Company shall name Owner as an additional insured (except in the case of Worker's Compensation/Employer's Liability Insurance) and each policy shall provide a waiver of subrogation in favor of Owner to the extent of the obligations assumed by the Company under this Agreement and afford full contractual liability sufficient to cover Company's indemnity obligations under this Agreement.

Company represents and warrants to Owner that it has full right, power and authority to execute this Agreement.

This Agreement shall be governed by the laws of the State of Texas, without reference to its principles of conflicts of laws.

IN WITNESS WHEREOF, the Parties have executed this Agreement on the date first written above.

AP Holdings Southaven, LLC				[Company]

By:								By:

Its:								Its: