## Summary
Item | Total
Labor | 717007.668
T&L Expenses | 123200
Equipment | 92000
Office / Consumables | 23469.2
Manuals / Commissioning Procedures | 35000
Materials | 3216895
Misc & Contingency - 5% | 210378.5934
Total Estimated Installation Costs | 4417950.4614 | 0
NOT Included;
no SMEC & SOTR
no tanks
no import duties
no drainage / ground works
no performance test
Included;
assuming we provide air & oil filters
assuming we supply first fill of oils

## Expenses
T&L Expense | Unit Cost | Quantity | People | Total Costs | Materials
Airfare | 2500 | 4 | 2 | 20000 | Oil CTG | 32000
Hotel | 175 | 45 | 8 | 63000 | Oil GTG | 30000
Meals Variable Daily Cost | 45 | 45 | 8 | 16200 | Oil Hydraulic | 6000
Visa/Passport/CAC/ Medical/ Drug | 700 | 1 | 8 | 5600 | Filters GTG Air house | 50000
US Departure Processing | 500 | 1 | 8 | 4000 | Filters Oil, hydraulic, etc. | 35000
Rental Car | 80 | 45 | 4 | 14400
Subtotal |  |  |  | 123200 | Pipe x 2 - oil & gas | 300000
[5 empty] | Conex x 6 (est. 15k per) | 90000
Office / Consumables | Item Cost | Unit | Quantity | Total Cost | Sttructural Steel / Steel plate | 600000
Rent | 2400 | month | 0 | 0 | Electrical Misc | 600000
Supplies | 10000 | each | 1 | 10000 | Grounding Grid | 150000
Long Distance Phone Service | 4000 | month | 1 | 4000 | Disconnects HV, LV, Cable | 600000
Furniture | 1000 | person | 1 | 1000 | Cable Tray | 50000
Computers - Laptops | 2658 | each | 1 | 2658
Printer | 500 | each | 1 | 500
Copier | 750 | month | 1 | 750 | Sub Total - Materials | 2543000
Petty Cash | 500 | month | 3 | 1500
sub total |  |  |  | 20408 | Shipping | 254300 | 10%
Mark Up percentage |  |  | 15% | 3061.2 | Mark Up | 419595 | 15%
Total Office / Consumables |  |  |  | 23469.2
[5 empty] | Total | 3216895
Equipment
Lube Oil flush kit |  |  |  | 10000
Crane |  |  |  | 50000
Forklift |  |  |  | 14000
Truck |  |  |  | 18000
Total - Equipment |  |  |  | 92000

## Rate Sheet
| Position | Rate/hr
| Installation Manager | 121.8075
| Lead Electrical | 89.3255
| Electrical Start up Engineer | 77.9568
| Lead Mechanical | 89.3255
| Mechanical Startup Engineer | 77.9568
| Lead I&C | 89.3255
| I&C Start Up Engineer | 77.9568
| Planner/Scheduler | 113.687
* | Electrician | 56.8435
* | Millwright/Mechanic | 48.723
* | Welder/Fitter | 48.723
* | I&C Technicians | 56.8435
| DCS Engineer | 121.8075
| EH&S Field Engineer | 81.205
| TA's Controls & Mechanical | 150
| Civil Craft | 68.2122
* positions receiving overtime pay when applicable

## Labor Cost
Position | QTY | Pay Rate | FICA | FUTA | SUTA | Medicare | G&L Ins | WC Ins | Other | Markup | Labor | Labor | Hours | Weeks | Cost | Billing | Margin
|  | Per Hour | 7.65% | 0.8% | 3.51% | 1.45% | 7% | 7% | 35% |  | Cost | Bill Rate | Week
Installation Manager | 2 | 75 | 5.7375 | 0.6 | 2.6325 | 1.0875 | 5.25 | 5.25 | 26.25 | 1.6241 | 95.5575 | 121.8075 | 65 | 6 | 74534.85 | 95009.85
Lead Electrical | 2 | 55 | 4.2075 | 0.44 | 1.9305 | 0.7975 | 3.85 | 3.85 | 19.25 | 1.6241 | 70.0755 | 89.3255 | 65 | 6 | 54658.89 | 69673.89
Electrical Start up Engineer |  | 48 | 3.672 | 0.384 | 1.6848 | 0.696 | 3.36 | 3.36 | 16.8 | 1.6241 | 61.1568 | 77.9568 | 65 | 6 | 0 | 0
Lead Mechanical | 2 | 55 | 4.2075 | 0.44 | 1.9305 | 0.7975 | 3.85 | 3.85 | 19.25 | 1.6241 | 70.0755 | 89.3255 | 65 | 6 | 54658.89 | 69673.89
Mechanical Startup Engineer |  | 48 | 3.672 | 0.384 | 1.6848 | 0.696 | 3.36 | 3.36 | 16.8 | 1.6241 | 61.1568 | 77.9568 | 65 | 6 | 0 | 0
Lead I&C |  | 55 | 4.2075 | 0.44 | 1.9305 | 0.7975 | 3.85 | 3.85 | 19.25 | 1.6241 | 70.0755 | 89.3255 | 65 | 6 | 0 | 0
I&C Start Up Engineer |  | 48 | 3.672 | 0.384 | 1.6848 | 0.696 | 3.36 | 3.36 | 16.8 | 1.6241 | 61.1568 | 77.9568 | 65 | 6 | 0 | 0
Planner/Scheduler |  | 70 | 5.355 | 0.56 | 2.457 | 1.015 | 4.9 | 4.9 | 24.5 | 1.6241 | 89.187 | 113.687 | 65 | 6 | 0 | 0
Electrician | 4 | 35 | 2.6775 | 0.28 | 1.2285 | 0.5075 | 2.45 | 2.45 | 12.25 | 1.6241 | 44.5935 | 56.8435 | 65 | 6 | 69565.86 | 88675.86
Millwright/Mechanic | 4 | 30 | 2.295 | 0.24 | 1.053 | 0.435 | 2.1 | 2.1 | 10.5 | 1.6241 | 38.223 | 48.723 | 65 | 6 | 59627.88 | 76007.88
Welder/Fitter | 6 | 30 | 2.295 | 0.24 | 1.053 | 0.435 | 2.1 | 2.1 | 10.5 | 1.6241 | 38.223 | 48.723 | 65 | 6 | 89441.82 | 114011.82
I&C Technicians | 2 | 35 | 2.6775 | 0.28 | 1.2285 | 0.5075 | 2.45 | 2.45 | 12.25 | 1.6241 | 44.5935 | 56.8435 | 65 | 6 | 34782.93 | 44337.93
DCS Engineer |  | 75 | 5.7375 | 0.6 | 2.6325 | 1.0875 | 5.25 | 5.25 | 26.25 | 1.6241 | 95.5575 | 121.8075 | 65 | 6 | 0 | 0
EH&S Field Engineer |  | 50 | 3.825 | 0.4 | 1.755 | 0.725 | 3.5 | 3.5 | 17.5 | 1.6241 | 63.705 | 81.205 | 65 | 6 | 0 | 0
TA's Controls & Mechanical |  | 80 | 6.12 | 0.64 | 2.808 | 1.16 | 5.6 | 5.6 | 28 | 1.875 | 101.928 | 150 | 65 | 6 | 0 | 0
Civil Craft | 6 | 42 | 3.213 | 0.336 | 1.4742 | 0.609 | 2.94 | 2.94 | 14.7 | 1.6241 | 53.5122 | 68.2122 | 65 | 6 | 125218.548 | 159616.548
Totals | 28 | [13 empty] | 562489.668 | 717007.668 | 154518
Labor Margin | 154518
Shipping
Material Mark Up | 419595
Misc & Contingency | 210378.5934
Consumable Mark Up | 3061.2
Margin | 787552.7934
Total Billing | 4417950.4614
Margin % | 17.83%