Page 1

PRIVATE TENDER FOR THE ELECTROMECHANICAL MONTAGE OF THE ELECTRIC TURBOGENERATORS & POWER ISLANDS FOR GENERATION OF JOSEFA CAMEJO PLANT, PUNTO FIJO,

EDO. FALCÓN.

CONDITIONS OF THE PRIVATE TENDER

1.- INTRODUCTION:

PACIFIC RIM ENERGY CONSORTIUM, according to what it is established in its Contractual Manual, has the pleasure of informing that it has pre-selected your company and invites you to participate in the Private Contest to contract the Electromechanical Montage of Three Dual Combustible Electric turbo generating Units including the Integral Montage of Islands of generation for the Josefa Camejo Plant, Municipio Autonomous Los Taques, falcon State.

Exposition of the Motive:  The Anonymous Company of Administration and Electric Foment (CADAFE) has contracted the services of Consortium PACIFIC RIM ENERGY, to execute Project IPC key in hand of the Generating Plant Josefa Camejo, Municipio Autonomous Los Taques, Falcon State, conformed by  Three

(03) Gas and Fuel Turbo Generating Units in open or simple axis with the possibility of work in a combined cycle in the future, of 150 Megawatts each, installed at open air, including montage and operation.

2.- OBJECTIVE:

The objective of the present process is “THE CONTRACT FOR ELECTROMECHANICAL MONTAGE OF THE TURBO GENERATORS IN THE ELECTRIC PLANT JOSEFA CAMEJO”

3.- SCOPE OF THE JOB TO BE CONTRACTED:

3.1.- General Scope:

The objective of this tender, is the construction, within the limits of the Electric plant Josefa Camejo, of Three (3) Power Islands, starting from the erection of each one of the main and Auxiliary components of the Turbo generators Siemens-Westinghouse W501F, the installation of ducts of insulated bars, switches, switchboards, elevating transformer and portico for high voltage, to the   potency wiring and control that will allow its complete functionality in an optimal way. The job to be contracted includes supplying all the materials, equipment, necessary direct and indirect labor and complete execution of the job object of this contract, according to the norms and standards indicated by CADAFE, COVENIN and the applicable current normative.

Only the bare Turbines and Generators, without enclosures, auxiliary equipments

or assembly of any kind, will be placed over the foundations by the contractor in charge of Heavy Transportation of equipments. The chosen Contractor’s Electromechanical Montage will start at the precise moment in which the leveling and alignment activity of these equipments as well as the due assistance for the correct placement begins.

The scope includes Construction and Integral Montage of the Power Islands of Generation, according to details in the following paragraphs, up to its mechanical completion. The scope includes the permanence of a group of a selected key personnel from the Contractor’s Company, tools and basic equipment for the Technical assistance in the (Commissioning) and the Start Up and Performance Tests, according to what is required by PACIFIC RIM ENERGY. The responsibilities of the Contractor that results elected, particularly in the activities of Commissioning and Start Up of the Plant will be limited only  to supplying labor, (direct labor), as well as tools and equipment necessary for its execution.

3.2.- Scope of Supplies and Services of the Job:

• All consumable materials, including, but not limited:

Tie rap, epoxy or no epoxy sealers for multi-conductor cables

(Armed or unarmed), insulating bands, electrodes, oxygen, acetylene,

graphite grease or similar for pulling of cables, consumable kits, (sandpaper,

special sealers for connectors, etc.) for the connection of Fiber optic, and all necessary materials that warrant the correct installation of the TG.

• All minor Materials, not included either by being supplied by Siemens-

Westinghouse or by other manufacturer of equipment, necessary for the correct and integral installation and connection of such equipment including, but no limited to: braces, unistrut clamps, sections of flexible conduit, accessories for drain pipe, supports, connectors and electrical terminals of low, medium and high  voltage, bands or thermo retractile sleeves, numeration for the termination of cables, medium and high voltage terminal cups, tow press, PVC covers, paints, accessories for electric canalization, Hilti anchor bolts,  connectors and accessories for fiber optic , etc. The quantities of material will be estimated in each “partida”. In case the attached technical information is not sufficient, Pacific Rim Energy could send additional information during the time of the elaboration of the Offers, according to what it is required.

.

• All non-destructive trials and testing that are necessary or required according to CADAFE National and International Norms

applicable to all equipment, cables or installations in the job, objective of this tender.

• Costs for providing Electric Energy, raw water, drinking water and water for experiments that are necessary.

• All direct labor, according to the actual Construction Collective Contract.

• All supervision and Construction Managing Staff, such as Project Manager, Residing Engineer, Planner, QA/QC, Safety , Health and Environment Supervisor, etc.

• Elaboration of drawings “As Built” in electronic form as well as hard copies.

• All Tools and Equipment for Construction in sufficient qualities and quantities, such as: scaffolds, cranes, forklifts, various tools, equipment, tube threading

Equipment for cable pulling, terminals press, equipment and tools for fiber optic, and any other necessary equipment or tool for the correct execution of the job.

• Provisional Installations for the personnel that works directly with the Contractor that is selected, which will be located in the area that Pacific Rim Energy Consortium establishes for such objective.

• Personnel Transport, and the surveillance that the contracting company considers necessary to safeguard its own installations tools and equipment.

• All Insurances, policies and legal representation required in the tender.

• The favored contracting company that becomes selected must submit all certificates of quality of all material employed as well as certificates of trials and testing that are necessary according to the type of work to be executed, such as

Cables megawatts, Hi-Pot tests, dielectric oil testing, relay, and other that could be necessary for CADAFE Procedures.

• Above Mentioned Costs, all those that can not be included as direct costs in the individual “Partidas” such as provisional installations, surveillance, bonuses and other similar ones, must be included in the percentage of administrative or indirect expenditure. Therefore Pacific Rim Energy will consider that the percentage of administrative expenditure include all the concepts above named.

3.3.- Description of the Scope of the “Partidas”  of the Job:

The “Partidas” in Attachment B will accomplish what it is established in this tender and its attached documentation, including what it is specified in what follows:

3.3.1.- Scope of Montage of Equipment belonging to the Econopack.

Includes the montage and Mechanical Assembly, Electric, Instrumentation and

Controls of the equipment that are part of the Econopack W501F supplied by Siemens-Westinghouse, according to the Document  “SCOPE OF ELECTROMECHANICAL MONTAGE ” No. 1123-05-90-M01-TEC002 attached, this Tender and all other attached Technical Documents, include:

• Three (3) Turbines and  Three (3) Generators, including support structures, conduit piping , oil and combustible piping enclosures, cables, anchor bolting, connections and the erection and integral montage up to its finishing touches in all and each of the components supplied by SWPC. PACIFIC RIM ENERGY CONSORTIUM will deliver to the contractor that wins the tender all the foundations, already finished, with its anchor bolts for the fixation of the equipment to such foundations. Only in the particular case of the Turbine and the Generator, the equipment will be placed on its foundation by third parties.

• The  contractor that wins the tender must, on its own, transport parts and pieces for assembling each Turbo generator from the PACIFIC RIM ENERGY CONSORTIUM Warehouse, located inside the perimeter of the Job, to its respective foundations, anchor bolting  and leveling them, and beginning its integral assembly, according to  the Drawings and Documents of Manufacturers.

• Montage of the totality of the Auxiliary Equipment of the Three Turbo generators:

Including the Electric package, Mechanical Package, Lubricant Oil Coolers, Filters, Filter House, the Electric Packets, Contact Shoe Combustible Package, Contact Shoe Equipment against Fire, Starter Package (Starter Motor and Gearshift box), Packet of Compressed Air, TXP System of Control, Switchboard and Continues Current System, Batteries Bank, Air-Air Coolers, TEWAC Coolers, System of the excitatriz ??of the Generator, Chimney (exhaust Rack), transitional duct for the chimney, and any other that is part of the supplying Econopack from Siemens Westinghouse. The PACIFIC RIM ENERGY CONSORTIUM will hand down to the Contractor that resulted elected, the foundations for the equipments with its anchor-bolts. The chosen Contractor must transport, on its own, the auxiliary equipment of each mentioned Turbo generator, as well as any other part or piece from the Warehouse of the PACIFIC RIM ENERGY CONSORTIUM located in the perimeter of the Job, to their respective foundations, anchor bolting, leveling of the equipment, and starting initial integral assembly, according to the Manufacturers Drawings and Documents

• Montage, Installation and Electric Cabling and Control of Siemens TXP Control System,

including the local consoles (located inside the respective Electric packages of each Turbo generating Unit) as well as the main remote Control Unit (server) located in the Main Control Room.  The TXP cabling includes cables and fiber optic connection. The Fiber Optic connection will be supplied by Pacific Rim Energy, however, the connectors and connection kits must be under the account of the contractor.

• Communication Cables between the TXP Server and the Main Control Room (TXP Server Unit) and the Plant Distributing System in the same Control Room (DCS for the B.O.P. and TG) this cable of communication can involve connections to the Network, digital  or fiber optic, whatever the case may be.

3.3.2.- Scope of the  Montage of the Equipments that do not belong to the Econopack.

The  Mechanic,  Electric, Instrumentation and Control of the Equipments that are not part of the W501F Econopack, but are an integral part of the  Scope of the Job of the Power Islands in this contract, according to the attached document ” SCOPE OF THE  ELECTRO-MECHANIC MONTAGE” No. 1123-05-90-M01-TEC002, this tender and other attached technical documents include:

• Three (3) complete Sets of Insulated Isophase Bar Ducts, including all the supporting structure , its installation and connections from the Generators terminals up to the terminal of the Main Switch, as well as from the exit of the Main Switch to the 115 kV Transformer Elevator, including the derivation towards the 4,16 kV Auxiliary redactor.

• Three (3) 24 kV Main Switches (11500 A nominal and 100 kA RMS Symmetric Fault), including its supporting structure, connections to the Insulate Bar such, and the Electric Cables for action control, relays, signals and communications.

• Three (3) Elevating Transformers (Triphasic in Configuration Delta-Estrella with  neutral to Earth), One of them (1) with a transforming relation of 16,5/115 kV and two (2) with a relation of Transformation of 15/115 kV, all of them 230 MVA / OFAF, including the montage of the cask, assembly of all auxiliary equipment, relays, protections, transformers of potency and current, preparation, filtering and filling of dielectric oil, up to the final and total assembly of it, including necessary operational testing, according to the applicable National and International CADAFE Norms, including testing of equipment for electric protection, current and voltage transformers, earthen and associated equipment. The installation includes the supply and construction of terminals of low and high voltage

Page 7

for the transformers.

• Three (3) Transformers For Auxiliary Services (Of Triphasic Configuration Delta-Estrella with neutral to Earth), One (1) of them with a transforming relation of 16,5/4,16 kV and two (2) with a transforming relation of 15/4,16 kV, all of them 12,5 MVA / ONAN/ONAF,

Including the montage of the cask, assembly of auxiliary equipment, preparation, filtering and filling with dielectric oil, to the final and total assembly of it, including the installation and testing of equipment for electric protection, Current and Voltage Transformers, earthen and associated equipment. The installation includes the supply and construction of the low and High Voltage terminals for the transformers.

• Six (6) Transformers For Auxiliary Services (Of Triphasic Configuration Delta-Estrella with neutral to Earth ), One(1) of them with a transforming relation of 4,16/0,480 kV ONAN/ONAN with a power of 2800 kVA Including the montage of  the cask, assembly of Auxiliary equipment, preparation, filtering and filling with dielectric oil, to the final and total assembly of it , including necessary operational testing, according to the applicable National and International CADAFE Norms, including testing of equipment for electric protection, current and voltage transformers, earthen and associated equipment. The installation includes the supply and construction of the low and High Voltage terminals for the transformers.

• One (1) Switch Board or Cell at SG-3001 (Switchgear of a Shelter type) Triphasic with two Bars at Medium Voltage fed by 4, 16 kV, connected up stream to two (2) main feeds (Coming from two Trx Aux.), and connected downstream towards Ten (10) loads, known as: 1 Trx Auxiliary Services of MT, 2 Cells for Compressors, 2 Starter Motors, 2 Fuel Oil Pumps, 2 Transformers for Auxiliary Services 480 V and 1 tie in with a switchboard 2. The installation of the switchboards include its transportation inside the perimeter of the JOB, its placement and fixation, as well as the supply, fabrication and the connection of the terminals of entry to the bar and of exit towards all the loads.

• ONE (1) Switchboard  o Cell at SG-3002 (Switchgear of a Shelter type) Triphasic with two Bars of Medium Voltage fed at  4,16 kV,  connected up stream to

Three (3) main feeds (Coming from two Trx. Aux. + Black Start), and connected downstream towards Nine) loads, known as: 1 Trx Auxiliary Services of MT, 1 Compressor 1 Starter Motors, 1 Fuel Oil Pump , 2 480 V Transformers for Auxiliary Services, 1 tie in with a SG-3001 switchboard and tie in with 2 SG-3003 switchboard. The installation of the switchboards include its transportation inside the perimeter of the JOB, its placement and fixation, as well as

Page 8

the supply, fabrication and the connection of the terminals of entry to the bar and of exit towards all the loads.

• ONE (1) Switchboard o Cell SG-3003 (Switchgear of a Shelter type) Triphasic with two Bars of Medium Voltage fed at 4, 16 kV, connected up stream to two (2) main feeds (Coming from SG-3002), and connected down stream to six (6) loads, known as: 1 Trx Auxiliary Services of MT, 1 Compressor, 2 480 V Transformers for Auxiliary Services, 2 Auxiliary Services for S/E 115 kV. The installation of the switchboards include its transportation inside the perimeter of the JOB, its placement and fixation, as well as

• Three (3) Switchboards of low Voltage (CP-3001, CP-3002 y CP-3003), in 480 V Low Voltage Triphasic, with two Bars fed through transformers, from the switchboards of Medium Voltage, that serve all the loads  for the power islands of generation that are fed at this nominal tension.

• ONE (1) 13,8/4,16 kV 7500 kVA Transformer that supplies emergency feeding. The cables will be supplied by Pacific Rim Energy; however, the contractor will supply and install the terminals in Medium and High Voltage

• ONE (1) Black Start Equipment ( Black Start). Includes the totality of the Works necessary for the installation of two Generators (Operating in parallel) each of 2500kVA at 4,16 kV, put in motion by Diesel Motors. This equipment comes assembled over a connector shoe, and the scope contemplates its placement over the foundation, leveling, anchor bolting and connection of its electric switchboards.

• Installation of the Battery Room and UPS. It refers to the installation and connection of the batteries to be installed in a room built by a third party for such objective. It includes the installation of the charger Equipment or UPS.

• Power Line cables and Connections among all the named equipments, according to attached Unifilar General Diagrama No. 1123-05-90-E03-001. The electric cables will be supplied by Pacific Rim Energy; however, the contractor will supply and install the Medium Voltage terminals. It includes all loads from the Low Voltage Power generating Islands (480 V, 208 V y 120 V)

• Installation of Equipment of High Voltage in Exit Porticos: (It does not include the erection of the portico or its foundation). Includes the bare conduits from the terminal of High Voltage of the Transformer to the insulators in the porticos (it does not include the supply of bare conduits) but includes the connection, the terminals and accessories (hardware) necessary for the objective. This job includes the installation of all the equipment located in such portico, such as

Page 9

insulators, hardware, fasteners, winds, etc. The portico mentioned above constitutes the limit of battery of work on High VOLTAGE CONTRACTED IN THIS Tender, before this; the connection from the Portico to the S/E will be carried out by Third parties. The structure of the Portico will be supplied by a third party.

• Cables of Potency and of control for all equipment already mentioned through the support for the ducts, conduit that are superficial or embedded in concrete, piping between each other and up to the control room or to the main control room. Includes the supply and installation of the High, Medium, and Low wattage cables or associated bare conductors (The cables and/ or conductors will be supplied by Pacific Rim Energy).

Start Up Tests: The scope of it includes, as it was indicated above, the execution of all linking tests between the control systems of the power islands mentioned above, as part of Pre-commissioning. The scope also includes the assistance from the Contractor Personnel for the execution of cool and hot trial operations, as part of Commissioning. The start up activities of the Power Units will be headed by THE Final CLIENT (CADAFE), with the assistance of (Technical Field Assistance) and the technical assistance of Pacific Rim Energy. The contractor that resulted chosen will need to have to Client’s disposal the minimal necessary personnel, tools and equipment for necessary support for Start Up tests.

Therefore, the Offerers must indicate in their offer, in the document relating to Technical Assistance with regards to Start up Tests, the cost and the duration of such assistance. Pacific Rim Energy estimates that such time lapse will not be more than two months (2)  for TG.

The scope does not include the supply of mineral dielectric oil for the transformer elevator or the oil for the cooling system of the Econopack equipment. Power and Control cables will be supplied by Pacific Rim Energy. All Foundations and Duct Banks will be executed by another Contractor dedicated to Civil Works. The scope does not include montage of the electromechanical of the (B.O.P) such as the centrifugals for liquid combustible, gas or liquid combustible piping aloof to the Econopack, gas compressor, demineralization water plant, emission treatment plant, Gas tanks, Raw water tanks,  Drinking water tanks and Fire fighter System, and other equipment that are no part of the Power islands.

Page 10

Planning of Activities:

The Project is of a fast-track nature and for that reason the scope of the contract includes the correct planning of the activities and the supply of a Full Time Planner in site. On one hand, The Pacific Rim Energy Consortium has contracted from the Manufacturers of the main equipments the (SWPC Technical Field Assistance), and on the other hand, the technical assistance from a Company Overseas specialized in the Montage of Turbines and Generators, whose personnel will exercise the Superintendence of Labors in the Field, and it is for this reason that the technical assistance during the phase of the Electromechanical Montage will be guaranteed by Pacific Rim Energy Consortium.

Time of Execution

Pacific Rim Energy Consortium plans to execute the Montage of each unit in the Econopak in a period no longer than four (4) months, from its beginning to the mechanical completion.

In any case the time Lapse for the execution will be an important factor in the technical evaluation of the offers.

Technical Specifications: In the attached documents to this Price Consulting Document (contained in a Compact Disc) are the technical specifications created by the Engineering Consulting firm designated for such objective. These specifications are complimentary and form an integral part of this Tender.

4.- DOCUMENTOS SUPPLIED BY PACIFIC RIM ENERGY CONSORTIUM

The technical documentation technical related to the present Bid will be supplied by PACIFIC RIM ENERGYCONSOTIUM electronically, in Laser Compact, or in hard copies of the same, according to the applicability of the case. All information provided is confidential and must not be either shared, or reproduced, and it must be returned to PACIFIC RIM  ENERGY CONSORTIUM  by all participants to the term of this bid.

5.- OFFER LANGUAGE:

The Offers and all other documents must be presented in the Castilian language.

6.- OFFER CURRENCY:

The Offers must be expressed in Bolívares.

7.- OFFER PRESENTATION:

The Offers must be presented according to:

a) On Monday 09 of July 2007, at the following address: Av.

Principal de El Bosque, Torre Credicard, piso 8, oficina 86-87, Chacaito, Caracas,

To the attention of: Comité de Licitaciones del CONSORCIO PACIFIC RIM ENERGY

b) The name of the company participating must be clearly indicated on the envelops

c) Manifestation of Will on the part of the participant company will be included (according to the model in ATACHMENT C)

d) The participating Company must present together with its offer, and in a separate envelop, Certified Copy of the current, where the objective of the company ios clearly explained, the identity of its legal representatives, faculties, and designations of power of attorneys, if that is the case. Also it must include the RIF and NIT Number of the Company. The company must also present its balance, Statement of profits and Losses and a Declaration of tax (Impuesto sobre La Renta) corresponding to the last three (3) fiscal years.

e) All the pages in the offer must be duly signed and with seals by the representative or legal person authorized by the company.

f) Participants will provide one (1) original and one (1) copy of the technical as well as of the economic offer. In case of discrepancies the original offer will prevail over the copy. The offers must be clearly identified.

g) Each participant must present an envelop marked with an “A” which includes the technical offer that relates to the technical Offer and another envelop marked with a “B” corresponding to The economic Offer, accompanied by a folder that contains the legal documents and required documents for this tender, duly sealed and identified(in a disc or hard copy) . The content in the mentioned envelops is detailed in ATTACHMENT “A “part of this document.

h) The opening of the Technical and Economic envelops will take place  in an internal  private act of PACIFIC RIM ENERGY CONSORTIUM.

i) The company must present the documentation that credits its experience in executing work and similar services.

j) The Offering Company is obligated to supply in its offer the address of the place to which  the notifications will be made to, as well as its telephone, fax numbers and email.

k) The participant will pay for all costs related to the preparation and presentation of its offer and they will be done at its sole cost and risk. PACIFIC RIM ENERGY CONSORTIUM will not recognize or reimburse any amount for such concept.

l) The unitary costs presented by participants in the offer will be firm and will remain fix during the execution of the Contract, will not be subjected to variation for any reason, except those indicated in it and that derive from no imputable causes to the participant  that is selected. The offers presented with adjustable prices or variables will be rejected.

m) In case a variation in quantity of work to be executed arises, after the reception of the offers, and prior to the signing of the contract, consequently PACIFIC RIM ENERGY CONSORTIUM could request to the participant to modify or adjust the price of the offer.

No one variation in the quantities of the job will mean a variation in the respective unitary prices or in the cost per unit.

8.- OFFERS WILL BE IN EFFECT UNTIL

The participants are obligated to maintain their offers for a period of sixty (60) calendar days, counted from the reception day of these, to secure the subscription to the respective contract, in case of being granted “Buena Pro”. Likewise during that lapse of time, the offers cannot be modified, or withdrawn.

The Offers can be renewed after expiring, if PACIFIC RIM ENERGY CONSORTIUM requires.

9.- CLARIFICATION OF THE PRESENT CONDITIONS:

Any Participant can request in writing before PACIFIC RIM ENERGY CONSORTIUM, the clarifications that it considers necessary, through electronic mail or fax number specified as follows: jdamico@prenergy.com, fax number: 0212-953-7995. The time for clarification will end 29 June  2007, and such consultations will be answered by PACIFIC RIM ENERGY CONSORTIUM through electronic mail, fax or written communication to the addresses indicated by each participant and without indicating its origins.

10.- MODIFICATIÓN OF THE PRESENT CONDITIONS:

PACIFIC RIM ENERGY CONSORTIUM could modify the present conditions up to the day of the present offers, and it will notify of it to participants, at no cost PACIFIC RIM ENERGY CONSORTIUM.

11.- CLARIFICATION OF OFFERS:

With the purpose of facilitating the examination and evaluation of the Offers, PACIFIC RIM ENERGY CONSORTIUM, could to its discretion request, to participants, to clarify their offers. The request for Clarification and the response will be done in writing, fax or electronic mail, and changes in prices, or in the substantial aspects of the offer, except those determined by arithmetical errors  and disparities in amounts when the criteria for evaluation is applied.

In case of existing some discrepancy between this document of invitation , the offer presented by the participant and the final contract. What is established in the contract will prevail.

12.- CRITERIA FOR GRADING:

PACIFIC RIM ENERGY CONSORTIUM will execute the evaluation of the proposals with the purpose of establishing a valid comparison between the presented offers by the participants, and to determine which of the offeres presented show a major advantage  to its interests.

efectuará la evaluación de las

propuestas con el fin de establecer una comparación válida entre las Ofertas

presentadas por los participantes, y determinar entre las consideradas aceptables,

las que ofrecen las mayores ventajas a sus intereses.

A tal efecto, el CONSORCIO PACIFIC RIM ENERGY tomará en consideración la

evaluación financiera y técnica que haga de cada uno de los participantes.

El CONSORCIO PACIFIC RIM ENERGY evaluará las ofertas técnicas y las

ofertas económicas de la siguiente forma:

1. Evaluación Técnica: Se evaluará la experiencia de la constructora, el

organigrama propuesto y su plan de trabajo (cronograma de ejecución).

El cronograma o tiempo de ejecución se considera un factor de suma

importancia y por ningún motivo podrá ser omitido en la oferta.

2. Evaluación Económica: Se evaluarán los Análisis de Precios Unitarios así

como los porcentajes de costos Indirectos. También será evaluado el Monto

Solicitado en calidad de Anticipo por las Contratistas oferentes.

13.- BUENA PRO Y MODALIDAD DE CONTRATACIÓN

Una vez evaluadas las ofertas, el CONSORCIO PACIFIC RIM ENERGY

procederá a negociar las condiciones particulares del contrato con aquella

empresa constructora que resultare con la mejor calificación técnico-económica.

En caso de no llegar a un acuerdo satisfactorio para ambas partes, el

CONSORCIO PACIFIC RIM ENERGY procederá a negociar con la empresa

constructora que hubiese quedado en segundo lugar y así sucesivamente.

Una vez acordadas las condiciones por ambas partes, será notificada la Buena

Pro a la empresa constructora que resultare favorecida.

La modalidad de contratación será a suma global.

14.- PLAZO PARA LA SUSCRIPCIÓN DEL CONTRATO O LA ORDEN DE

COMPRA:

Una vez notificado el otorgamiento de la Buena Pro, las partes suscribirán el

Contrato respectivo, dentro de los diez (10) días hábiles siguientes a la notificación

al beneficiario de la Buena Pro, cumplidos todos los requisitos exigidos en las

presentes condiciones.

15.- CONDICIONES GENERALES DEL CONTRATO A SER SUSCRITO:

15.1 SITIO PARA LA EJECUCIÓN DE LOS TRABAJOS:

La totalidad de los trabajos objeto de este Concurso serán ejecutados en el sitio

de la Obra, en Punto Fijo, Estado Falcón. El CONSORCIO PACIFIC RIM

ENERGY no reconocerá gastos de viaje, transporte o de envíos postales en

ningún caso, aún si la empresa favorecida realiza alguna parte de los trabajos o

prefabricación de alguno de los componentes en otra ciudad.

15.2 DOCUMENTACIÓN A SER SUMINISTRADA POR EL CONSORCIO

PACIFIC RIM ENERGY

Será por cuenta del CONSORCIO PACIFIC RIM ENERGY suministrar la siguiente

información técnica a la Empresa constructora que resulte adjudicada: a) Planos

y Documentos de la Ingeniería de Detalle de las Instalaciones a ser Construidas.

16.- CRITERIOS DE RECHAZOS DE LAS OFERTAS

Las Ofertas podrán ser rechazadas entre otras, por las siguientes causas:

a) Las Ofertas que no cumplan con las presentes Condiciones.

b) Ofertas cuyo período de validez sea inferior al solicitado en estas

Condiciones o no sean renovadas cuando así lo solicitare el CONSORCIO

PACIFIC RIM ENERGY.

c) Ofertas que incluyan información o datos falsos.

d) Ofertas que no estén firmadas por las personas que representan al

participante o que estén firmadas por personas naturales distintas a las

suficientemente autorizadas para representar a la empresa participante.

e) Aquellas Ofertas que no presenten la documentación obligatoria requerida

en las presentes condiciones.

f) Ofertas que provengan de un mismo proponente.

g) Las presentadas por personas distintas, naturales o jurídicas, si se

comprueba la participación de ellas o de sus socios, directivos o gerentes

en la integración o dirección de otro participante en el proceso.

h) La presentada por un participante respecto al que se haya determinado que

ha participado en prácticas de corrupción o prácticas fraudulentas en el

procedimiento de que se trate, o por aquél que pretenda un resultado

favorable, ejerciendo presión y/o influencia sobre los empleados del

CONSORCIO PACIFIC RIM ENERGY.

i) Cuando las Ofertas no se ajusten a las Especificaciones Técnicas

establecidas en estas Condiciones.

17.- FIANZAS Y SEGUROS:

El participante que resulte favorecido con la Buena Pro deberá presentar a plena

satisfacción del CONSORCIO PACIFIC RIM ENERGY las siguientes Fianzas y

Seguros:

17.1.- FIANZA DE ANTICIPO

En el caso de que el CONSORCIO PACIFIC RIM ENERGY otorgue un anticipo

equivalente a un porcentaje del monto total de la Oferta, la empresa beneficiada

con la Buena Pro deberá presentar una fianza de anticipo detenderamente notariada,

emitida por una institución bancaria o empresa de seguros, de reconocido

prestigio, domiciliada en el país y detenderamente autorizada por la Superintendencia

de Bancos y/o de Seguros, según sea el caso, a favor del CONSORCIO PACIFIC

RIM ENERGY“ (según modelo del ANEXO D).

17.2.- FIANZA DE FIEL CUMPLIMIENTO

Previo al pago del anticipo la empresa beneficiada con la Buena Pro deberá

presentar, conjuntamente con la fianza de anticipo, una fianza notariada de fiel

cumplimiento emitida por una institución bancaria o empresa de seguro de

reconocido prestigio y domiciliada en el país, detenderamente autorizada por la

Superintendencia de Bancos y/o de Seguros, a favor del CONSORCIO PACIFIC

RIM ENERGY equivalente al 10% del monto total del contrato respectivo, para

garantizar la fiel y oportuna prestación de los servicios (según modelo del ANEXO

E).

17.3.- FIANZA DE BUENA CALIDAD

A la culminación de la ejecución de la obra y la entrega de los productos y

documentos derivados del mismo, la empresa beneficiada con la Buena Pro

deberá presentar fianza notariada de Buena Calidad otorgada por una institución

bancaria o empresa de seguros de reconocido prestigio domiciliada en el país y

detenderamente autorizada por la Superintendencia de Bancos ó de Seguros, según

sea el caso, a favor del CONSORCIO PACIFIC RIM ENERGY, para garantizar

esta última, la buena calidad de los servicios y el producto derivado de la

prestación de los mismos, el cual debe estar ajustado a las características reales o

condiciones del terreno. Dicha Fianza tendrá una vigencia de dos (2) años

contados a partir de la culminación o recepción definitiva de los servicios. (según

modelo del ANEXO F).

17.4 FIANZA DE RESPONSABILIDAD LABORAL:

LA CONTRATISTA presentará una Fianza de Responsabilidad Laboral, por la

cantidad equivalente al diez por ciento (10%) del monto del Contrato, para

garantizar a EL CONSORCIO el cumplimiento por parte de LA CONTRATISTA de

todas las obligaciones laborales y de seguridad social, legales o contractuales,

frente a sus trabajadores, derivados de la ejecución del TRABAJO bajo el

presente CONTRATO. La presente fianza se mantendrá vigente hasta catorce

(14) meses después de la fecha del Acta de Aceptación Provisional, siempre y

cuando LA CONTRATISTA presente los finiquitos laborales de cada uno de sus

trabajadores homologados por la Inspectoría del Trabajo de la zona donde se

ejecutó el TRABAJO, con constancia emitida por dicho organismo donde se

indique que no existen reclamaciones pendientes por tales conceptos contra LA

CONTRATISTA.

Queda entendido entre las partes que esta fianza será presentada por LA

CONTRATISTA antes de iniciar los trabajos.

17.5 PÓLIZAS DE SEGURO

17.5.1 LA CONTRATISTA suscribirá y mantendrá vigentes durante el plazo de

ejecución del CONTRATO y el de sus prórrogas, si las hubiere, pólizas de

seguros que cubran todos los riesgos de sus respectivos empleados

asignados al cumplimiento de la ejecución de los TRABAJOS, incluyendo

pero sin limitarse a muerte, lesiones, enfermedades y accidentes.

17.5.2 LA CONTRATISTA suscribirá y mantendrá vigente, durante el tiempo de la

ejecución del TRABAJO y el de sus prórrogas, si las hubiere, y hasta la

RECEPCIÓN PROVISIONAL, con compañías aseguradoras aceptadas por

EL CONSORCIO, y presentará antes del inicio de los TRABAJOS, a

satisfacción de EL CONSORCIO, las siguientes Pólizas de Seguros:

a) Pólizas de Responsabilidad Patronal, para cubrir la diferencia entre el

monto de la indemnización que corresponda según la Ley Orgánica

del Trabajo, Ley Orgánica de Prevención, Condición y Medio

Ambiente del Trabajo y Ley del Seguro Social y/o la Convención

Colectiva del Trabajo aplicable, de acuerdo con los límites

estipulados en dicha normativa. En las áreas donde no rija el Seguro

Social Obligatorio, la póliza deberá cubrir los límites previstos en la

referida Convención Colectiva del Trabajo aplicable. Esta póliza

deberá estar vigente hasta la fecha de la RECEPCIÓN

PROVISIONAL y con los límites de cobertura acordados entre las

PARTES, por persona y por evento.

b) Pólizas de Responsabilidad Civil General, para amparar lesiones o

muerte de personas, así como para cubrir daños o pérdidas de

bienes de EL CONSORCIO o de terceras personas. Dichas pólizas

deberán contener la Cláusula de Responsabilidad Civil Cruzada, y

deberá expresar que La Aseguradora renuncia a los derechos de

subrogación que pudiera ejercer en contra de EL CONSORCIO o su

personal. Estas pólizas deberán estar vigentes hasta la fecha de la

RECEPCIÓN PROVISIONAL y con límites de cobertura que

convengan LAS PARTES, por persona y por evento. Es entendido

que estas pólizas y sus coberturas, sólo coadyuvan al cumplimiento

de la responsabilidad que LA CONTRATISTA asume frente a

terceros, pero en ningún caso limita, libera o exime de las

obligaciones que a cargo de LA CONTRATISTA puedan derivarse de

la ejecución del TRABAJO y construcción de La Obra frente a

terceros.

c) Pólizas de Responsabilidad Civil de Vehículos, básicas y con exceso

de límites por ocurrencia, para cubrir lesiones corporales o muertes

de personas y daños a bienes de terceros, y para cubrir gastos de

defensa legal, ambas de acuerdo a lo convenido entre las PARTES.

Estas pólizas deberán contener una cláusula de Restitución

Automática y de Predios Privados.

d) Pólizas de Todo Riesgo de Construcción, para cubrir cualquier

pérdida física, Responsabilidad Civil General por todo riesgo de

construcción o los daños de las facilidades e instalaciones, hasta por

el precio total del presente CONTRATO, incluyendo todos los

EQUIPOS Y MATERIALES que conforman La Obra, durante el

tiempo que dure su guarda y custodia, por una cantidad no

acumulada y acordada entre las PARTES.

18.- FORMA DE PAGO

La forma de pago será mediante anticipo por el porcentaje acordado entre las

partes, previa presentación del documento de pago correspondiente y la Fianza de

Anticipo por un monto equivalente; y el saldo restante mediante valuaciones

periódicas (mensuales) sobre hitos de avance o porcentajes de avance físico,

según sea acordado entre las partes. De dichas valuaciones se retendrá el

porcentaje del anticipo previamente otorgado para la amortización del mismo.

19.- SUSPENSIÓN Y TERMINACIÓN DEL PROCESO.

El CONSORCIO PACIFIC RIM ENERGY se reserva el derecho y podrá, cuando a

su juicio lo considere conveniente y en cualquier fase del proceso, suspender y

terminar este proceso, y tomar cualquier decisión que considere conforme a sus

intereses, en cuyo caso lo hará del conocimiento de los participantes mediante

notificación en no más de tres (3) días hábiles siguientes a la misma. En estos

supuestos no procederá indemnización alguna a los interesados o participantes ni

reembolso de gastos.

20.- VACÍOS NORMATIVOS

Cualquier otro asunto relacionado con, o derivado del presente proceso, no

expuesto en estas Condiciones para la selección, deberá tratarse exclusivamente

por escrito con el CONSORCIO PACIFIC RIM ENERGY.

21.- ÍNDICE DE ANEXOS

ANEXO A CONTENIDO DE LAS OFERTAS TÉCNICAS Y ECONÓMICAS

ANEXO B LISTADO DE PARTIDAS DE INGENIERÍA.

ANEXO C MODELO DE MANIFESTACIÓN DE VOLUNTAD PARA

PARTICIPAR EN EL PROCESO DE SELECCIÓN.

ANEXO D MODELO FIANZA DE ANTICIPO

ANEXO E MODELO FIANZA DE FIEL CUMPLIMIENTO

ANEXO F MODELO FIANZA DE BUENA CALIDAD

ANEXO A

CONTENIDO DE LAS OFERTAS TÉCNICAS Y ECONÓMICAS

1. SOBRE A: Los Sobres con la Información Técnica deberán contener:

1.1 Listado de Obras Ejecutadas durante los últimos cinco (5) años, incluyendo el

nombre completo de la obra, cliente, valor y fecha de ejecución.

1.2 Organigrama Propuesto para la ejecución de la Obra con los nombres del

personal clave.

1.3 Currícula Vitarum del personal Clave propuesto en su organización (como

mímino del gerente de proyecto, planificador, y líderes de área).

1.4 Fotocopia de las certificaciones de calidad (si las hubiere).

1.5 Organigrama de la Empresa con sus nombres y cargos.

1.6 Plan del Proyecto (En formato MS Project), y narrativa o estrategia de

ejecución.

2. SOBRE B: Los sobres con la información Económica deberán contener:

2.1 Carta de Presentación y Manifestación de Voluntad según el Anexo C.

2.2 Precio Total de la Oferta en Bolívares, tanto en letras como en números. En

caso de discrepancia prevalecerán las letras. En ningún caso los precios

incluirán el I.V.A.

2.3 Tabla Resumen de costos, indicando claramente las cantidades por los

siguientes conceptos:

2.3.1 Mano de Obra Directa, discriminando Horas Hombre y el Costo Directo Total.

2.3.2 Gastos de Administración e Indirectos, en porcentaje y monto.

2.3.4 Utilidad e Imprevistos Declarados, en porcentaje y monto.

2.3.5 Monto Total de la Oferta (sumatoria de los puntos anteriores).

2.3.6 Listado de Partidas indicando cantidades, precios unitarios y Totales. Se

deben incluir todas las partidas contenidas en el Anexo B.

2.3.7 Análisis de Precios Unitarios de Todas las Partidas.

2.4 Tabla de Tarifas por concepto de Maquinarias y Horas Hombre en Stand By.

2.5 Plazo de ejecución comprometido por escrito (en meses y días) de acuerdo

al cronograma presentado en la Oferta Técnica.

2.6 Cálculo del Factor de Sobrecosto de Labor Directa (Contrato Colectivo de la

Construcción).

3. SOBRE LEGAL:

Los sobres con la información Legal deberán contener una carpeta contentiva de

todo lo indicado en el punto 7.d de esta invitación.

ANEXO B

LISTADOS DE PARTIDAS

No. DESCRIPCIÓN CANTIDAD P. U. PRECIO

TOTAL

HORAS

HOMBRE

1

Montaje Electromecánico de Turbina

y Generador Econopack W501F

según anexos.

3

2

Montaje Electromecánico de todos

los Equipos Auxiliares del

Turbogenerador, según el Alcance

anexo.

3

3

Montaje de Ductos de Barras

Aisladas Isophase e Interruptor

Principal, según alcance anexo.

3

4 Montaje de Transformadores

elevadores 230 MVA, según anexo. 3

5 Montaje de Transformadores

Auxiliares 12,5 MVA, según anexo. 3

6

Montaje de Transformadores de

Servicios Auxiliares 2800 kVA, según

anexo.

6

7 Montaje de Celdas de media Tensión

(SG-3001,3002 y 3003) según anexo. 3

8 Montaje de Tableros de Baja Tensión

en 480 V, según alcance anexo. 3

9 Montaje de Transformador Auxiliar de

7500 kVA, según alcance anexo. 1

10 Montaje del Equipo de Arranque en

Negro, según alcance anexo. 1

11

Instalación de Equipos en el Pórtico

de Alta tensión, según alcance

anexo.

1

12

Cableado Integral de todos los

equipos de las Islas de Generación

según descrito en el alcance anexo.

1

13 Instalación de Banco de Baterías y

UPS. 1

14 Asistencia Técnica a las Pruebas en

Caliente y al Arranque de Planta. 1

Todos los Análisis de Precios Unitarios deberán cumplir con el Alcance

referido en este Pliego (punto 3) y con las especificaciones técnicas de

los Documentos de Ingeniería anexos en Disco Compacto, en particular

el Documento 1123-05-90-M01-TEC002.

PACIFIC RIM ENERGY podrá excluir alguna de las partidas anteriores

del Alcance de los Trabajos, previo a la Firma del Contrato.

ANEXO C

MODELO DE MANIFESTACIÓN DE VOLUNTAD PARA PARTICIPAR

EN EL PROCESO DE CONSULTA DE PRECIOS

Fecha:

Consulta de Precios N°:_______________

Señores:

CONSORCIO PACIFIC RIM ENERGY

Presente.-

Yo, (identificación completa del representante autorizado de la empresa),

actuando en mi carácter de Representante Legal (o persona autorizada) de la

empresa (identificación de la empresa), detenderamente facultado por los estatutos

sociales (o por sesión de Junta Directiva N°________________, o poder

otorgado ante_______________), por medio de la presente me dirijo a ustedes

en la oportunidad de manifestarles el interés de mi representada en participar en

la Consulta de Precios para la CONTRATACIÓN DEL MONTAJE

ELECTROMECÁNICO DE LAS ISLAS DE GENERACIÓN DE LA PLANTA

ELÉCTRICA JOSEFA CAMEJO”.

Mi representada declara conocer las condiciones y normas que rigen el proceso,

a las cuales me obligo.

Caracas, en fecha --------- de 2007.

(FIRMA DEL REPRESENTANTE AUTORIZADO DE LA EMPRESA)

------------------------------------------

Dirección:

E-mail:

Teléfonos:

Número de fax:

ANEXO D

MODELO FIANZA DE ANTICIPO

Yo,_____________, (colocar identificación del representante legal de la

empresa aseguradora), de nacionalidad _____________, mayor de edad, de

este domicilio y titular de la cédula de identidad _______________ actuando en

representación de la Sociedad Mercantil (colocar nombre de la empresa

aseguradora), inscrita en el Registro Mercantil _________________ de la

Circunscripción Judicial de _____________, el _________de _________, bajo el

Nro. ______, Tomo _______, en lo adelante denominada “LA COMPAÑÍA”,

suficientemente autorizado según se evidencia en ______________________,

declaro: Constituyo a mi representada en fiadora solidaria y principal pagadora

de la empresa: ________________________ (colocar identificación completa de

la empresa), Sociedad Mercantil inscrita en el Registro Mercantil________ de la

Circunscripción Judicial de _____________, el _________de _________, bajo el

Nro. ______, Tomo _______, en lo adelante denominado “EL AFIANZADO”

hasta por la cantidad de ____________ (colocar cantidad en letras y números),

para garantizar a CONSORCIO PACIFIC RIM ENERGY, domiciliado en

Caracas, detenderamente inscrito por ante el Registro Mercantil V de la

Circunscripción Judicial del Distrito Capital y Estado Miranda, en fecha 16 de

mayo de 2006, bajo el N° 11, Tomo 28 C, en lo sucesivo denominado “EL

ACREEDOR”, la Amortización y/o el reintegro del anticipo que por la cantidad

antes mencionada hará “EL AFIANZADO”, según lo establecido en el Contrato

cuyo objeto es la “CONTRATACIÓN DEL MONTAJE ELECTROMECÁNICO

DE LAS ISLAS DE GENERACIÓN TERMOELÉCTRICA DE LA PLANTA

ELÉCTRICA JOSEFA CAMEJO”. La presente fianza empezará a regir a partir

de la fecha en que “EL AFIANZADO” reciba el anticipo mencionado de parte

de “EL ACREEDOR” según contrato derivado de la Consulta de Precios Nº

_____ y estará vigente hasta la total amortización o devolución del anticipo

señalado y que “EL ACREEDOR” expida el finiquito correspondiente.

Asimismo, “LA COMPAÑÍA” renuncia expresamente a los beneficios

acordados en los artículos 1.833, 1.834 y 1.836 del Código Civil. Se fija como

domicilio especial, a los efectos de este contrato, la ciudad de Caracas a la

jurisdicción de cuyos Tribunales las partes declaran someterse, con exclusión de

cualquier otra.

ANEXO E

MODELO FIANZA DE FIEL CUMPLIMIENTO

SUMA AFIANZADA:

Bs.

VIGENCIA:

DESDE:

HASTA:

Yo, venezolano, mayor de edad, de este domicilio, titular de la Cédula de

Identidad Nº_______, procediendo en mi carácter de Apoderado de la Sociedad

Mercantil Compañía Anónima de Seguros

(En lo adelante denominada la Compañía), inscrita ante el Registro Mercantil, en

fecha _____, anotada bajo el Nº ____, tomo___, registrada en la

Superintendencia de Seguros bajo el Nº ____ carácter este que se evidencia de

instrumento-poder otorgado por ante la Notaria Pública ___________ de _______,

en fecha anotado bajo el Nº ___, tomo ___, de los libros de autenticaciones

llevados por esa Notaria, y en acatamiento a lo resuelto por la Junta Directiva, en

su sesión de fecha, declaro: de acuerdo con las Condiciones Generales para las

fianzas, cuyo texto se encuentra autenticado ante la Notaria Pública _____, en

fecha __ de ___ de_, bajo el Nº ___, tomo ____, y salvo lo establecido en las

Condiciones Especiales de esta fianza, las cuales son de preferente aplicación,

constituyo a mi Representada en Fiadora Solidaria y Principal Pagadora de la

Sociedad Mercantil, inscrita por ante el Registro Mercantil en fecha ___ de ____

de _____, anotada bajo el Nº ____, y última modificación realizada por ante el

Registro Mercantil _____, en fecha ___ de de__, anotada bajo el Nº ____, tomo

______, en lo adelante denominada EL AFIANZADO, hasta por la cantidad de

Bolívares con 00/100 (Bs._________), para garantizar a CONSORCIO PACIFIC

RIM ENERGY, , domiciliado en Caracas, detenderamente inscrito por ante el Registro

Mercantil V de la Circunscripción Judicial del Distrito Capital y Estado Miranda, en

fecha 16 de mayo de 2006, bajo el N° 11, Tomo 28 C, en lo sucesivo denominado

EL ACREEDOR, en fiel, cabal y oportuno cumplimiento por parte de EL

AFIANZADO, de todas y cada una de las obligaciones que resulten a su cargo y a

favor de EL ACREEDOR, según lo establecido en el Contrato cuyo objeto es la

“CONTRATACIÓN DE LA CONSTRUCCIÓN DEL MONTAJE

ELECTROMECÁNICO DE LAS ISLAS DE GENERACIÓN TERMOELÉCTRICA

DE LA PLANTA ELÉCTRICA JOSEFA CAMEJO”, en virtud del otorgamiento de

la Buena Pro.

La presente fianza estará vigente hasta que se efectúe la Recepción Definitiva a

satisfacción de EL ACREEDOR de los servicios prestados y la entrega de los

productos derivados de los mismos.

LA COMPAÑÍA renuncia expresamente a los beneficios acordados en los

artículos 1.833, 1834 y 1836 del Código Civil,

Se elige como domicilio especial, para todos los efectos del presente contrato de

fianza, a la ciudad de Caracas, a cuya jurisdicción las partes declaran someterse

con exclusión de cualquier otra.

ANEXO F

MODELO DE FIANZA DE BUENA CALIDAD

Yo, ___________, (colocar identificación del representante legal de la empresa

aseguradora), de nacionalidad ________, mayor de edad, de este domicilio y

titular de la cédula de identidad ______ actuando en representación de la

sociedad mercantil (colocar nombre de la empresa aseguradora), inscrita en el

Registro Mercantil _____ de la Circunscripción Judicial de _____, el ____ de

____, bajo el Nro. _____, Tomo ___, en lo adelante denominada “LA

COMPAÑÍA”, suficientemente autorizado según se evidencia en

______________, declaro: constituyo a mi representada en fiadora solidaria y

principal pagadora de la empresa: _______________ (colocar identificación

completa de la empresa), sociedad mercantil inscrita en el Registro Mercantil

______ de la Circunscripción Judicial de _____, el ___de ___, bajo el Nro. ____,

Tomo ______, en lo adelante denominado “EL AFIANZADO” hasta por la

cantidad de ______ (colocar cantidad en letras y números), para garantizar a

CONSORCIO PACIFIC RIM ENERGY, domiciliado en Caracas, detenderamente

inscrito por ante el Registro Mercantil V de la Circunscripción Judicial del Distrito

Capital y Estado Miranda, en fecha 16 de mayo de 2006, bajo el N° 11, Tomo 28

C, en lo sucesivo denominado “EL ACREEDOR”, la buena calidad de la obra

ejecutada y el producto derivado de la ejecución de la misma, la cual debe estar

ajustada a las características reales o condiciones del terreno, a ser

suministrados por parte de “EL AFIANZADO”, según lo establecido en el

Contrato cuyo objeto es la “CONTRATACIÓN DE LA CONSTRUCCIÓN DEL

MONTAJE ELECTROMECÁNICO DE LAS ISLAS DE GENERACIÓN

TERMOELÉCTRICA DE LA PLANTA ELÉCTRICA JOSEFA CAMEJO”, en

virtud del otorgamiento de la Buena Pro

La presente fianza empezará a regir a partir de la instalación definitiva de los

bienes objeto de dicho contrato y estará vigente por los dos (02) años

siguientes. Asimismo, “LA COMPAÑÍA” renuncia expresamente a los

beneficios acordados en los artículos 1.833, 1.834 y 1.836 del Código Civil. Se

fija como domicilio especial, a los efectos de este contrato, la ciudad de Caracas

a la jurisdicción de cuyos tribunales las partes declaran someterse, con

exclusión de cualquier otra.

Helpful translations

FABRICATION, ERECTION, TESTING, PAINTING, GROUTING ETC FOR PART ‘A’ COVERS POWER HOUSE BUILDING CONSISTING OF TURBINE BAY & ELECTRICAL / CONTROL ROOM BAY AND PART ‘B’ COVERS BUNKERS, BUNKER BAY & PIPE RACK INCLUDING SUPPLY OF ALL MATERIALS EXCEPT THOSE PROPOSED TO BE SUPPLIED BY BHEL FOR 2 X 250 MW UNITS (UNIT 8 & 9) AT HARDUAGANJ THERMAL POWER STATION (HTPS) OF UPRVUNL AT HARDUAGANJ, UP.”

PROVIDING ALL SERVICES AS STIPULATED IN THE TENDER SPECIFICATION FOR HANDLING, SHIFTING OF MATERIALS FROM PROJECT STORE/ STORAGE YARD TO ERECTION SITE, PRESERVATION INCLUDING TOUCH UP PAINTING, WATCH & WARD, CHECKING, CHIPPING AND LEVELING OF FOUNDATIONS, IF NECESSARY, PRE-ASSEMBLY, ERECTION, ALIGNMENT, GROUTING, WELDING, RADIOGRAPHY, LPI/MPI TESTING WHEREVER REQUIRED, HEAT TREATMENT, APPLICATION OF THERMAL INSULATION, FINISH PAINTING ETC., INTERCONNECTION WITH GT EXHAUST ALONG WITH DIVERTER DAMPER/ GUILLOTINE/ SEAL AIR FAN/ BYPASS STACK (HEIGHT OF APPROX 30 M) ETC (INCLUDING E & C OF ELECTRICAL, C & I SYSTEM REQUIRED FOR DIVERTER DAMPER BASED BYPASS STACK & HRSG OPERATION, BOTH FROM LOCAL & REMOTE, AS REQUIRED), HYDRAULIC TEST, AIR LEAK TEST, ALKALI BOIL OUT, CHEMICAL CLEANING, STEAM BLOWING, SAFETY VALVE FLOATING AND INCLUDING ERECTION AND DISMANTLING OF ALL TEMPORARY PIPING, VALVE PUMPS, TANKS ETC. REQUIRED FOR ABOVE OPERATIONS AND ALL COMMISSIONING ACTIVITIES INCLUDING POST COMMISSIONING, TRIAL OPERATIONS AND HANDING OVER, PG TEST OF 3 X 42 TON/HR. WASTE RECOVERY BOILERS AND CHIMNEY (HEIGHT OF APPROX 30 M) WITH ALL AUXILIARIES AND PIPING AT 1 X 37.2 MW APGCL-LAKWA PROJECT, ASSAM.

Generator based power plants

Diesel generators can be operated together (in parallel). The use of parallel running generators provides the advantages of more capacity, efficiency and redundancy. A power plant driven by diesel generators will typically include between three and six machines.

Generators can be connected together through the process of synchronization. Synchronization involves matching voltage, frequency and phase before connecting the generator to a live busbar. Failure to synchronize before connection could cause a high current short-circuit or wear and tear on the generator and/or its switch gear. The synchronization process can be done automatically by an auto-synchronizer module. The auto-synchronizer will read the voltage, frequency and phase parameters form the generator and busbar voltages, while regulating the speed through the engine governor or ECU (Engine Control Module).

Load can be shared among parallel running generators through load sharing. Like auto-synchronization, load sharing can be automated by using a load sharing module. The load sharing module will measure the load and frequency at the generator, while it constantly adjusts the engine speed to shift load to and from the remaining power sources. A generator will take active load if its speed is increased, while load is released if speed is decreased